## Defect Monitor 2020
Wokingham Micro Programme 2020 All Sites
Client ID | Plan | PLAN | PROCESSE4:R26O53E4:R24E4E4:Q53 | ORDER | ROAD NAME | Ward | Complete / On Site | Gullies | Manholes | Observations | Defects | Defect Completion Date | Inspected | Interim Inspection Date | Inspected | Signed off Year 1 | Inspected | Signed off Year 2
2853 |  | MICRO | 2000150 | 20-21 WBC | A321/580 - Church Street | Remenham, Wargrave & Ruscombe | YES | Complete | Complete | Third Party damage. PSS. Monitor |  |  | S Diton | 16th November 2020
3592 |  | MICRO | 2000153 | 20-21 WBC | U7878/9 - BAYLISS ROAD (All) 20-21 | Remenham, Wargrave & Ruscombe | YES | Complete | Complete |  |  |  | S Diton | 16th November 2020
3576 | 1 | MICRO | 1900637 | 19-20 WSP | U7775/13 - MENDIP CLOSE (Chiltern Dr to end, including loop) | Charvil | YES | Complete | Complete |  |  |  | S Diton | 16th November 2020
3695 |  | MICRO | 2000154 | 20-21 WBC | U7675/8 - LITTLE GLEBE (Pound Ln to Garde Ln, incl. Glebe Gdns) | Sonning | YES | Complete | Complete | Minor Ponding, End spur not done | End spur not done |  | S Diton | 16th November 2020
| 23DFT | MICRO | 1900373 | 19-20DFT | FAIRWATER DRIVE (Service rd nos 33-135) | Woodley | YES | Complete | Complete |  |  |  | S Diton | 16th November 2020
3526 | 7 | MICRO | 1900627 | 19-20 WSP | U7572/28 - WALLACE CLOSE (All) | Woodley | YES | Complete | Complete | Manhole covered | Manhole covered |  | S Diton | 16th November 2020
| 22DFT | MICRO | 1900556 | 19-20DFT | LARCH DRIVE (all adopted) | Woodley | YES | Complete | Complete |  |  |  | S Diton | 16th November 2020
3519 | 2 | MICRO | 1900623 | 19-20 WSP | U7571/17 - ROSEWOOD (Linden Rd to end) | Woodley | YES | Complete | Complete |  |  |  | S Diton | 16th November 2020
3521 | 3 | MICRO | 1900625 | 19-20DFT | U7571/29 - LINDEN ROAD (Nightingale Rd to end) | Woodley | YES | Complete | Complete |  |  |  | S Diton | 16th November 2020
3572 | 8 | MICRO | 1900636 | 19-20 WSP | U7772/30 - AUSTIN ROAD (Vauxhall Dr to Colemansmoor Rd) | Woodley | YES | Complete | Complete | Areas of stripping and machine damage | Areas of stripping and machine damage |  | S Diton | 16th November 2020
3570 | 12 | MICRO | 1900635 | 19-20 WSP | U7771/16 - GREENACRES AVENUE (A329 Reading Rd to end) | Winnersh | YES | Complete | Complete | 2x manholes covered | 2x manholes covered |  | S Diton | 16th November 2020
3583 | 13 | MICRO | 1901220 | 19-20 WSP | U7870/15 - CHATSWORTH AVENUE (No. 1 to no. 63) | Winnersh | YES | Complete | Complete |  |  |  | S Diton | 16th November 2020
3582 | 14 | MICRO | 1900638 | 19-20 WSP | U7870/10 - DANYWERN DRIVE (Robinhood Ln to Wedderburn Cl) | Winnersh | YES | Complete | Complete |  |  |  | S Diton | 16th November 2020
3602 | 15 | MICRO | 1900639 | 19-20 WSP | U7970/16 - LENHAM CLOSE (Western spur) | Winnersh | YES | Complete | Complete | Water WO valve partially covered | Water WO valve partially covered |  | S Diton | 17th November 2020
3332 | 31 | MICRO | 1900619 | 19-20 WSP | U7670/10 - EDENHAM CLOSE | Earley | YES | Complete | Complete |  |  |  | S Diton | 17th November 2020
4011 | 30DFT | MICRO | 1900558 | 19-20DFT | THE DELPH (include spurs and turning areas) | Earley | YES | Complete | Complete |  |  |  | S Diton | 17th November 2020
3246 | 25DFT | MICRO | 1900558 | 19-20 DFT | WHITTON CLOSE | Earley | YES | Complete | Complete |  |  |  | S Diton | 17th November 2020
3245 | 24DFT | MICRO | 1900558 | 19-20 DFT | FELIXSTOWE CLOSE | Earley | YES | Complete | Complete |  |  |  | S Diton | 17th November 2020
3516 |  | MICRO | 2000144 | 20-21 WBC | U7570/38 - RATBY CLOSE (Measham Way to end) | Hawkedon | YES | Complete | Complete |  |  |  | S Diton | 17th November 2020
3515 | 11 | MICRO | 1900622 | 19-20 WSP | U7570/101 - DODDINGTON CLOSE (Meldreth Way to granite setts) | Earley | YES | Complete | Complete |  |  |  | S Diton | 17th November 2020
4010 | 27DFT | MICRO | 1900558 | 19-20 DFT | MERRIFIELD CLOSE | Earley | YES | Complete | Complete |  |  |  | S Diton | 17th November 2020
4009 | 28DFT | MICRO | 1900558 | 19-20 DFT | LITTINGTON CLOSE | Earley | YES | Complete | Complete |  |  |  | S Diton | 17th November 2020
3500 | 10 | MICRO | 1900621 | 19-20 WSP | U7471/7 - NASH CLOSE (Hartsbourne Rd to end) | Earley | YES | Complete | Complete | Ponding to monitor |  |  | S Diton | 17th November 2020
3487 |  | MICRO | 2000145 | 20-21 WBC | U7369/30 - MALTBY WAY (Ryhill Way to Tilney Way) | Hillside | YES | Complete | Complete |  |  |  | S Diton | 17th November 2020
3300 | 16 | MICRO | 1900615 | 19-20 WSP | U7269/73 - MITFORD CLOSE (All) | Shinfield North | YES | Complete | Complete | Minor surface defect o/s 31 | Minor surface defect o/s 31 |  | S Diton | 17th November 2020
3301 | 17 | MICRO | 1900617 | 19-20 WSP | U7269/17 - REGIS CLOSE (All) | Shinfield North | YES | Complete | Complete |  |  |  | S Diton | 17th November 2020
3302 | 18 | MICRO | 1900616 | 19-20 WSP | U7269/18 - WOODSIDE WAY (All, not RBC-owned cway) | Shinfield North | YES | Complete | Complete |  |  |  | S Diton | 17th November 2020
|  | MICRO | 1900662 | 19-20 Housing | Drewett Close | Shinfield | YES | Complete | Complete | Minor ponding to monitor |  |  | S Diton | 18th November 2020
3483 |  |  | 2000151 | 20-21 WBC | U7368/12 - FAIRMEAD ROAD (Hollow Ln to Oatlands Rd) | Shinfield South | YES | Complete | Complete |  |  |  | S Diton | 18th November 2020
3475 | 19 | MICRO | 1900620 | 19-20 WSP | U7266/3 - ELIZABETH ROUT CLOSE | Shinfield South | YES | Complete | Complete | Minor ponding |  |  | S Diton | 18th November 2020
3656 |  | MICRO | 2000157 | 20-21 WBC | U8464/21 - ROWAN DRIVE (Belmont Rd to Old Wokingham Rd) | Wokingham Without | YES | Complete | Complete |  |  |  | S Diton | 18th November 2020
3643 |  | MICRO | 2000158 | 20-21 WBC | U8264/17 - GREENSIDE (Linkway to end) | Wokingham Without | YES | Complete | Complete |  |  |  | S Diton | 18th November 2020
3274 | 21 | MICRO | 1900609 | 19-20 WSP | U7965/29 - TICKENOR DRIVE (All) | Finchampstead North | YES | Complete | Complete | manhole covered o/s 27 | manhole covered o/s 27 |  | S Diton | 18th November 2020
3273 | 20 | MICRO | 1900609 | 19-20 WSP | U7965/28 - RADICAL RIDE (All) | Finchampstead North | YES | Complete | Complete | Minor ponding to monitor |  |  | S Diton | 18th November 2020
3277 | 24 | MICRO | 1900609 | 19-20 WSP | U7965/30 - CHALLENOR CLOSE (All) | Finchampstead North | YES | Complete | Complete | Manhole cover 0/s 23 | Manhole cover 0/s 23 |  | S Diton | 18th November 2020
3276 | 23 | MICRO | 1900609 | 19-20 WSP | U7965/26 - MCCARTHY WAY (spine road) | Finchampstead North | YES | Complete | Complete | Manhole covered @ j/w the spinney | Manhole covered @ j/w the spinney |  | S Diton | 18th November 2020
3275 | 22 | MICRO | 1900609 | 19-20 WSP | U7965/27 - MCCARTHY WAY (spur) | Finchampstead North | YES | Complete | Complete |  |  |  | S Diton | 18th November 2020
3542 |  | MICRO | 2000134 | 20-21 WBC | U7665/10 - BRAMSHILL CLOSE (Baird Rd to end) | Arborfield/Barkham | YES | Complete | Complete | 50m2 remedial outside Whitehall Mews | 50m2 remedial outside Whitehall Mews |  | S Diton | 18th November 2020
3686 |  | MICRO | 2000143 | 20-21 WBC | U8068/30 - OAKLANDS DRIVE (Cul-de-sac nos 8-22) | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 18th November 2020
3257 | 1DFT | MICRO | 1900555 | 19-20 DFT | LIME CLOSE | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 18th November 2020
3255 | 2DFT | MICRO | 1900555 | 19-20 DFT | SNOWBERRY CLOSE | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 18th November 2020
3254 | 4DFT | MICRO | 1900555 | 19-20 DFT | WALNUT CLOSE | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 18th November 2020
3259 | 3DFT | MICRO | 1900555 | 19-20 DFT | WISTERIA CLOSE | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 18th November 2020
3253 | 10DFT | MICRO | 1900555 | 19-20 DFT | APPLE CLOSE | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 18th November 2020
3251 | 7DFT | MICRO | 1900555 | 19-20 DFT | BEECHNUT CLOSE | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 18th November 2020
4007 | 11DFT | MICRO | 1900555 | 19-20 DFT | ROWAN CLOSE | Wokingham | YES | Complete | Complete | Minor ponding to monitor |  |  | S Diton | 19th November 2020
3252 | 9DFT | MICRO | 1900555 | 19-20 DFT | MAGNOLIA WAY (cul-de-sac) | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 19th November 2020
3250 | 6DFT | MICRO | 1900555 | 19-20 DFT | LINDEN CLOSE | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 19th November 2020
4006 | 12DFT | MICRO | 1900555 | 19-20 DFT | HAZEL CLOSE | Wokingham | YES | Complete | Complete | Minor ponding to monitor |  |  | S Diton | 19th November 2020
4182 | 14DFT | MICRO | 1900364 | 19-20 DFT | LAUREL CLOSE | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 19th November 2020
3258 | 13DFT | MICRO | 1900555 | 19-20 DFT | EVERGREEN WAY | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 19th November 2020
3252 | 8DFT | MICRO | 1900555 | 19-20 DFT | MAGNOLIA WAY | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 19th November 2020
3284 |  | MICRO | 2000141 | 20-21 WBC | U7968/40 - FALCON WAY (Kestrel Way to end, including spurs) | Wokingham | YES | Complete | Complete | Manhole covered NR Linnet Walk | Manhole covered NR Linnet Walk |  | S Diton | 19th November 2020
3448 |  | MICRO | 2000155 | 20-21 WBC | D8611/10 - RANCES LANE (Tattersall Cl to Waterloo Rd) | Wescott | YES | Complete | Complete |  |  |  | S Diton | 19th November 2020
3449 |  | MICRO | 2000156 | 20-21 WBC | D8611/50 - RANCES LANE (A329 Reading Rd to Tattersall Cl) | Wescott | YES | Complete | Complete | Minor ponding to monitor | Manhole frame loose, repair required |  | S Diton | 19th November 2020
3278 | 25 | MICRO | 1900610 | 19-20 WSP | U8268/3 - WATERLOO ROAD No's 97-139 | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 19th November 2020
3279 | 26 | MICRO | 1900612 | 19-20 WSP | U8268/2 - WATERLOO ROAD No's 141-175 | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 19th November 2020
3290 | 27 | MICRO | 1900613 | 19-20 WSP | U8268/58 - WATERLOO ROAD No's 177-195 | Wokingham | YES | Complete | Complete |  |  |  | S Diton | 19th November 2020
3538 |  | MICRO | 2000136 | 20-21 WBC | U7573/8 - WALTON CLOSE (Grays Cres to end) | Bulmershe & Whitegates | YES | Complete | Complete |  |  |  | S Diton | 19th November 2020
3537 | 9 | MICRO | 1900634 | 19-20 WSP | BRUCE RD (Wheble to Wheeble | Woodley | YES | Complete | Complete |  |  |  | S Diton | 19th November 2020
3571 |  | MICRO | 2000146 | 20-21 WBC | U7772/71 - REDWOOD AVENUE (Oak Dr to Holly Rd) | Loddon | YES | Complete | Complete |  |  |  | S Diton | 19th November 2020
3331 | 30 | MICRO | 1900618 | 19-20 WSP | U7570/73 - STOWMARKET CLOSE | Earley | YES | Complete | Complete |  |  |  | S Diton | 20th November 2020
3329 | 28 | MICRO | 1900618 | 19-20 WSP | U7570/27 - LEISTON CLOSE | Earley | YES | Complete | Complete | Minor ponding to monitor |  |  | S Diton | 20th November 2020
4008 | 26DFT | MICRO | 1900558 | 19-20 DFT | HARWICH CLOSE | Earley | YES | Complete | Complete |  |  |  | S Diton | 20th November 2020
3330 | 29 | MICRO | 1900618 | 19-20 WSP | U7570/17 - SOUTHWOLD CLOSE | Earley | YES | Complete | Complete |  |  |  | S Diton | 20th November 2020
3640 |  | MICRO | 2000148 | 20-21 WBC | U8169/3 - BUDGES ROAD (Ashridge Rd to Pigott Rd) | Norreys | YES | Complete | Complete | 2x manholes covered 2 areas cracking | 2x manholes covered 2 areas cracking |  | S Diton | 20th November 2020
3618 |  | MICRO | 2000138 | 20-21 WBC | U8068/18 - HEELAS ROAD (Meadow Rd to Mansfield Rd) | Emmbrook | YES | Complete | Complete |  |  |  | S Diton | 20th November 2020
3650 |  | MICRO | 2000149 | 20-21 WBC | U8269/25 - PLOUGH LANE (Bean Oak Rd to Binfield Rd) | Norreys | YES | Complete | Complete |  |  |  | S Diton | 20th November 2020
|  |  |  | 20-21 WBC | EMMBROOK ROAD | Emmbrook | YES | Complete | Complete | Speed tables not done. Manhole rattler | Speed tables not done. Manhole rattler |  | S Diton | 20th November 2020
|  |  | NS | NS Not Started
|  |  | S | Started
|  |  | S&C | Started and Completed on same day
|  |  | C | Completed