## About
HIMS enquiries from 1 April 2019 to 8 October 2021
Selected for STREET DESCRIPTOR = EVENDONS LANE or EDNEYS HILL
Test entries removed
Personal identifiers removed

## Evendons & Edneys
ENQUIRY REFERENCE | ENQUIRY TIME | ACTUAL COMPLETION DATE | ENQUIRY CATEGORY | ENQUIRY ITEM TYPE | ENQUIRY DETAIL | COMMENTS | STREET DESCRIPTOR | LOCATION DESCRIPTION | IN HOUSE COMMENTS
W19126 | 2019-04-05 12:08 | 2020-03-24 10:30 | Flooding or Drainage | Drainage | Drainage | drain cover storm drain edge is sinking | EDNEYS HILL, WOKINGHAM | between greenfields farm and ten acres farm | pot hole opposite the drainage hole cover needs to be looked at as well FH Comments: This has been sent to the flooding team to take further action. However, it looks like the inspector has investigated and identified that there is a default and the gully lid needs replacing. Therefore, the inspector or Volker should have created a default on this order rather than sending it through to the flooding team. 25/4/2019
W19190 | 2019-04-09 13:45 | 2019-09-11 08:48 | Potholes | Footway | Pothole | pot holes all the way along the road and the customer thinks that the speed limit should be slower | EDNEYS HILL, WOKINGHAM | coming from Wokingham side passed nashgrove lane on the left and on the bend | ?
W19384 | 2019-04-24 09:55 | 2019-06-11 08:13 | Damaged Road | Carriageway | Road Damage | I'm reporting this on behalf of Cllr Kerr. The information provided refers to the entire length of the de-restricted section of Evendons Lane. Concern has also be expressed about a sinking trench. | EVENDONS LANE, WOKINGHAM | Please find attached images of the road along the de-restricted section of Evendons Lane/Edneys Hill. These are examples of where the road is crumbling away at the edges. There are also images of the middle of one of the carriageways where it is very uneven. I've had cyclists contact me as it's becoming more dangerous for them to use the road. | ?
W19658 | 2019-05-11 21:08 | 2019-05-13 12:38 | Broken/ Missing Ironwork | Gully | Broken Gully | There is a drain which is blocked and causing water to escape from a sealed cover not shown on your map. the water has been running since Friday 10th May and still running at this time. | EVENDONS LANE, WOKINGHAM | Outside 171 Evendons Lane opposite side of the road, approx. 20 metre down (towards Nash Grove Lane) | can you please visit this one. Passed to drainage and flooding 13/05/19
W19681 | 2019-05-14 08:55 | 2958101 | Flooding or Drainage | Drainage | Flooding | The footpath is completely impassible. Water and a thick layer of muddy sludge is running like a stream down the path and onto Evendons lane. | EVENDONS LANE, WOKINGHAM | This is the footpath off Evendons lane that is opposite the scout hut and goes into the golf course. | passed to inspector 3 to investigate
W19981 | 2019-05-30 13:26 | 2019-07-05 18:43 | Road Markings | Road Markings | Condition of White Lines | tarmac on pavement big dip in it | EVENDONS LANE, WOKINGHAM | outside school inward gate | passed to inspector 3
W191112 | 2019-06-07 15:19 | 2019-06-11 09:26 | Potholes | Footway | Pothole | Due to the location, this is quite a dangerous one. Cars who are turning have to drive into the middle of the oncoming traffic to avoid the pothole. | EVENDONS LANE, WOKINGHAM | Right on the junction in the middle of the road. | assigned to Inspector 3
W191189 | 2019-06-11 10:01 | 2019-07-05 11:48 | Damaged Road | Carriageway | Road Damage | Please forward to Highway Assets. Large patch required to repair severly damaged c/way,. 10mmDBM Approx 25sqm. Road Closure required. | EVENDONS LANE, WOKINGHAM | Evendons Lane junction with Blagrove Lane | sent to inspector 3 11.6.19 Highway Assets 5 July 2019: added to resurfacing requests tracker sheet (SVS)
W192283 | 2019-08-08 11:39 | 2020-04-07 14:28 | Road Markings | Road Markings | Condition of White Lines | All white lines badly faded and require refreshing | EVENDONS LANE, WOKINGHAM | Entire length of EVENDINS LANE from BLAGROVE LANE to WOKINGHAM ROAD | assigned to inspector 3
W192635 | 2019-08-30 09:57 | 2020-05-05 14:14 | Potholes | Footway | Pothole | Large pot hole caused tyre to burst | EVENDONS LANE, WOKINGHAM | coming into lane from finchampsted road | assigned to inspector 2 Reassigned Date: Aug 30 2019 11:44AM Reassigned By: Shona Harris Reassigned To: Josh Uzzell Comment: Please can you check if valid for a urgent repair? Across yellow line Outside 17 Evendons Lane JU - I have been on site, the minor deterioration of Surface course outside No.17 could not of caused the tyre damage described by the member of Public. This is not a safety defect. On further review, the defect described by the member of Public is at the JN. There was once a deep pothole which has already been made safe and marked for patch. I visited yeasterday on jn Finchampstead Road I cannot see a defect only minor wear & tear. THE PHOTO ATTACHED WOULD NOT CAUSE TYRE DAMAGE!!WR 5/5/20
W192853 | 2019-09-11 13:03 | 2958101 | Damaged Road | Carriageway | Road Damage | not road damage however the speed limit down the narrow road. recent road accident, police have been at the scene and said how bad the road is. | EDNEYS HILL, WOKINGHAM | ednesy hill, before everdons lane | ?
W193264 | 2019-10-02 14:41 | 2958101 | Damaged Road | Carriageway | Road Damage | There is a long stretch of road on Evendons Lane between Nashgrove Road & Blagrove Road where the road has been taken up and repaired for pipes or cables or something similar. &nbsp;The tarmac that has been used to infill the trench has sunk resulting in it being 2- 5 cms below the level of the main carriageway. &nbsp; We were using this road on a Breeze ride this morning. &nbsp;A lady fell off her bicycle due to the uneven road surface resulting in bruising & shock. &nbsp;We were fortunate that a passing car had already cleared the area, otherwise the consequences may have &nbsp;been far worse. This road needs to be repaired properly in order to prevent further accidents. | EVENDONS LANE, WOKINGHAM | Evendons Lane, Wokingham between Nash Grove Lane & Blagrave Lane | assigned to inspector 3 Reassigned Date: Oct 3 2019 1:35PM Reassigned By: Joshua Kinge Reassigned To: Streetworks Comment: Unsure which utility company carries out the work, but it seems the surface has failed in areas Please see photos attached as discussed this trench is well out of guarantee and requires patching by WBC/VH. JG 28/05 Reassigned Date: Jun 2 2020 10:00AM Reassigned By: Stephen Watkins Reassigned To: VolkerHighways Admin Comment: Unsure which utility company carries out the work, but it seems the surface has failed in areas Please see photos attached Please send to streetworks and highway assets. Work still not complete
W193327 | 2019-10-07 13:28 | 2019-10-08 13:34 | Potholes | Footway | Pothole | ? | EVENDONS LANE, WOKINGHAM | As you travel along Evendons Lane with Finchampstead Road ahead of you and the school on your right hand side, there is a pothole on the left side of the carriageway. It goes across the double yellow lines. | assigned to inspector 3
W193550 | 2019-10-14 11:44 | 2019-10-16 09:02 | Flooding or Drainage | Drainage | Flooding | There is often flooding in this area after heavy rain. This is partly caused by a block drain, but there's also a section of the road which is lower than the rest and the water congregates there after a downpour. | EVENDONS LANE, WOKINGHAM | This is outside 1 Evendons Lane in the turning circle of the cul de sac | ?
ENQ194406 | 2019-11-21 15:25 | 2958101 | Damaged Road | Carriageway | Road Damage | ? | EVENDONS LANE, WOKINGHAM | Blagrove Lane to Nashgrove Lane | assigned to inspector 3 Please inspect this section of Evendons Lane for hazardous defects in response to Councillor enquiry Reassigned Date: Dec 10 2019 1:11PM Reassigned By: Stephen Watkins Reassigned To: Highway Assets Comment: Please see details above and photo attached
W195067 | 2019-12-17 16:07 | 2020-04-11 12:56 | Broken/ Missing Ironwork | Gully | Broken Gully | leaves covering drain | EVENDONS LANE, WOKINGHAM | drain in road customer lives in redlands place | ?
W195068 | 2019-12-17 16:08 | 2019-12-18 09:17 | Broken/ Missing Ironwork | Gully | Broken Gully | gully full of leaves | EVENDONS LANE, WOKINGHAM | gully in road by redlands place | please take photos and send to flooding
W205466 | 2020-01-02 11:30 | 2020-01-07 15:07 | Damaged Road | Carriageway | Road Damage | One of our Ride leaders (Chris Ross) reported this problem on 2nd October 2019 but nothing appears to have been done about it in 3 months. The reference no. was W193264. There is a trench on Evendons Lane where the road has been dug up and not filled in properly, resulting in a trench which is 2- 5 cms below the main carriageway. This caused an accident on a cycle ride in October, when one lady caught her wheel on the step down to the trench and this caused her to fall off her bike, sustaining bruises and shock. | EVENDONS LANE, WOKINGHAM | Evendons Lane, Wokingham on the stretch between Nashgrove Lane and Blagrove Lane. The road damage is on the left hand side of the carriageway after turning right from Nasgrove Lane, heading towards Wokingham. | ?
W205704 | 2020-01-09 16:47 | 2958101 | Potholes | Footway | Pothole | The area next to the pothole has been repaired in the last few months. | EVENDONS LANE, WOKINGHAM | This is directly on the junction of Evendon’s lane and blagrove Lane on the carriageway furthest away the junction. | ?
W205705 | 2020-01-09 16:47 | 2020-01-22 10:49 | Potholes | Footway | Pothole | ? | EVENDONS LANE, WOKINGHAM | This is at the edge of the driveway of 83 Evendon’s lane. | ?
W206429 | 2020-01-20 19:49 | 2020-02-03 14:14 | Pavement and Cycleway | Pavement and Cycleway | Pavement and Cycleway | The kerb stone has come free needs to be repositioned back into place. | EVENDONS LANE, WOKINGHAM | Drop kerb in front of 120b Evendon’s lane | ?
W207109 | 2020-02-05 10:45 | 2020-02-12 09:31 | Potholes | Footway | Pothole | pothole in cul de sac | EVENDONS LANE, WOKINGHAM | cul de sac opposite the entrance to evendons primary school | ?
W207554 | 2020-02-16 16:17 | 2020-02-21 13:18 | Debris, Spillage or Obstruction on the Road | Carriageway | Debris Spillage or Obstruction on the Road | Fallen tree blocking path next to folly foot cottage | EDNEYS HILL, WOKINGHAM | Off Edneys hill | ?
W207987 | 2020-02-25 15:18 | 2020-02-27 13:10 | Damaged Road | Carriageway | Road Damage | Reported by phone call: Based off of information provided by caller, 2Hr ticket raised. Investigation and permanent repair is still needed. Described as major pothole in wheel track of CW. Caller had hit it with her car and it caused a serious bang. Please investigate | EVENDONS LANE, WOKINGHAM | outside No.123 Everdons Ln. Also near convivence store | Based off of information provided by caller, 2Hr ticket raised. Permanent repair needed Assigned to Inspector area 3 on 25/02/2020 at 1525
W208151 | 2020-02-28 21:40 | 2020-03-03 14:29 | Damaged Road | Carriageway | Road Damage | Big deep pot holes | EVENDONS LANE, WOKINGHAM | 125 evendons lane out side | ?
W208326 | 2020-03-04 12:16 | 2020-03-05 13:13 | Potholes | Footway | Pothole | Close to edge of road.. VERY DANGEROUS | EDNEYS HILL, WOKINGHAM | Greenfields House Edneys Hill, Barkham, RG41 4DS Nearest postcode to the pin placed on the map (automatically generated): RG41 4DT (189m away) Greenfields House Edneys Hill, Barkham, RG41 4DS Nearest postcode to the pin placed on the map (automatically generated): RG41 4DT (189m away) | assigned to inspector 3 04/03/2020 Reassigned Date: Mar 4 2020 1:14PM Reassigned By: Stephen Watkins Reassigned To: VolkerHighways Admin Comment: Is there a way of replying directly to the person? Unfortunately the edge of the carriageway is the verge which isn't meant to be driven on, it's not overly dangerous as this isnt part of the carriageway but more the verge has sunk Stephen, his contact details are on hims so will receive the email from you once shut down :)
W208938 | 2020-03-25 11:24 | 2958101 | Green | Green | Green - Single black bag | this should read Garden Waste - not Green | EVENDONS LANE, WOKINGHAM | ? | ?
W209187 | 2020-04-08 08:31 | 2020-04-20 11:15 | Road Signs | Sign | Damaged/Missing Non-Illuminated Road Sign | The Tight bend / Reduce Speed Now sign has fallen off the post and is lying at the bottom of the post | 44702201 - EDNEYS HILL - BARKHAM | At the bottom end of Edneys Hill. About 100 yards from Barkham Road just after the entrance to Mortimers Lodge farm on the opposite side of the road. | ?
W209731 | 2020-05-05 10:50 | 2020-07-09 08:10 | Road Signs | Sign | Damaged/Missing Illuminated Road Sign | Wooden swing gate has been (professionally) removed allowing bikes easy access to the field. | 44700524 - EVENDONS LANE - WOKINGHAM | Entrance to the field of Redlands Farm Park, accessed next to Scout Hut car park off Evendon's Lane | ?'Reassigned Date: May 5 2020 11:46AM Reassigned By: Shona Harris Reassigned To: VolkerHighways Admin Comment: Please can you send to Andrew Fletcher PROW
W209890 | 2020-05-11 11:47 | 2020-06-24 09:58 | Damaged Road | Carriageway | Road Damage | Old utility trench sunk Upto 40mm below carriageway level over 200lm ''Please pass to Highway assets ''Ray Smith | 44700524 - EVENDONS LANE - WOKINGHAM | The Myrtles | The c/way trench has been wearing for sometime but surface wear is beteen 20-30mm not dangerous but will need to be monitored. WR 24/6/20
W2010288 | 2020-05-22 16:22 | 2020-05-26 12:15 | Debris, Spillage or Obstruction on the Road | Carriageway | Debris Spillage or Obstruction on the Road | have loss of his internet connection, which his service provider has said is the fault of the tree on the junction of Finchampstead road and Evedons Lane. A branch on this tree has completely overgrown and is touching the telephone lines. | 44700524 - EVENDONS LANE - WOKINGHAM | 1 Evendons Lane wokingham RG41 4AA | ?
W2010910 | 2020-06-12 14:19 | 2020-06-18 11:39 | Debris, Spillage or Obstruction on the Road | Carriageway | Debris Spillage or Obstruction on the Road | When pulling out of Redlands Place, the vegetation is overgrown on the bend so you can’t see traffic coming from Finchampstead road. | 44700524 - EVENDONS LANE - WOKINGHAM | ? | ?
W2012212 | 2020-07-27 09:04 | 2020-07-29 08:23 | Debris, Spillage or Obstruction on the Road | Carriageway | Debris Spillage or Obstruction on the Road | I have received a report of a tree directly outside a residents house that is growing and when you reverse out of her drive you cant see because the tree branches are blocking the road. | 44700524 - EVENDONS LANE - WOKINGHAM | 73 Evendons Lane, RG41 4AD | ?
W2012401 | 2020-08-02 10:31 | 2958101 | Street Cleansing | Street Cleansing | Encroachment | Pavements alongside the school is full of bushes and leaves and makes it extremely difficult not only to walk as it’s now so narrow, but 2 metre distancing is being compromised. | 44700524 - EVENDONS LANE - WOKINGHAM | Pavement alongside school | ?'Reassigned Date: Aug 4 2020 9:02AM Reassigned By: Shona Harris Reassigned To: Locality Officer Comment: Believe this may be for sweeping, several areas of footpath covered in leaves and weeds,
W2012506 | 2020-08-05 09:45 | 2958101 | Damaged Road | Carriageway | Road Damage | There is a longitudinal strip of road damage Eastbound between Nash grove lane and the scout hut where there has been a previous repair or utility repairs but the repair is lower than the main road surface, causing a dangerous lip for cyclists. This strip will also fill will water when wet and be dangerous in the dark. Cyclists have to either ride very close to the edge of the road or in the middle of the road to avoid it. | 44700524 - EVENDONS LANE - WOKINGHAM | Edneys hill/evendons lane Eastbound between nash grove lane and evendons lane | ?
W2013144 | 2020-08-21 11:52 | 2020-08-21 15:03 | Debris, Spillage or Obstruction on the Road | Carriageway | Debris Spillage or Obstruction on the Road | The oak tree has grown out horizontally and it is so wide that both properties struggle to see out of their driveway when they reverse out. They are concerned that when the school starts again their will be more traffic and there might be accident as it is getting dangerous.''Follow up email received 21/8 11:55AM: ''Further to my request for urgent tree pruning outside 73 Evendon’s Lane'Please see photos below (added to HIMS). The tree obscures cars even only a few feet from the driveway and it has grown a lot more since it was first reported about a month ago. It affects ourselves and our neighbours at 75. It be will be even more dangerous once the school reopens as then there are cars parked opposite making it a single lane so cars are pushed over onto our side of the road. It would be much appreciated if this could be dealt with before it causes an accident.'Thank you'Julie Wilding' | 44700524 - EVENDONS LANE - WOKINGHAM | Outside property between 73 and 75 evendons Lane | ?
W2013750 | 2020-09-07 08:50 | 2020-09-10 11:00 | Debris, Spillage or Obstruction on the Road | Carriageway | Debris Spillage or Obstruction on the Road | Someone has dumped a large metal bar in the road, I have moved it onto the side outside my house @ 15 Evendons Lane. Children go to the school and I am worried that someone will trip on it. | 44700524 - EVENDONS LANE - WOKINGHAM | 15 Evendons Lane on the pavement | ?
W2014361 | 2020-09-23 09:51 | 2020-09-29 14:00 | Street Cleansing | Street Cleansing | Road not swept as scheduled | We have not seen a road sweeper in Evendons lane this year ( between Blagrove Lane and Edneys Hill). The council installed kerbs outside Redland Place to stop vehicle pushing the grass verges into the ditch. Please can you arrange to have the road sweeper Also there are drain outside Redlands Place which have not been cleaned this year and need to be cleaned please. | 44700524 - EVENDONS LANE - WOKINGHAM | ? | ?
W2014953 | 2020-10-08 11:39 | 2958101 | Damaged Road | Carriageway | Road Damage | Hi there, a pipe/cables must have been laid at one time along the left side of Evendons lane, facing east from Nashgrove lane. The repair work was shoddy and is very dangerous. I have almost fallen off my bike a number of times when I moved from the repaired area to the existing road.''The repaired area needs to be replace along its length. | 44700524 - EVENDONS LANE - WOKINGHAM | Evendons lane, left side of road facing east between Nashgrove lane and the bend before Blagrove lane.'The full trench needs to be repaired as it is uneven/broken up.''This marker shows one point along the trench'Marker at: SU7948666752 / SU76Y'Lat: 51.39424 Lon: -0.85892 | ?'Reassigned Date: Apr 14 2021 4:42PM Reassigned By: Shona Harris Reassigned To: Highway Assets Comment: Please see resident concerns
W2015231 | 2020-10-16 08:50 | 2020-10-19 12:40 | Other Household Waste | Other Household Waste | Other household waste - Car boot load or less | Child's car seat | 44700524 - EVENDONS LANE - WOKINGHAM | As pinned on map'By the entrance to Wokingham Scout Hut car park'Driving from Wokingham, it's the right hand turn approx 50m after Redlands Place | ?
ENQ2015367 | 2020-10-20 10:19 | 2958101 | Damaged Road | Carriageway | Road Damage | ? | 44700524 - EVENDONS LANE - WOKINGHAM | Report of carriageway haunching causing potholes at edgings on the 60mph section of Evendons Lane and Edney's Hills could this be made safe and supply photos. | ?
W2015368 | 2020-10-20 10:20 | 2958101 | Damaged Road | Carriageway | Road Damage | Road surface along edge of Carridgeway badly damaged'Approximately 20m by 1m | 44700524 - EVENDONS LANE - WOKINGHAM | Evendons lane, just past junction of blagrove lane | ?'Reassigned Date: Oct 20 2020 12:18PM Reassigned By: Stephen Watkins Reassigned To: VolkerHighways Admin Comment: This was noted during an inspection
W2015371 | 2020-10-20 10:30 | 2020-10-26 11:06 | Damaged Road | Carriageway | Road Damage | Send to assests''Condition of utility trench has sunk 'Please investigate or send to streetworks, unable to om enquiry | 44700524 - EVENDONS LANE - WOKINGHAM | Evendons lane, before edneys hill | ?
W2017076 | 2020-12-10 16:05 | 2020-12-11 17:30 | Potholes | Footway | Pothole | large pothole | 44700524 - EVENDONS LANE - WOKINGHAM | opposite primary school | by width restrictions
W2017089 | 2020-12-10 20:42 | 2020-12-16 07:29 | Potholes | Footway | Pothole | ? | 44700524 - EVENDONS LANE - WOKINGHAM | Just by the dreadful new “road layout”. Right hand side if turning in from Finchampstead road. | ?''Reassigned Date: Dec 14 2020 7:23AM Reassigned By: Shona Harris Reassigned To: Inspection Area 2 Comment: Reassigned
W2117957 | 2021-01-11 10:07 | 2958101 | Broken/ Missing Ironwork | Gully | Broken Gully | Full of leaves and resulting in flooding when the weather's wet. | 44700524 - EVENDONS LANE - WOKINGHAM | ? | ?
W2118211 | 2021-01-18 15:06 | 2021-01-19 12:57 | Construction/Demolition/Excavation | Construction/Demolition/Excavation | Construction / demolition / excavation - Transit van load | big bags of construction waste - roofting, concrete etc | 44700524 - EVENDONS LANE - WOKINGHAM | in between nash grove and scout hut | ?
W2118216 | 2021-01-18 16:01 | 2021-01-19 09:41 | Other (Unidentified) | Other (Unidentified) | Other (unidentified) - Car boot load or less | 4 blue bags in the ditch just before the bend by the scout hut, on opposite side of road to scout hut | 44700524 - EVENDONS LANE - WOKINGHAM | ? | Potential duplicate of W2118211 / D2013489:'"Big bags of construction waste - roofing, concrete etc"'"in between nash grove and scout hut"'No new Defect required if duplicate.
W2118224 | 2021-01-18 21:34 | 2021-01-19 09:41 | Other (Unidentified) | Other (Unidentified) | Other (unidentified) - Other single items | Several blue bags, not Council rubbish bags, dumped on side of the road with what looks like hardcore in. Between Nashgrove junction and blagrove junction. | 44700524 - EVENDONS LANE - WOKINGHAM | On Evendons lane before it changes to Edney’s Hill. Left hand side driving towards Toad hall from Evendons Convenience store. | ?
W2118423 | 2021-01-24 18:32 | 2021-01-26 10:36 | Broken Temporary Traffic Lights | Temporary Traffic Lights | Broken Temporary Traffic Light | Traffic lights not working stuck on red | 44702201 - EDNEYS HILL - BARKHAM | Junction School Road and Barkham Road and Langley common Road | Re-assigned to Traffic signals 26.01.21 as not for street lighting'i think these are the temp lights at Arborfield bridge? I have therefore forwarded to streetworks.''26/1 AS'Inspector has driven through the site and lights are working
W2118660 | 2021-01-30 16:12 | 2958101 | Broken/ Missing Ironwork | Gully | Broken Gully | Blocked and water level at the surface | 44700524 - EVENDONS LANE - WOKINGHAM | ? | 01/02 - emailed resident for more information
W2118816 | 2021-02-02 16:16 | 2021-02-10 09:07 | Potholes | Footway | Pothole | Giant crater opposite follyfoot cottage there are further holes all along the edge of the road right past the ponderosa on both sides | 44707066 - EDNEYS HILL - WOKINGHAM | opposite follyfoot cottage down to ponderosa on both sides of the road | ?
W2118820 | 2021-02-02 17:28 | 2021-02-08 14:00 | Potholes | Footway | Pothole | ? | 44700524 - EVENDONS LANE - WOKINGHAM | on the nashgrove road side of edneys hill just before Nashgrove lane heading towards the Barkham road | ?
W2119060 | 2021-02-08 11:55 | 2958101 | Broken/ Missing Ironwork | Gully | Broken Gully | Blocked | 44700524 - EVENDONS LANE - WOKINGHAM | ? | 10/02 -ORD2100252
W2119063 | 2021-02-08 11:59 | 2021-02-15 14:00 | Street Cleansing | Street Cleansing | Road not swept as scheduled | This section of Evendons Lane is constantly missed | 44700524 - EVENDONS LANE - WOKINGHAM | ? | ?
W2119085 | 2021-02-08 17:18 | 2021-02-17 11:47 | Damaged Road | Carriageway | Road Damage | Poor road surface along this stretch Eastbound where a previous repair along carriageway for about 100m is below the level of the rest of the road, making a gully/ledge which is very dangerous for cyclists, and terrible in the dark. This has been reported numerous times on https://www.fillthathole.org.uk/hazards/map but still there. | 44700524 - EVENDONS LANE - WOKINGHAM | Edneys Hill Eastbound between NashGrove lane and Relands farm | ?
W2119102 | 2021-02-09 10:26 | 2021-02-09 14:10 | Other Household Waste | Other Household Waste | Other household waste - Small van load | About 9 bags worth, all in Wokingham blue bags, next to the Evendons Primary School sign. | 44700524 - EVENDONS LANE - WOKINGHAM | Next to the Evendons Primary School sign by the In gate. | ?
W2119265 | 2021-02-12 16:09 | 2021-02-17 14:20 | Road Signs | Sign | Damaged/Missing Non-Illuminated Road Sign | Missing "give way to oncoming vehicles" sign | 44700524 - EVENDONS LANE - WOKINGHAM | Evendons Lane, outside Evendons Primary, on that side of the road | ?
W2119486 | 2021-02-18 17:24 | 2021-02-22 14:37 | Other (Unidentified) | Other (Unidentified) | Other (unidentified) - Car boot load or less | 3 blue rubble bags on verge of road. I have adopted the road for litter picking but the bags i believe have rubble in and are too heavy. | 44702201 - EDNEYS HILL - BARKHAM | ? | ?
W2119610 | 2021-02-22 09:37 | 2021-02-24 11:00 | Street Cleansing | Street Cleansing | Road not swept to standard | Most of road has been well cleansed up to Blagrove Lane but there is a section missed near a gully where there's a lot of built up detritus. | 44700524 - EVENDONS LANE - WOKINGHAM | On Evendons Lane just past the Blagrove Lane junction by industrial buildings. | ?
W2119776 | 2021-02-25 08:18 | 2958101 | Flooding or Drainage | Drainage | Drainage | The drainage gully under car park entrance is blocked not allowing water to flow from the dike in front of Redlands Cottage. | 44700524 - EVENDONS LANE - WOKINGHAM | RG41 4 DX entrance to Redlands Fram Park by scout hut | ?
W2120220 | 2021-03-06 16:09 | 2021-03-10 09:32 | Potholes | Footway | Pothole | This has had a temporary fill but its failing. | 44700524 - EVENDONS LANE - WOKINGHAM | Outside 17 evendons Lane. | ?
W2120224 | 2021-03-06 16:28 | 2021-03-09 14:03 | Tyres | Tyres | Tyres - Other single items | Small wheel and yellow bag | 44700524 - EVENDONS LANE - WOKINGHAM | In scrub land by 1 evendons Lane | ?
W2120383 | 2021-03-10 14:34 | 2021-03-23 11:43 | Inspection | Pre-Patching | Carriageway Pre-Patching | attended site 09/03, Pothole outside school has been made safe on D2015030. please can you review for inclusion for future works. | 44700524 - EVENDONS LANE - WOKINGHAM | Outside Evendons school, carriageway | ?'Reassigned Date: Mar 11 2021 10:51AM Reassigned By: Rebecca Barnes Reassigned To: Highway Assets Comment: Please make permanent repair outside number 17''15.03.21 - ORDER - ORD2100430
W2120525 | 2021-03-13 12:43 | 2958101 | Potholes | Footway | Pothole | 3 very deep holes on the most dangerous bend. Could cause an accident or at the least take out someones steering/damage to wheel & car. | 44707066 - EDNEYS HILL - WOKINGHAM | Opposite to Follyfoot Cottage & before Shawmount on Edneys Hill | ?''Reassigned Date: Apr 14 2021 4:43PM Reassigned By: Rebecca Barnes Reassigned To: Highway Assets Comment: Please make a permanent repair near the entrance to Toad Hall nursery
W2120677 | 2021-03-17 10:24 | 2021-03-18 09:54 | Pavement and Cycleway | Pavement and Cycleway | Pavement and Cycleway | There are two loose kerb stones raised above the pavement outside 120B Evendons Lane. | 44700524 - EVENDONS LANE - WOKINGHAM | ? | ?
W2120678 | 2021-03-17 10:25 | 2958101 | Potholes | Footway | Pothole | there are a large number of potholes in this section of Evendons lane | 44700524 - EVENDONS LANE - WOKINGHAM | ? | ?''Reassigned Date: Apr 14 2021 4:43PM Reassigned By: Rebecca Barnes Reassigned To: Highway Assets Comment: Please consider to resurface the road as the surface is deteriorating
W2121521 | 2021-04-09 08:47 | 2958101 | Inspection | Road Markings | White road markings | Please send to Highways Assets as part of Highways Inspection 09/04/2021''Keep clear Road markings faded | 44700524 - EVENDONS LANE - WOKINGHAM | Just past School heading towards Finchampstead Road | ?
W2122184 | 2021-04-26 16:23 | 2021-04-28 07:30 | Other Household Waste | Other Household Waste | Other household waste - Small van load | several old fence panels | 44700524 - EVENDONS LANE - WOKINGHAM | ? | ?
W2122329 | 2021-04-29 20:40 | 2958101 | Damaged Road | Carriageway | Road Damage | Carriageway collapsed into ditch. Left hand side as travel towards edneys hill | 44707066 - EDNEYS HILL - WOKINGHAM | ? | ?''Reassigned Date: Apr 30 2021 10:31AM Reassigned By: Marjorie Mcivor Reassigned To: Highway Assets Comment: Please consider patching this section of carridgeway due to collapsed In to verge , opposite signs for Greenfield Carp Fishery
W2122642 | 2021-05-09 17:54 | 2021-05-10 07:32 | Dead Animals | Dead Animals | Deer | ? | 44707066 - EDNEYS HILL - WOKINGHAM | ? | ?
W2123065 | 2021-05-20 08:43 | 2021-05-20 08:43 | Inspection | Encroachment | Vegetation | Hi Is it possible for the grass on the front of 51 / 53 Evendons Lane to be left uncut. There is a slope as part of the verge that is regularly scalped (I re-seeded it recently and it&#39;s been scalped again today). I&#39;m happy to take responsibility to cut the area in front of these two houses. Please advise if this is possible Many thanks Nigel Crow | 44700524 - EVENDONS LANE - WOKINGHAM | 51 / 53 Evendons Lane | ?
W2123263 | 2021-05-25 14:40 | 2021-05-26 12:44 | Potholes | Footway | Pothole | 3 significant potholes at or near junction of cul de sac with main part of Evendons Lane | 44700524 - EVENDONS LANE - WOKINGHAM | At and near junction of cul de sac with main part of Evendons Lane | ?
W2123650 | 2021-06-08 14:44 | 2021-06-14 12:01 | Road Markings | Road Markings | Condition of White Lines | 122 EVENDONS LANE white lines have faded and needs re painting | 44700524 - EVENDONS LANE - WOKINGHAM | ? | ?'Reassigned Date: Jun 9 2021 2:25PM Reassigned By: Marjorie Mcivor Reassigned To: Traffic Management Comment: Please refresh road markings as they are very worn with gaps from patching works , Not saftey critical.''TM Response : Lining will be incorporated in forthcoming traffic management scheme so no further action required at this time.
W2123889 | 2021-06-14 15:10 | 2021-06-14 15:10 | Inspection | Encroachment | Vegetation | Brambles are overgrown and very high. | 44700524 - EVENDONS LANE - WOKINGHAM | ? | ?
W2123971 | 2021-06-16 02:10 | 2958101 | Inspection | Encroachment | Trees | There is a very large oak tree near number 51 Evendons Lane that over the past few years has started to look unhealthy. This year it has a good number if branches that have no leaves on and the branches with leaves are looking less than full. Apart from the need to remove the dead branches as a danger to the public, as such a massive tree please could you check it’s general health because if this came down, even in part, it would cause serious damage to property and potentially people. | 44700524 - EVENDONS LANE - WOKINGHAM | Evendons Lane, outside numbers 51 and 49. On the right just after the turning into Evendons Close, if approaching from the Finchampstead Road. | ?
W2124172 | 2021-06-19 07:21 | 2021-06-21 11:18 | Debris, Spillage or Obstruction on the Road | Carriageway | Debris Spillage or Obstruction on the Road | Thames Valley Police Control Room C4251 - There is a shed falling apart on the side of the road and parts of this shed including fencing panels are blowing from the shed into the road, RP XRT11 has attended today at 0630hrs for a report of wood in the middle of the road - the road has been cleared although this shed will need a risk assessment from local authority as to it's condition and how it's situated due to the risk it poses to road users. TVP INC-20210619-0457 refers, please call 101 for any further information | 44702201 - EDNEYS HILL - BARKHAM | This shed is outside Edneys Hill Farm, Edneys Hill, Wokingham, RG41 4DP | ?
W2124175 | 2021-06-19 10:16 | 2958101 | Broken/ Missing Ironwork | Gully | Broken Gully | This is not a broken gulley, but a problem with drainage to it, caused by a permanent lump of tarmac in the gutter just upstream, outside 136 Evendons Lane, which causes a problem at 134, next door. I took photographs, which I attach. | 44700524 - EVENDONS LANE - WOKINGHAM | 134/136 Evendons Lane | ?
W2124355 | 2021-06-22 14:10 | 2021-06-25 12:47 | Potholes | Footway | Pothole | ? | 44700524 - EVENDONS LANE - WOKINGHAM | Outside 83 evendons Lane ' | ?
W2124356 | 2021-06-22 14:12 | 2958101 | Broken/ Missing Ironwork | Gully | Broken Gully | Blocked. | 44700524 - EVENDONS LANE - WOKINGHAM | Outside 82 evendons lane | 22/06 - new work order raised ORD2101149
W2124357 | 2021-06-22 14:14 | 2958101 | Flooding or Drainage | Drainage | Drainage | Gully blocked. Overflowing with water during heavy rainfall | 44700524 - EVENDONS LANE - WOKINGHAM | Outside 72 evendons lane | 22/06 - new work order raised ORD2101149
W2124436 | 2021-06-23 15:52 | 2021-06-23 15:52 | Inspection | Encroachment | Vegetation | Vegetation is overgrowing highway | 44700524 - EVENDONS LANE - WOKINGHAM | ? | ?
W2124626 | 2021-06-28 07:56 | 2958101 | Broken/ Missing Ironwork | Gully | Broken Gully | Blocked | 44700524 - EVENDONS LANE - WOKINGHAM | ? | ?
W2124658 | 2021-06-28 10:48 | 2958101 | Inspection | Vegetation | Vegetation Public Land | Please send to Localities as part of Highways Inspection 28/06/2021''Please cut back overgrown vegetation encroaching onto footpath | 44702201 - EDNEYS HILL - BARKHAM | Corner of Edneys Hill as entering from Barkham Road | Update 02/07/2021 letter issued to resident '''''28/6/21 - Localities comment: WBC only responsible for grass on corner - vegetation appears to be private and associated with 384 Barkham Road. Please review attached maps and serve letter. DS
W2125066 | 2021-07-06 07:59 | 2958101 | Flooding or Drainage | Drainage | Drainage | Blocked dyke outside of Redlands Cottage and Redlands Town Farm Park. The dyke is blocked and water is flooding onto Road. This has been reported twice already and no action taken to date | 44700524 - EVENDONS LANE - WOKINGHAM | Outside of Redlands Cottage and Redlands Town Farm Park | ?
W2125067 | 2021-07-06 08:08 | 2958101 | Inspection | Encroachment | Trees | Oak tree has a lot of dead wood overhanging my drive and several large pieces have recently fell just missing my car. The lower branches are now impacting the entrance and touching cars as the enter. This tree needs urgent remedial work | 44700524 - EVENDONS LANE - WOKINGHAM | Tree at right hand side of entrance to Redlands Cottage. This tree has a TPO and is owned by the council | ?
W2125331 | 2021-07-12 12:26 | 2021-07-13 09:03 | Pavement and Cycleway | Pavement and Cycleway | Pavement and Cycleway | Hole in pavement outside 11 Evendons Lane. Path is a very well used route for children, mums with buggies etc on route to Evendons school. We are worried a child or adult will hurt themselves given the amount of foot traffic on the pavement twice each day. | 44700524 - EVENDONS LANE - WOKINGHAM | Hole in pavement outside 11 Evendons Lane. | ?
W2126196 | 2021-08-03 12:59 | 2958101 | Potholes | Footway | Pothole | Big hole as haunches of road are crumbling away. | 44700524 - EVENDONS LANE - WOKINGHAM | Same side of road as nashgrove lane | ?''Reassigned Date: Aug 4 2021 10:44AM Reassigned By: Marjorie Mcivor Reassigned To: Highway Assets Comment: Please consider resurfacing this road due to failing cracking and Fretting and general poor condition edge of carridgeway is falling into the verge
W2126197 | 2021-08-03 13:21 | 2958101 | Potholes | Footway | Pothole | ? | 44707066 - EDNEYS HILL - WOKINGHAM | outside follyfoot cottage and shaw mount. | ?''Reassigned Date: Aug 4 2021 11:36AM Reassigned By: Marjorie Mcivor Reassigned To: Highway Assets Comment: Please consider patching sections of this road due to large edge of carridgeway defects along Edneys hill.
W2126358 | 2021-08-06 13:28 | 2958101 | Road Signs | Sign | Damaged/Missing Non-Illuminated Road Sign | The road name sign for Edneys Hill has been removed and is by the side of the track on Nashgrove Lane, just south of the barriers | 44707066 - EDNEYS HILL - WOKINGHAM | Sign has been dumped on the west side of the Nashgrove Lane track just south of the barriers, 100m or so from the junction with Edneys Hill/Evendons Lane | ?
W2126472 | 2021-08-09 18:36 | 2021-08-17 09:22 | Potholes | Footway | Pothole | Tarmac coming up from road causing a hazard on the side of the road | 44707066 - EDNEYS HILL - WOKINGHAM | Road at exit of Toad Hall Nursery | ?'Reassigned Date: Aug 10 2021 2:11PM Reassigned By: Marjorie Mcivor Reassigned To: Highway Assets Comment: Please consider patching this section of the carriageway due to carriageway cracking directly outside a nursery school.''11.08.21 - WHIP Risk Matrix - This would not be considered dangerous at this time as made-safe by VH and will be monitored by VH regular cyclic inspections.
W2127152 | 2021-08-26 09:24 | 2958101 | Inspection | Vegetation | Vegetation Public Land | Please forward to localities on behalf of DTC vegetation spread sheet. RB'Reference W2123889 and W2124436'Please cut back the overgrown brambles and the overgrowing vegetation along the road. | 44700524 - EVENDONS LANE - WOKINGHAM | Please forward to localities on behalf of DTC vegetation spread sheet. RB'Reference W2123889 and W2124436'Please cut back the overgrown brambles and the overgrowing vegetation along the road.'PLEASE NOTE: Localities do not deal with overgrown veg | 31/08/21 - Please arrange to cut back the overgrown vegetation and brambles along the road.''1.9.21 EP - Works order raised for GM contractor Tivoli to cut back vegetation from the highway. Dynamics ref. 87629
W2127174 | 2021-08-26 13:24 | 2958101 | Pavement and Cycleway | Pavement and Cycleway | Pavement and Cycleway | Please send to Highways Assets as part of inspection found section of fway uneven, pulling down from kerb side. | 44700524 - EVENDONS LANE - WOKINGHAM | Between entrance gates to Evendons Primary school | 09.09.21 - As this was identified as part of an inspection please carry out works or confirm the area is not dangerous.
W2127601 | 2021-09-08 15:35 | 2021-10-01 13:17 | Damaged Road | Carriageway | Road Damage | the edges are degraded and a cyclist has been taken to hospital after hitting a depression and coming off | 44707066 - EDNEYS HILL - WOKINGHAM | on edneys hill near the scout hut | ?'Reassigned Date: Sep 10 2021 10:50AM Reassigned By: Marjorie Mcivor Reassigned To: Highway Assets Comment: Repeated visits to edge of carridgeway over run. Requires Intervention to prevent deterioration.''WHIP Risk Matrix - This would not be considered dangerous at this time as made-safe by VH and will be monitored by VH regular cyclic inspections.
W2128543 | 2021-09-29 19:21 | 2021-10-01 11:35 | Other Household Waste | Other Household Waste | Other household waste - Other single items | toilet and wash basin | 44700524 - EVENDONS LANE - WOKINGHAM | ? | ?
W2128609 | 2021-10-01 11:11 | 2958101 | Damaged Road | Carriageway | Road Damage | Please forward for the attention of Highways Assets 'Noted as part of driven 3mth inspection 01.10.2021 - SN'Multiple edge of carriageway defects along the length of this location'National Speed Limit 60mph 'Traffic count medium 'Width of carriageway 4.0m'No footway present 'This particular enquiry relates to an edge of carriageway defect 3.0m x 1.0m'Make safe requested but permanent remedy required - road closure would be required 'Further investigation/consideration required | 44702201 - EDNEYS HILL - BARKHAM | Outside drive to property known as 'The Bungalow' | 04.10.21 - Please carry out works as required as they were identified as part of an inspection and within the bounds of the patching stipulations.