## Sheet1
Hatch Farm Position Statement at 06.10.2021
P+G: Place and Growth Directorate
JD: Jeanette Davey, Team Leader, Development Management, P+G
| Date | Purpose | Attendees | Reason and Next steps
1 | 16.05.2019 | Site Visit | JD | Familiarisation
2 | 09.07.2019 | Site Visit and Survey | JD | Survey of hard and soft landscaping and country park works
|  |  | Duncan Fisher, Ecologist, P+G | Shortfalls noted and developers written to, seeking improvements
Catherine Brimble, Landscape Architect, P+G
Brigitte Crafer, Landscape Architect, P+G
3 | 07.10.2019 | Site Visit | JD | Reason for visit not recorded in calendar
4 | 22.01.2020 | Site Visit for live PA | JD | 193167 Live PA for temporary construction access
5 | 04.03.2020 | Site Meeting | JD | Site meeting for discussion of open space
Darren MacArthur, Bovis Homes
6 | 17.04.2020 | Site Visit | Justin Turvey, Operational Manager, Development Management, P+G | Complaint
7 | 28.04.2020 | Site Visit and Survey | JD | (Training exercise for new starters)
|  |  | Kieran Neumann, Planning Officer, P+G | Survey of soft landscaping, garage door sizes and ground levels
|  |  | Shaun Hill, Planning Officer, P+G | Significant quantity of dead trees and plants recorded
8 | 14.07.2020 | Site Visit and Survey | JD | (Training exercise for new starters)
|  |  | Hannah Skeels, Enforcement Officer, P+G | Survey of soft landscaping, garage door sizes and ground levels
|  |  | Marcus Watts, Enforcement Officer, P+G | Significant quantity of dead trees and plants recorded
9 | 11.02.2021 | Site Visit | Suraj Phandey, Enforcement Officer, P+G | Enforcement report re: damaged hoarding around construction site
Hoarding had been removed by time of visit - case closed
10 | 17.03.2021 | Site Visit for live PA | JD | 210013 Live PA for Haul Road
11 | 07.04.2021 | Site Visit for enforcement | JD | Enforcement re: Great Crested Newts pond infilling and parking area by 10, Gale Close
|  |  | Marcus Hillman, Intern, P+G | Recorded what was witnessed in writnig and by photograph
Reports forwarded to Thames Valley Police who considered that action could not be taken
12 | 05.05.2021 | Site Visit | Marcus Watts, Enforcement Officer, P+G | Enforcement report re: footpath surfacing not being in accordance with approved plans
13 | 06.05.2021 | Site Visit | Marcus Hillman, Intern, P+G | 10, Gale Close
14 | 24.05.2021 | Site Visit | Marcus Hillman, Intern, P+G | 10, Gale Close
15 | 04.06.2021 | Site Visit | Marcus Watts, Enforcement Officer, P+G | Enforcement report re: removal of boundary fence by developer
16 | 09.06.2021 | Site Visit | Justin Turvey, Operational Manager, Development Management, P+G | Complaint
17 | 16.06.2021 | Site survey for landscaping | JD | Six hours on site - Many long-term dead trees on site
|  | and for live PA | Catherine Brimble, Landscape Architect, P+G | Lack of planting clearly evident again this year
211196 Live PA for the NEAP
18 | 04.08.2021 | Site Visit | Steve Moore, Director, P+G | Reconnaissance
Mark Cupit, Head of Development Delivery, P+G
19 | 10.08.2021 | Site Visit | Justin Turvey, Operational Manager, Development Management, P+G | Complaint