## Summary Jobs Issued
JOBNO | STREET | AREADESC | CREATEDATE | DESCRIPT | PRIORDESC | CTRCOMPD | SHORTDESC | DESCRIPT0
89121 | THE RIDGES | Finchampstead | 2012-01-23 | Break out/Relay Setts' - in 5 strips as marked Use sufficent concrete to stop vehicles ""knocking out"" setts when parking. Additional concrete required on Heathland side to support setts as in other locations along The Ridges 1 = 2.7m 2 = 2.1m 3 | Programmed | 2012-02-17 | Break out/Relay Setts | Remove from store and relay granite kerbing 100mm x 150mm on edge with 150mm thick ST1 concrete bed and haunching laid straight or curved over 15 metre radius.
89121 | THE RIDGES | Finchampstead | 2012-01-23 | Break out/Relay Setts' - in 5 strips as marked Use sufficent concrete to stop vehicles ""knocking out"" setts when parking. Additional concrete required on Heathland side to support setts as in other locations along The Ridges 1 = 2.7m 2 = 2.1m 3 | Programmed | 2012-02-17 | Break out/Relay Setts | Take up or down &amp; set aside for re-use or remove to store Granite Kerbing
89121 | THE RIDGES | Finchampstead | 2012-01-23 | Break out/Relay Setts' - in 5 strips as marked Use sufficent concrete to stop vehicles ""knocking out"" setts when parking. Additional concrete required on Heathland side to support setts as in other locations along The Ridges 1 = 2.7m 2 = 2.1m 3 | Programmed | 2012-02-17 | Break out/Relay Setts | Take Up or Down &amp; Remove to Tip off Site Granite Setts
89121 | THE RIDGES | Finchampstead | 2012-01-23 | Break out/Relay Setts' - in 5 strips as marked Use sufficent concrete to stop vehicles ""knocking out"" setts when parking. Additional concrete required on Heathland side to support setts as in other locations along The Ridges 1 = 2.7m 2 = 2.1m 3 | Programmed | 2012-02-17 | Break out/Relay Setts | Granite kerbs 100 x 200 on edge to WSD/1100/1, type DS2, laid straight or curved over 15 metre radius.
89123 | THE RIDGES | Finchampstead | 2012-01-23 | Reinstate C/way 10mm (DBM)' 2 way lights on bend by gulley | 28 Days | 2012-02-13 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
89123 | THE RIDGES | Finchampstead | 2012-01-23 | Reinstate C/way 10mm (DBM)' 2 way lights on bend by gulley | 28 Days | 2012-02-13 | Reinstate C/way 10 (DBM) | two way
89123 | THE RIDGES | Finchampstead | 2012-01-23 | Reinstate C/way 10mm (DBM)' 2 way lights on bend by gulley | 28 Days | 2012-02-13 | Reinstate C/way 10 (DBM) | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
89124 | THE RIDGES | Finchampstead | 2012-01-23 | 'Pothole' x 2 on bend | 24 Hours (40%) | 2012-01-23 | Pothole | Repairs to Potholes with Patching Material
89124 | THE RIDGES | Finchampstead | 2012-01-23 | 'Pothole' x 2 on bend | 24 Hours (40%) | 2012-01-23 | Pothole | Provision of man and stop/go board
89134 | THE RIDGES | Finchampstead | 2012-01-23 | Manhole C&F replace' replace manhole (750mm, 550mm) - as shown on attached location plan please wait for Stats | Programmed | 2012-01-25 | RAY - Manhole C&F replace | Take up or down and remove to tip off site chamber cover and frame 0.11sq.m. to 0.60sq.m.
89134 | THE RIDGES | Finchampstead | 2012-01-23 | Manhole C&F replace' replace manhole (750mm, 550mm) - as shown on attached location plan please wait for Stats | Programmed | 2012-01-25 | RAY - Manhole C&F replace | Raising or lowering the level of cover/grating and frame 0.11sq.m.up to 0.60sq.m. on existing chamber not exceeding 150mm
89134 | THE RIDGES | Finchampstead | 2012-01-23 | Manhole C&F replace' replace manhole (750mm, 550mm) - as shown on attached location plan please wait for Stats | Programmed | 2012-01-25 | RAY - Manhole C&F replace | Extra over previous two items for provision of new cover and frame.
89312 | THE RIDGES | Finchampstead | 2012-02-01 | Reinstate C/way 10mm (DBM)' 2 way lights near bend | 28 Days | 2012-02-13 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
89312 | THE RIDGES | Finchampstead | 2012-02-01 | Reinstate C/way 10mm (DBM)' 2 way lights near bend | 28 Days | 2012-02-13 | Reinstate C/way 10 (DBM) | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
89312 | THE RIDGES | Finchampstead | 2012-02-01 | Reinstate C/way 10mm (DBM)' 2 way lights near bend | 28 Days | 2012-02-13 | Reinstate C/way 10 (DBM) | two way
89524 | THE RIDGES | Finchampstead | 2012-02-07 | Manhole C&F replace' Replace manhole outside Hunters Wood (750mm, 550mm) Stats sent by e-mail | 28 Days | 2012-02-22 | RAY - Manhole C&F replace | Take up or down and remove to tip off site chamber cover and frame 0.11sq.m. to 0.60sq.m.
89524 | THE RIDGES | Finchampstead | 2012-02-07 | Manhole C&F replace' Replace manhole outside Hunters Wood (750mm, 550mm) Stats sent by e-mail | 28 Days | 2012-02-22 | RAY - Manhole C&F replace | Raising or lowering the level of cover/grating and frame 0.11sq.m.up to 0.60sq.m. on existing chamber not exceeding 150mm
89524 | THE RIDGES | Finchampstead | 2012-02-07 | Manhole C&F replace' Replace manhole outside Hunters Wood (750mm, 550mm) Stats sent by e-mail | 28 Days | 2012-02-22 | RAY - Manhole C&F replace | Extra over previous two items for provision of new cover and frame.
91915 | THE RIDGES | Finchampstead | 2012-05-22 | Pothole' Plug 2 potholes o/s Springwood House (marked with white paint) | Emergency 2Hr | 2012-05-22 | OTHER | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
91915 | THE RIDGES | Finchampstead | 2012-05-22 | Pothole' Plug 2 potholes o/s Springwood House (marked with white paint) | Emergency 2Hr | 2012-05-22 | OTHER | Repairs to Potholes with Patching Material
91915 | THE RIDGES | Finchampstead | 2012-05-22 | Pothole' Plug 2 potholes o/s Springwood House (marked with white paint) | Emergency 2Hr | 2012-05-22 | OTHER | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
91915 | THE RIDGES | Finchampstead | 2012-05-22 | Pothole' Plug 2 potholes o/s Springwood House (marked with white paint) | Emergency 2Hr | 2012-05-22 | OTHER | Emergency (2hr) repairs to potholes using Instarmac (25kg tub)
91938 | THE RIDGES | Finchampstead | 2012-05-23 | Reinstate C/way 10mm (DBM)' 2 way lights | 28 Days | 2012-06-18 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
91938 | THE RIDGES | Finchampstead | 2012-05-23 | Reinstate C/way 10mm (DBM)' 2 way lights | 28 Days | 2012-06-18 | Reinstate C/way 10 (DBM) | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
91938 | THE RIDGES | Finchampstead | 2012-05-23 | Reinstate C/way 10mm (DBM)' 2 way lights | 28 Days | 2012-06-18 | Reinstate C/way 10 (DBM) | two way
91940 | THE RIDGES | Finchampstead | 2012-05-23 | Reinstate C/way 10mm (DBM)' | 28 Days | 2012-06-18 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
91940 | THE RIDGES | Finchampstead | 2012-05-23 | Reinstate C/way 10mm (DBM)' | 28 Days | 2012-06-18 | Reinstate C/way 10 (DBM) | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
91940 | THE RIDGES | Finchampstead | 2012-05-23 | Reinstate C/way 10mm (DBM)' | 28 Days | 2012-06-18 | Reinstate C/way 10 (DBM) | two way
92262 | THE RIDGES | Finchampstead | 2012-06-07 | Reinstate C/way 10mm (DBM)' Marked as Patch 2 2 way lights, near bend | 28 Days | 2012-06-19 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
92262 | THE RIDGES | Finchampstead | 2012-06-07 | Reinstate C/way 10mm (DBM)' Marked as Patch 2 2 way lights, near bend | 28 Days | 2012-06-19 | Reinstate C/way 10 (DBM) | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
92262 | THE RIDGES | Finchampstead | 2012-06-07 | Reinstate C/way 10mm (DBM)' Marked as Patch 2 2 way lights, near bend | 28 Days | 2012-06-19 | Reinstate C/way 10 (DBM) | two way
94720 | THE RIDGES | Finchampstead | 2012-10-01 | Out of Hours - EMERGENCY' RTA, damage to road surface and damage to wall. Clear debris and spread absorbant granules, make save damaged wall (private). Police had already departed site on BBLP's arrival. URN 1694. C1549 | Out of hours | 2012-09-22 | Out of Hours - EMERGENCY | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
94720 | THE RIDGES | Finchampstead | 2012-10-01 | Out of Hours - EMERGENCY' RTA, damage to road surface and damage to wall. Clear debris and spread absorbant granules, make save damaged wall (private). Police had already departed site on BBLP's arrival. URN 1694. C1549 | Out of hours | 2012-09-22 | Out of Hours - EMERGENCY | Ditto outside normal working hours
94720 | THE RIDGES | Finchampstead | 2012-10-01 | Out of Hours - EMERGENCY' RTA, damage to road surface and damage to wall. Clear debris and spread absorbant granules, make save damaged wall (private). Police had already departed site on BBLP's arrival. URN 1694. C1549 | Out of hours | 2012-09-22 | Out of Hours - EMERGENCY | Emergency (2hr) spread absorbent granules (30kg bag) on spills (oil, diesel and the like).
96632 | THE RIDGES | Finchampstead | 2012-12-31 | Pothole' x 12 - All potholes on bend. | 7 Days (10%) | 2013-01-02 | Pothole | Repairs to Potholes with Patching Material
96635 | THE RIDGES | Finchampstead | 2012-12-31 | Reinstate C/way 10mm (DBM)' | 28 Days | 2013-01-17 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
96635 | THE RIDGES | Finchampstead | 2012-12-31 | Reinstate C/way 10mm (DBM)' | 28 Days | 2013-01-17 | Reinstate C/way 10 (DBM) | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
97709 | THE RIDGES | Finchampstead | 2013-02-05 | Pothole, works to be carried out within 2hrs' On the corner bend, near Havenwood breaking up near the white line and towards the edge. | Emergency 2Hr | 2013-02-05 | POTHOLE - URGENT | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
97709 | THE RIDGES | Finchampstead | 2013-02-05 | Pothole, works to be carried out within 2hrs' On the corner bend, near Havenwood breaking up near the white line and towards the edge. | Emergency 2Hr | 2013-02-05 | POTHOLE - URGENT | Emergency (2hr) repairs to potholes using patching materials
97795 | THE RIDGES | Finchampstead | 2013-02-07 | Reinstate C/way 10mm (DBM)' Patch 1A = 1.1m x 1.1m, Patch 1 = 1.2m x 0.7m, Patch 2 = 6.0m x 0.9m, Patch 3 = 8.8m x 3.2m, Patch 4 = 1.3m x 1.3m, Patch 5 = 1.6m x 0.7m, Patch 6 = 2.0m x 1.0m. 2 way lights, on bend | 28 Days | 2013-03-06 | Reinstate C/way 10 (DBM) | Adjustment of the rate in previous item per 10mm in variation above or below 60mm in binder course
97795 | THE RIDGES | Finchampstead | 2013-02-07 | Reinstate C/way 10mm (DBM)' Patch 1A = 1.1m x 1.1m, Patch 1 = 1.2m x 0.7m, Patch 2 = 6.0m x 0.9m, Patch 3 = 8.8m x 3.2m, Patch 4 = 1.3m x 1.3m, Patch 5 = 1.6m x 0.7m, Patch 6 = 2.0m x 1.0m. 2 way lights, on bend | 28 Days | 2013-03-06 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
97795 | THE RIDGES | Finchampstead | 2013-02-07 | Reinstate C/way 10mm (DBM)' Patch 1A = 1.1m x 1.1m, Patch 1 = 1.2m x 0.7m, Patch 2 = 6.0m x 0.9m, Patch 3 = 8.8m x 3.2m, Patch 4 = 1.3m x 1.3m, Patch 5 = 1.6m x 0.7m, Patch 6 = 2.0m x 1.0m. 2 way lights, on bend | 28 Days | 2013-03-06 | Reinstate C/way 10 (DBM) | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
97795 | THE RIDGES | Finchampstead | 2013-02-07 | Reinstate C/way 10mm (DBM)' Patch 1A = 1.1m x 1.1m, Patch 1 = 1.2m x 0.7m, Patch 2 = 6.0m x 0.9m, Patch 3 = 8.8m x 3.2m, Patch 4 = 1.3m x 1.3m, Patch 5 = 1.6m x 0.7m, Patch 6 = 2.0m x 1.0m. 2 way lights, on bend | 28 Days | 2013-03-06 | Reinstate C/way 10 (DBM) | two way
98392 | THE RIDGES | Finchampstead | 2013-02-22 | Pothole' x 5 as marked, between Dell Road & Dell House | 24 Hours (40%) | 2013-02-22 | Pothole | Repairs to Potholes with Patching Material
98393 | THE RIDGES | Finchampstead | 2013-02-22 | Pothole' x 3 as marked, near junction sign | 24 Hours (40%) | 2013-02-22 | Pothole | Repairs to Potholes with Patching Material
98393 | THE RIDGES | Finchampstead | 2013-02-22 | Pothole' x 3 as marked, near junction sign | 24 Hours (40%) | 2013-02-22 | Pothole | Repairs to Potholes with Viafix Material or approved equivalent.
98418 | THE RIDGES | Finchampstead | 2013-02-25 | Reinstate C/way 10mm (DBM)' Patch 1 = 6.4m x 1.0m (re-new 6.4m 100mm white line on completion) Patch 2 = 4.0m x 1.0m, Patch 3 = 1.8m x 1.0m. 2 way lights on bend | 28 Days | 2013-04-04 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
98418 | THE RIDGES | Finchampstead | 2013-02-25 | Reinstate C/way 10mm (DBM)' Patch 1 = 6.4m x 1.0m (re-new 6.4m 100mm white line on completion) Patch 2 = 4.0m x 1.0m, Patch 3 = 1.8m x 1.0m. 2 way lights on bend | 28 Days | 2013-04-04 | Reinstate C/way 10 (DBM) | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
98418 | THE RIDGES | Finchampstead | 2013-02-25 | Reinstate C/way 10mm (DBM)' Patch 1 = 6.4m x 1.0m (re-new 6.4m 100mm white line on completion) Patch 2 = 4.0m x 1.0m, Patch 3 = 1.8m x 1.0m. 2 way lights on bend | 28 Days | 2013-04-04 | Reinstate C/way 10 (DBM) | two way
98418 | THE RIDGES | Finchampstead | 2013-02-25 | Reinstate C/way 10mm (DBM)' Patch 1 = 6.4m x 1.0m (re-new 6.4m 100mm white line on completion) Patch 2 = 4.0m x 1.0m, Patch 3 = 1.8m x 1.0m. 2 way lights on bend | 28 Days | 2013-04-04 | Reinstate C/way 10 (DBM) | Continuous line in white thermoplastic screed with applied ballotini up to 100mm wide.
98419 | THE RIDGES | Finchampstead | 2013-02-25 | Reinstate C/way 10mm (DBM)' Patch 1 = 1.5m x 1.0m, Patch 2 = 1.0m x 1.0m 2 way lights near bend | 28 Days | 2013-03-15 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
98419 | THE RIDGES | Finchampstead | 2013-02-25 | Reinstate C/way 10mm (DBM)' Patch 1 = 1.5m x 1.0m, Patch 2 = 1.0m x 1.0m 2 way lights near bend | 28 Days | 2013-03-15 | Reinstate C/way 10 (DBM) | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
98419 | THE RIDGES | Finchampstead | 2013-02-25 | Reinstate C/way 10mm (DBM)' Patch 1 = 1.5m x 1.0m, Patch 2 = 1.0m x 1.0m 2 way lights near bend | 28 Days | 2013-03-15 | Reinstate C/way 10 (DBM) | two way
98993 | THE RIDGES | Finchampstead | 2013-03-18 | Pothole' | 24 Hours (40%) | 2013-03-18 | Pothole | Repairs to Potholes with Patching Material
99294 | THE RIDGES | Finchampstead | 2013-03-27 | Pothole, works to be carried out within 2hrs' Plug potholes between Dell Road and Ridgeland House. Not marked as called in by resident. | Emergency 2Hr | 2013-03-27 | POTHOLE - URGENT | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
99294 | THE RIDGES | Finchampstead | 2013-03-27 | Pothole, works to be carried out within 2hrs' Plug potholes between Dell Road and Ridgeland House. Not marked as called in by resident. | Emergency 2Hr | 2013-03-27 | POTHOLE - URGENT | Emergency (2hr) repairs to potholes using patching materials
99318 | THE RIDGES | Finchampstead | 2013-03-27 | Pothole, works to be carried out within 2hrs' - Make safe/repair pothole between between Wick Hill Lane and The Ridges, on the Wokingham bound carriageway. | Emergency 2Hr | 2013-03-27 | POTHOLE - URGENT | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
99318 | THE RIDGES | Finchampstead | 2013-03-27 | Pothole, works to be carried out within 2hrs' - Make safe/repair pothole between between Wick Hill Lane and The Ridges, on the Wokingham bound carriageway. | Emergency 2Hr | 2013-03-27 | POTHOLE - URGENT | Emergency (2hr) repairs to potholes using patching materials
99318 | THE RIDGES | Finchampstead | 2013-03-27 | Pothole, works to be carried out within 2hrs' - Make safe/repair pothole between between Wick Hill Lane and The Ridges, on the Wokingham bound carriageway. | Emergency 2Hr | 2013-03-27 | POTHOLE - URGENT | Emergency (2hr) repairs to potholes using Instarmac (25kg tub)
99445 | THE RIDGES | Finchampstead | 2013-04-03 | Pothole' | 24 Hours (40%) | 2013-04-03 | Pothole | Repairs to Potholes with Patching Material
99749 | THE RIDGES | Finchampstead | 2013-04-17 | Reinstate C/way 10mm (DBM)' New frame & cover 2 way lights 17/4 C2 info applied for | Programmed | 2013-07-02 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
99749 | THE RIDGES | Finchampstead | 2013-04-17 | Reinstate C/way 10mm (DBM)' New frame & cover 2 way lights 17/4 C2 info applied for | Programmed | 2013-07-02 | Reinstate C/way 10 (DBM) | two way
99749 | THE RIDGES | Finchampstead | 2013-04-17 | Reinstate C/way 10mm (DBM)' New frame & cover 2 way lights 17/4 C2 info applied for | Programmed | 2013-07-02 | Reinstate C/way 10 (DBM) | Percentage adjustment to the basic cost of sub-contractors and specialists
99749 | THE RIDGES | Finchampstead | 2013-04-17 | Reinstate C/way 10mm (DBM)' New frame & cover 2 way lights 17/4 C2 info applied for | Programmed | 2013-07-02 | Reinstate C/way 10 (DBM) | Take up or down and remove to tip off site chamber cover and frame 0.11sq.m. to 0.60sq.m.
99749 | THE RIDGES | Finchampstead | 2013-04-17 | Reinstate C/way 10mm (DBM)' New frame & cover 2 way lights 17/4 C2 info applied for | Programmed | 2013-07-02 | Reinstate C/way 10 (DBM) | Raising or lowering the level of cover/grating and frame 0.11sq.m.up to 0.60sq.m. on existing chamber not exceeding 150mm
99749 | THE RIDGES | Finchampstead | 2013-04-17 | Reinstate C/way 10mm (DBM)' New frame & cover 2 way lights 17/4 C2 info applied for | Programmed | 2013-07-02 | Reinstate C/way 10 (DBM) | Extra over previous two items for provision of new cover and frame.
99750 | THE RIDGES | Finchampstead | 2013-04-17 | Reinstate C/way 10mm (DBM)' Patch 1 = 2.9m x 1.4m, Patch 2 = 6.7m x 1.7m 2 way lights | 28 Days | 2013-05-15 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
99750 | THE RIDGES | Finchampstead | 2013-04-17 | Reinstate C/way 10mm (DBM)' Patch 1 = 2.9m x 1.4m, Patch 2 = 6.7m x 1.7m 2 way lights | 28 Days | 2013-05-15 | Reinstate C/way 10 (DBM) | two way
99750 | THE RIDGES | Finchampstead | 2013-04-17 | Reinstate C/way 10mm (DBM)' Patch 1 = 2.9m x 1.4m, Patch 2 = 6.7m x 1.7m 2 way lights | 28 Days | 2013-05-15 | Reinstate C/way 10 (DBM) | Percentage adjustment to the basic cost of sub-contractors and specialists
99750 | THE RIDGES | Finchampstead | 2013-04-17 | Reinstate C/way 10mm (DBM)' Patch 1 = 2.9m x 1.4m, Patch 2 = 6.7m x 1.7m 2 way lights | 28 Days | 2013-05-15 | Reinstate C/way 10 (DBM) | Adjustment for working outside normal hours (Code: YELLOW) Monday to Friday (inclusive) 0930 - 1600
99952 | THE RIDGES | Finchampstead | 2013-04-25 | Pothole' | 24 Hours (40%) | 2013-04-25 | Pothole | Repairs to Potholes with Patching Material
99953 | THE RIDGES | Finchampstead | 2013-04-25 | Reinstate C/way 10mm (DBM)' C/W 5.5m T/C low | 28 Days | 2013-04-27 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
99953 | THE RIDGES | Finchampstead | 2013-04-25 | Reinstate C/way 10mm (DBM)' C/W 5.5m T/C low | 28 Days | 2013-04-27 | Reinstate C/way 10 (DBM) | Percentage adjustment to the basic cost of sub-contractors and specialists
104226 | THE RIDGES | Finchampstead | 2013-11-27 | Break out/Relay Setts' 2 areas as marked (7.0m & 4.8m) Extra support for setts required on gravel side c/w 6.3m t/c med, 2 way lights required No footways 27th Nov C2 info requested | Programmed | 2014-01-16 | Break out/Relay Setts | Remove from store and relay granite kerbing 100mm x 150mm on edge with 150mm thick ST1 concrete bed and haunching laid straight or curved over 15 metre radius.
104226 | THE RIDGES | Finchampstead | 2013-11-27 | Break out/Relay Setts' 2 areas as marked (7.0m & 4.8m) Extra support for setts required on gravel side c/w 6.3m t/c med, 2 way lights required No footways 27th Nov C2 info requested | Programmed | 2014-01-16 | Break out/Relay Setts | Take up or down &amp; set aside for re-use or remove to store Granite Kerbing
104226 | THE RIDGES | Finchampstead | 2013-11-27 | Break out/Relay Setts' 2 areas as marked (7.0m & 4.8m) Extra support for setts required on gravel side c/w 6.3m t/c med, 2 way lights required No footways 27th Nov C2 info requested | Programmed | 2014-01-16 | Break out/Relay Setts | two way
104226 | THE RIDGES | Finchampstead | 2013-11-27 | Break out/Relay Setts' 2 areas as marked (7.0m & 4.8m) Extra support for setts required on gravel side c/w 6.3m t/c med, 2 way lights required No footways 27th Nov C2 info requested | Programmed | 2014-01-16 | Break out/Relay Setts | Percentage adjustment to the basic cost of sub-contractors and specialists
104226 | THE RIDGES | Finchampstead | 2013-11-27 | Break out/Relay Setts' 2 areas as marked (7.0m & 4.8m) Extra support for setts required on gravel side c/w 6.3m t/c med, 2 way lights required No footways 27th Nov C2 info requested | Programmed | 2014-01-16 | Break out/Relay Setts | Ganger
104226 | THE RIDGES | Finchampstead | 2013-11-27 | Break out/Relay Setts' 2 areas as marked (7.0m & 4.8m) Extra support for setts required on gravel side c/w 6.3m t/c med, 2 way lights required No footways 27th Nov C2 info requested | Programmed | 2014-01-16 | Break out/Relay Setts | Skilled Operative
104226 | THE RIDGES | Finchampstead | 2013-11-27 | Break out/Relay Setts' 2 areas as marked (7.0m & 4.8m) Extra support for setts required on gravel side c/w 6.3m t/c med, 2 way lights required No footways 27th Nov C2 info requested | Programmed | 2014-01-16 | Break out/Relay Setts | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
104339 | THE RIDGES | Finchampstead | 2013-12-03 | Pothole' x 2 | 24 Hours (40%) | 2013-12-04 | Pothole | Repairs to Potholes with Patching Material
106546 | THE RIDGES | Finchampstead | 2014-02-17 | Repair large pothole next to kerb along The Ridges approximately 200yds from the existing road works 'Wokingham Direct Report of urgent Highways issue' 'Pothole. Works to be carried out within 2hrs' | Emergency 2Hr | 2014-02-17 |  | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
106546 | THE RIDGES | Finchampstead | 2014-02-17 | Repair large pothole next to kerb along The Ridges approximately 200yds from the existing road works 'Wokingham Direct Report of urgent Highways issue' 'Pothole. Works to be carried out within 2hrs' | Emergency 2Hr | 2014-02-17 |  | Emergency (2hr) repairs to potholes using patching materials
107478 | THE RIDGES | Finchampstead | 2014-03-18 | Pothole, Damage already caused, on B3348 between Jubilee Road and The Ridges on the side of the road from Crowthorne to Finchampstead, 'Wokingham Direct Report of urgent Highways issue' 'Pothole. Works to be carried out within 2hrs' | Emergency 2Hr | 2014-03-18 |  | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
107478 | THE RIDGES | Finchampstead | 2014-03-18 | Pothole, Damage already caused, on B3348 between Jubilee Road and The Ridges on the side of the road from Crowthorne to Finchampstead, 'Wokingham Direct Report of urgent Highways issue' 'Pothole. Works to be carried out within 2hrs' | Emergency 2Hr | 2014-03-18 |  | Emergency (2hr) repairs to potholes using patching materials
107821 | THE RIDGES | Finchampstead | 2014-04-02 | Plug pothole and make safe Location: opposite greyhound pub, in the middle of the road 'Wokingham Direct Report of urgent Highways issue' 'Pothole. Works to be carried out within 2hrs' | Emergency 2Hr | 2014-04-02 |  | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
107821 | THE RIDGES | Finchampstead | 2014-04-02 | Plug pothole and make safe Location: opposite greyhound pub, in the middle of the road 'Wokingham Direct Report of urgent Highways issue' 'Pothole. Works to be carried out within 2hrs' | Emergency 2Hr | 2014-04-02 |  | Emergency (2hr) repairs to potholes using patching materials
107821 | THE RIDGES | Finchampstead | 2014-04-02 | Plug pothole and make safe Location: opposite greyhound pub, in the middle of the road 'Wokingham Direct Report of urgent Highways issue' 'Pothole. Works to be carried out within 2hrs' | Emergency 2Hr | 2014-04-02 |  | Emergency (2hr) repairs to potholes using Instarmac (25kg tub)
108119 | THE RIDGES | Finchampstead | 2014-04-15 | Pothole' x 5 In centre of carriageway. Stop/go required | 24 Hours (40%) | 2014-04-16 | Pothole | Repairs to Potholes with Patching Material
108119 | THE RIDGES | Finchampstead | 2014-04-15 | Pothole' x 5 In centre of carriageway. Stop/go required | 24 Hours (40%) | 2014-04-16 | Pothole | Provision of man and stop/go board
108119 | THE RIDGES | Finchampstead | 2014-04-15 | Pothole' x 5 In centre of carriageway. Stop/go required | 24 Hours (40%) | 2014-04-16 | Pothole | Repairs to Potholes with Proprietary Material
108121 | THE RIDGES | Finchampstead | 2014-04-15 | Pothole' x 2 In centre of carriageway. Stop/go required | 24 Hours (40%) | 2014-04-15 | Pothole | Repairs to Potholes with Patching Material
108121 | THE RIDGES | Finchampstead | 2014-04-15 | Pothole' x 2 In centre of carriageway. Stop/go required | 24 Hours (40%) | 2014-04-15 | Pothole | Provision of man and stop/go board
108121 | THE RIDGES | Finchampstead | 2014-04-15 | Pothole' x 2 In centre of carriageway. Stop/go required | 24 Hours (40%) | 2014-04-15 | Pothole | Repairs to Potholes with Proprietary Material
108138 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' c/w 6.6m t/c med | 28 Days | 2014-05-20 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
108138 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' c/w 6.6m t/c med | 28 Days | 2014-05-20 | Reinstate C/way 10 (DBM) | Percentage adjustment to the basic cost of sub-contractors and specialists
108138 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' c/w 6.6m t/c med | 28 Days | 2014-05-20 | Reinstate C/way 10 (DBM) | two way
108139 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' Patch 1 = 7.7m x 2.0m, Patch 2 = 3.3m x 2.0m, Patch 3 = 1.3m x 1.3m, Patch 4 = 1.0m x 1.0m, Patch 5 = 1.8m x 0.8m, Patch 6 = 1.4m x 1.2m c/w 6.6m t/c med 2 way lights 50mph. | 28 Days | 2014-05-19 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
108139 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' Patch 1 = 7.7m x 2.0m, Patch 2 = 3.3m x 2.0m, Patch 3 = 1.3m x 1.3m, Patch 4 = 1.0m x 1.0m, Patch 5 = 1.8m x 0.8m, Patch 6 = 1.4m x 1.2m c/w 6.6m t/c med 2 way lights 50mph. | 28 Days | 2014-05-19 | Reinstate C/way 10 (DBM) | Percentage adjustment to the basic cost of sub-contractors and specialists
108139 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' Patch 1 = 7.7m x 2.0m, Patch 2 = 3.3m x 2.0m, Patch 3 = 1.3m x 1.3m, Patch 4 = 1.0m x 1.0m, Patch 5 = 1.8m x 0.8m, Patch 6 = 1.4m x 1.2m c/w 6.6m t/c med 2 way lights 50mph. | 28 Days | 2014-05-19 | Reinstate C/way 10 (DBM) | two way
108140 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' c/w 6.6m t/c med 2 way lights 50mph. (on bend) | 28 Days | 2014-05-17 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
108140 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' c/w 6.6m t/c med 2 way lights 50mph. (on bend) | 28 Days | 2014-05-17 | Reinstate C/way 10 (DBM) | Percentage adjustment to the basic cost of sub-contractors and specialists
108140 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' c/w 6.6m t/c med 2 way lights 50mph. (on bend) | 28 Days | 2014-05-17 | Reinstate C/way 10 (DBM) | two way
108141 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' c/w 5.5m t/c med 2 way lights 50mph. (near bend) | 28 Days | 2014-05-20 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
108141 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' c/w 5.5m t/c med 2 way lights 50mph. (near bend) | 28 Days | 2014-05-20 | Reinstate C/way 10 (DBM) | Percentage adjustment to the basic cost of sub-contractors and specialists
108141 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' c/w 5.5m t/c med 2 way lights 50mph. (near bend) | 28 Days | 2014-05-20 | Reinstate C/way 10 (DBM) | two way
108141 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' c/w 5.5m t/c med 2 way lights 50mph. (near bend) | 28 Days | 2014-05-20 | Reinstate C/way 10 (DBM) | Adjustment for working outside normal hours (Code: YELLOW) Monday to Friday (inclusive) 0930 - 1600
108142 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' Patch 1 = 11.2m x 1.3m, Patch 2 = 5.6m x 1.5m c/w 6.0m t/c med 2 way lights 50mph. (near bend) | 28 Days | 2014-05-20 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
108142 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' Patch 1 = 11.2m x 1.3m, Patch 2 = 5.6m x 1.5m c/w 6.0m t/c med 2 way lights 50mph. (near bend) | 28 Days | 2014-05-20 | Reinstate C/way 10 (DBM) | Percentage adjustment to the basic cost of sub-contractors and specialists
108142 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' Patch 1 = 11.2m x 1.3m, Patch 2 = 5.6m x 1.5m c/w 6.0m t/c med 2 way lights 50mph. (near bend) | 28 Days | 2014-05-20 | Reinstate C/way 10 (DBM) | two way
108143 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' Patch 1 = 12.4m x 1.6m, Patch 2 = 9.5m x 1.7m c/w 6.0m t/c med 2 way lights 50mph. (near bend) | 28 Days | 2014-05-16 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
108143 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' Patch 1 = 12.4m x 1.6m, Patch 2 = 9.5m x 1.7m c/w 6.0m t/c med 2 way lights 50mph. (near bend) | 28 Days | 2014-05-16 | Reinstate C/way 10 (DBM) | Percentage adjustment to the basic cost of sub-contractors and specialists
108143 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' Patch 1 = 12.4m x 1.6m, Patch 2 = 9.5m x 1.7m c/w 6.0m t/c med 2 way lights 50mph. (near bend) | 28 Days | 2014-05-16 | Reinstate C/way 10 (DBM) | two way
108143 | THE RIDGES | Finchampstead | 2014-04-15 | Reinstate C/way 10mm (DBM)' Patch 1 = 12.4m x 1.6m, Patch 2 = 9.5m x 1.7m c/w 6.0m t/c med 2 way lights 50mph. (near bend) | 28 Days | 2014-05-16 | Reinstate C/way 10 (DBM) | Adjustment of the rate in previous item per 10mm in variation above or below 60mm in binder course
108144 | THE RIDGES | Finchampstead | 2014-04-15 | Footway Patch (m2)' 2 way lights, on bend c/w 5.5m t/c med | 28 Days | 2014-06-03 | Footway Patch (m2) | Patching in existing flexible footway, Type W, 75mm thick, 20mm surface Course, 55mm Binder Course
108144 | THE RIDGES | Finchampstead | 2014-04-15 | Footway Patch (m2)' 2 way lights, on bend c/w 5.5m t/c med | 28 Days | 2014-06-03 | Footway Patch (m2) | Percentage adjustment to the basic cost of sub-contractors and specialists
108144 | THE RIDGES | Finchampstead | 2014-04-15 | Footway Patch (m2)' 2 way lights, on bend c/w 5.5m t/c med | 28 Days | 2014-06-03 | Footway Patch (m2) | two way
108175 | THE RIDGES | Finchampstead | 2014-04-16 | Gully Emptier / Jetter during normal hours' Clear gully on the Ridges, Finchampstead - refer to hyperlinked plan for details. | 24 Hours (40%) | 2014-04-17 | RAY - Gully Emptier / Jetter | Driver / Machine Operator
108175 | THE RIDGES | Finchampstead | 2014-04-16 | Gully Emptier / Jetter during normal hours' Clear gully on the Ridges, Finchampstead - refer to hyperlinked plan for details. | 24 Hours (40%) | 2014-04-17 | RAY - Gully Emptier / Jetter | General Operative
108175 | THE RIDGES | Finchampstead | 2014-04-16 | Gully Emptier / Jetter during normal hours' Clear gully on the Ridges, Finchampstead - refer to hyperlinked plan for details. | 24 Hours (40%) | 2014-04-17 | RAY - Gully Emptier / Jetter | Gully emptier/jetter
108175 | THE RIDGES | Finchampstead | 2014-04-16 | Gully Emptier / Jetter during normal hours' Clear gully on the Ridges, Finchampstead - refer to hyperlinked plan for details. | 24 Hours (40%) | 2014-04-17 | RAY - Gully Emptier / Jetter | Provision of 3 men and stop/go boards plus radios
109283 | THE RIDGES | Finchampstead | 2014-06-10 | Clear all gullies on The Ridges - as clogged with leaves and overflowing into road all the way to the war memorial. TM possibly required - use stop and go boards 'Wokingham Direct report of a non urgent Highways issue' 'Gully Emptier / Jetter during n | 14 Days | 2014-06-12 |  | Driver / Machine Operator
109283 | THE RIDGES | Finchampstead | 2014-06-10 | Clear all gullies on The Ridges - as clogged with leaves and overflowing into road all the way to the war memorial. TM possibly required - use stop and go boards 'Wokingham Direct report of a non urgent Highways issue' 'Gully Emptier / Jetter during n | 14 Days | 2014-06-12 |  | General Operative
109283 | THE RIDGES | Finchampstead | 2014-06-10 | Clear all gullies on The Ridges - as clogged with leaves and overflowing into road all the way to the war memorial. TM possibly required - use stop and go boards 'Wokingham Direct report of a non urgent Highways issue' 'Gully Emptier / Jetter during n | 14 Days | 2014-06-12 |  | Gully emptier/jetter
109283 | THE RIDGES | Finchampstead | 2014-06-10 | Clear all gullies on The Ridges - as clogged with leaves and overflowing into road all the way to the war memorial. TM possibly required - use stop and go boards 'Wokingham Direct report of a non urgent Highways issue' 'Gully Emptier / Jetter during n | 14 Days | 2014-06-12 |  | Provision of man and stop/go board
110597 | THE RIDGES | Finchampstead | 2014-08-26 | Pothole' Plug approx 6 or 7 potholes between Dell Road junction and Springwood House some in the centre of the c/w. | 24 Hours (40%) | 2014-08-27 | Pothole | Repairs to Potholes with Patching Material
110597 | THE RIDGES | Finchampstead | 2014-08-26 | Pothole' Plug approx 6 or 7 potholes between Dell Road junction and Springwood House some in the centre of the c/w. | 24 Hours (40%) | 2014-08-27 | Pothole | Repairs to Potholes with Proprietary Material
112350 | THE RIDGES | Finchampstead | 2014-11-12 | Reinstate C/way 10mm (DBM)' Patch 1 = 7.8m x 2.9m (adjust 3 covers) Patch 2 = 6.2m x 2.9m (adjust 3 covers) Patch 3 = 7.3m x 1.2m 2 way lights C/w 6.0m, t/c med | 28 Days | 2014-12-04 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
112350 | THE RIDGES | Finchampstead | 2014-11-12 | Reinstate C/way 10mm (DBM)' Patch 1 = 7.8m x 2.9m (adjust 3 covers) Patch 2 = 6.2m x 2.9m (adjust 3 covers) Patch 3 = 7.3m x 1.2m 2 way lights C/w 6.0m, t/c med | 28 Days | 2014-12-04 | Reinstate C/way 10 (DBM) | Percentage adjustment to the basic cost of sub-contractors and specialists
112350 | THE RIDGES | Finchampstead | 2014-11-12 | Reinstate C/way 10mm (DBM)' Patch 1 = 7.8m x 2.9m (adjust 3 covers) Patch 2 = 6.2m x 2.9m (adjust 3 covers) Patch 3 = 7.3m x 1.2m 2 way lights C/w 6.0m, t/c med | 28 Days | 2014-12-04 | Reinstate C/way 10 (DBM) | two way
112350 | THE RIDGES | Finchampstead | 2014-11-12 | Reinstate C/way 10mm (DBM)' Patch 1 = 7.8m x 2.9m (adjust 3 covers) Patch 2 = 6.2m x 2.9m (adjust 3 covers) Patch 3 = 7.3m x 1.2m 2 way lights C/w 6.0m, t/c med | 28 Days | 2014-12-04 | Reinstate C/way 10 (DBM) | Raising or lowering the level of cover and frame up to 0.10sq.m. on existing chamber not exceeding 150mm
112350 | THE RIDGES | Finchampstead | 2014-11-12 | Reinstate C/way 10mm (DBM)' Patch 1 = 7.8m x 2.9m (adjust 3 covers) Patch 2 = 6.2m x 2.9m (adjust 3 covers) Patch 3 = 7.3m x 1.2m 2 way lights C/w 6.0m, t/c med | 28 Days | 2014-12-04 | Reinstate C/way 10 (DBM) | Raising or lowering the level of cover and frame up to 0.10sq.m. on existing chamber not exceeding 150mm
112350 | THE RIDGES | Finchampstead | 2014-11-12 | Reinstate C/way 10mm (DBM)' Patch 1 = 7.8m x 2.9m (adjust 3 covers) Patch 2 = 6.2m x 2.9m (adjust 3 covers) Patch 3 = 7.3m x 1.2m 2 way lights C/w 6.0m, t/c med | 28 Days | 2014-12-04 | Reinstate C/way 10 (DBM) | Adjustment for working outside normal hours (Code: YELLOW) Monday to Friday (inclusive) 0930 - 1600
113033 | THE RIDGES | Finchampstead | 2014-12-05 | Break out/Relay Setts' Relay loose setts | 24 Hours (40%) | 2014-12-06 | Break out/Relay Setts | Remove from store and relay granite kerbing 100mm x 150mm on edge with 150mm thick ST1 concrete bed and haunching laid straight or curved over 15 metre radius.
113033 | THE RIDGES | Finchampstead | 2014-12-05 | Break out/Relay Setts' Relay loose setts | 24 Hours (40%) | 2014-12-06 | Break out/Relay Setts | Take up or down &amp; set aside for re-use or remove to store Granite Kerbing
114165 | THE RIDGES | Finchampstead | 2015-01-27 | Pothole, Potential for damage, Pothole, , There are 2 potholes on the Wokingham bound carriageway between the war memorial and Wick Hill Lane (200m before Wick Hill Lane). 2 others were repaired at the same site in the last 2 weeks (can't believe these | Emergency 2Hr | 2015-01-27 |  | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
114165 | THE RIDGES | Finchampstead | 2015-01-27 | Pothole, Potential for damage, Pothole, , There are 2 potholes on the Wokingham bound carriageway between the war memorial and Wick Hill Lane (200m before Wick Hill Lane). 2 others were repaired at the same site in the last 2 weeks (can't believe these | Emergency 2Hr | 2015-01-27 |  | Emergency (2hr) repairs to potholes using Viafix
114647 | THE RIDGES | Finchampstead | 2015-02-10 | Pothole' by gully | 24 Hours (40%) | 2015-02-10 | Pothole | Repairs to Potholes with Patching Material
114647 | THE RIDGES | Finchampstead | 2015-02-10 | Pothole' by gully | 24 Hours (40%) | 2015-02-10 | Pothole | Repairs to Potholes with Proprietary Material
114648 | THE RIDGES | Finchampstead | 2015-02-10 | Reinstate C/way 10mm (DBM)' c/w 6.0m, t/c med 2 way lights. | 28 Days | 2015-03-26 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
114648 | THE RIDGES | Finchampstead | 2015-02-10 | Reinstate C/way 10mm (DBM)' c/w 6.0m, t/c med 2 way lights. | 28 Days | 2015-03-26 | Reinstate C/way 10 (DBM) | Percentage adjustment to the basic cost of sub-contractors and specialists
114648 | THE RIDGES | Finchampstead | 2015-02-10 | Reinstate C/way 10mm (DBM)' c/w 6.0m, t/c med 2 way lights. | 28 Days | 2015-03-26 | Reinstate C/way 10 (DBM) | two way
114648 | THE RIDGES | Finchampstead | 2015-02-10 | Reinstate C/way 10mm (DBM)' c/w 6.0m, t/c med 2 way lights. | 28 Days | 2015-03-26 | Reinstate C/way 10 (DBM) | Adjustment for working outside normal hours (Code: YELLOW) Monday to Friday (inclusive) 0930 - 1600
114649 | THE RIDGES | Finchampstead | 2015-02-10 | Break out/Relay Setts' 10/2 C2 stats applied for 20/2 C2 stats recevied. It would appear that BT, SEW, SGN and SSE (HV) all have plant in the area. Please complete the ticket. | Programmed | 2015-03-02 | Break out/Relay Setts | Remove from store and relay granite kerbing 100mm x 150mm on edge with 150mm thick ST1 concrete bed and haunching laid straight or curved over 15 metre radius.
114649 | THE RIDGES | Finchampstead | 2015-02-10 | Break out/Relay Setts' 10/2 C2 stats applied for 20/2 C2 stats recevied. It would appear that BT, SEW, SGN and SSE (HV) all have plant in the area. Please complete the ticket. | Programmed | 2015-03-02 | Break out/Relay Setts | Take up or down &amp; set aside for re-use or remove to store Granite Kerbing
114995 | THE RIDGES | Finchampstead | 2015-02-25 | Pothole, Damage already caused, Pothole, , HEADING TOWARDS FINCHAMPSTEAD, 2 POTHOLES ON LEFT HAND SIDE NEXT TO SOME ROAD SIGNS, JUST BEFORE DELL ROAD.,, | Emergency 2Hr | 2015-02-25 |  | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
114995 | THE RIDGES | Finchampstead | 2015-02-25 | Pothole, Damage already caused, Pothole, , HEADING TOWARDS FINCHAMPSTEAD, 2 POTHOLES ON LEFT HAND SIDE NEXT TO SOME ROAD SIGNS, JUST BEFORE DELL ROAD.,, | Emergency 2Hr | 2015-02-25 |  | Emergency (2hr) repairs to potholes using Viafix
115012 | THE RIDGES | Finchampstead | 2015-02-26 | Pothole, Potential for damage, Rather poor surface from this corner, around to the war memorial. Some potholes are getting significant and right in the path of wheels. The location is 100 yards to the left as you look down Dell Road from the B3348, | Emergency 2Hr | 2015-02-26 |  | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
115012 | THE RIDGES | Finchampstead | 2015-02-26 | Pothole, Potential for damage, Rather poor surface from this corner, around to the war memorial. Some potholes are getting significant and right in the path of wheels. The location is 100 yards to the left as you look down Dell Road from the B3348, | Emergency 2Hr | 2015-02-26 |  | Emergency (2hr) repairs to potholes using Instarmac (25kg tub)
116487 | THE RIDGES | Finchampstead | 2015-04-27 | Pothole, Damage already caused, Pothole on the ridges road, close to the post box. It is on the Finchampstead bound carriageway, | Emergency 2Hr | 2015-04-27 |  | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
116487 | THE RIDGES | Finchampstead | 2015-04-27 | Pothole, Damage already caused, Pothole on the ridges road, close to the post box. It is on the Finchampstead bound carriageway, | Emergency 2Hr | 2015-04-27 |  | Emergency (2hr) repairs to potholes using Instarmac (25kg tub)
119240 | THE RIDGES | Finchampstead | 2015-09-28 | Other Urgent Works. Works to be carried out within 2hrs.' Plug around gully that is located travelling from Crowthone towards Finchamsptead at sharp left hand bend as Wellingtonia Avenue becomes The Ridges. Gully has become detached from road surfa | Emergency 2Hr | 2015-09-28 | URGENT - Other Works | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
119240 | THE RIDGES | Finchampstead | 2015-09-28 | Other Urgent Works. Works to be carried out within 2hrs.' Plug around gully that is located travelling from Crowthone towards Finchamsptead at sharp left hand bend as Wellingtonia Avenue becomes The Ridges. Gully has become detached from road surfa | Emergency 2Hr | 2015-09-28 | URGENT - Other Works | Emergency (2hr) repairs to potholes using Viafix
119731 | THE RIDGES | Finchampstead | 2015-10-29 | Pothole. Works to be carried out within 2hrs' Plug pothole around a gully ON THE BEND opposite Ridge End | Emergency 2Hr | 2015-10-29 | URGENT - Pothole | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
119731 | THE RIDGES | Finchampstead | 2015-10-29 | Pothole. Works to be carried out within 2hrs' Plug pothole around a gully ON THE BEND opposite Ridge End | Emergency 2Hr | 2015-10-29 | URGENT - Pothole | Emergency (2hr) repairs to potholes using patching materials
119731 | THE RIDGES | Finchampstead | 2015-10-29 | Pothole. Works to be carried out within 2hrs' Plug pothole around a gully ON THE BEND opposite Ridge End | Emergency 2Hr | 2015-10-29 | URGENT - Pothole | Emergency (2hr) repairs to potholes using Instarmac (25kg tub)
119756 | THE RIDGES | Finchampstead | 2015-10-30 | Pothole' 2 no. at side of carriageway in patches 1 & 2 nr Havenwood 6 no. in centre of carriageway on bend nr Ridge End. 2 no. stop/go required. C/w 5.9m t/c med | 7 Days (10%) | 2015-11-03 | Pothole | Repairs to Potholes with Patching Material
119774 | THE RIDGES | Finchampstead | 2015-11-02 | Reinstate C/way 10mm (DBM)' Patch 1 = 3.0m x 1.2m Patch 2 = 1.9m x 1.1m (make firm loose gully grate) Patch 3 = 1.6m x 1.1m (at gully) c/w 6.0m t/c med. 2 way lights, patches on inside of bend | 28 Days | 2015-11-10 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
119774 | THE RIDGES | Finchampstead | 2015-11-02 | Reinstate C/way 10mm (DBM)' Patch 1 = 3.0m x 1.2m Patch 2 = 1.9m x 1.1m (make firm loose gully grate) Patch 3 = 1.6m x 1.1m (at gully) c/w 6.0m t/c med. 2 way lights, patches on inside of bend | 28 Days | 2015-11-10 | Reinstate C/way 10 (DBM) | two way
119774 | THE RIDGES | Finchampstead | 2015-11-02 | Reinstate C/way 10mm (DBM)' Patch 1 = 3.0m x 1.2m Patch 2 = 1.9m x 1.1m (make firm loose gully grate) Patch 3 = 1.6m x 1.1m (at gully) c/w 6.0m t/c med. 2 way lights, patches on inside of bend | 28 Days | 2015-11-10 | Reinstate C/way 10 (DBM) | Disposal of tar-bound material - WO 110000
119775 | THE RIDGES | Finchampstead | 2015-11-02 | Reinstate C/way 10mm (DBM)' Patch 1 = 1.0m x 1.0m, Patch 2 = 1.0m x 1.0m c/w 6.0m t/c med. 2 way lights, patches on inside of carriageway | 28 Days | 2015-11-10 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
119775 | THE RIDGES | Finchampstead | 2015-11-02 | Reinstate C/way 10mm (DBM)' Patch 1 = 1.0m x 1.0m, Patch 2 = 1.0m x 1.0m c/w 6.0m t/c med. 2 way lights, patches on inside of carriageway | 28 Days | 2015-11-10 | Reinstate C/way 10 (DBM) | two way
121207 | THE RIDGES | Finchampstead | 2016-01-18 | Pothole, Potential for damage, Directly outside Poor Ridge Cottage - pothole at the side of the road., | Emergency 2Hr | 2016-01-18 |  | Emergency (2hr) repairs to potholes using Instarmac (25kg tub)
121207 | THE RIDGES | Finchampstead | 2016-01-18 | Pothole, Potential for damage, Directly outside Poor Ridge Cottage - pothole at the side of the road., | Emergency 2Hr | 2016-01-18 |  | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
121237 | THE RIDGES | Finchampstead | 2016-01-19 | Pothole. Works to be carried out within 2hrs' Plug pothole located outside Poor Ridge Cottage. Road speed 50mph Road width 6.5m Traffic flow low-high depending on time of day Near bends Near junctions Traffic managment required | Emergency 2Hr | 2016-01-19 | URGENT - Pothole | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
121237 | THE RIDGES | Finchampstead | 2016-01-19 | Pothole. Works to be carried out within 2hrs' Plug pothole located outside Poor Ridge Cottage. Road speed 50mph Road width 6.5m Traffic flow low-high depending on time of day Near bends Near junctions Traffic managment required | Emergency 2Hr | 2016-01-19 | URGENT - Pothole | Emergency (2hr) repairs to potholes using patching materials
123916 | THE RIDGES | Finchampstead | 2016-04-12 | Out of Hours - EMERGENCY' Report of temporary traffic lights showing Red. Roadworks by Options Uttilities, contacted the temporary traffic lights engineer as the lights were locked. C3721 | Out of hours | 2016-04-03 | Out of Hours - EMERGENCY | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
123916 | THE RIDGES | Finchampstead | 2016-04-12 | Out of Hours - EMERGENCY' Report of temporary traffic lights showing Red. Roadworks by Options Uttilities, contacted the temporary traffic lights engineer as the lights were locked. C3721 | Out of hours | 2016-04-03 | Out of Hours - EMERGENCY | Ditto outside normal working hours
130105 | THE RIDGES | Finchampstead | 2016-12-16 | Investigate report below and clear 2 gullies including jetting outlets. Location: whiteknights, The Ridges. Refer to hyperlinked plan. Contact Nawaz (07714226751) /Eddie ( tel: 07880780360) if any issues Details: both rain gulleys beside the prop | 7 Days (10%) | 2017-01-03 | RAY - Gully Emptier / Jetter | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
130105 | THE RIDGES | Finchampstead | 2016-12-16 | Investigate report below and clear 2 gullies including jetting outlets. Location: whiteknights, The Ridges. Refer to hyperlinked plan. Contact Nawaz (07714226751) /Eddie ( tel: 07880780360) if any issues Details: both rain gulleys beside the prop | 7 Days (10%) | 2017-01-03 | RAY - Gully Emptier / Jetter | Driver / Machine Operator
130105 | THE RIDGES | Finchampstead | 2016-12-16 | Investigate report below and clear 2 gullies including jetting outlets. Location: whiteknights, The Ridges. Refer to hyperlinked plan. Contact Nawaz (07714226751) /Eddie ( tel: 07880780360) if any issues Details: both rain gulleys beside the prop | 7 Days (10%) | 2017-01-03 | RAY - Gully Emptier / Jetter | General Operative
130105 | THE RIDGES | Finchampstead | 2016-12-16 | Investigate report below and clear 2 gullies including jetting outlets. Location: whiteknights, The Ridges. Refer to hyperlinked plan. Contact Nawaz (07714226751) /Eddie ( tel: 07880780360) if any issues Details: both rain gulleys beside the prop | 7 Days (10%) | 2017-01-03 | RAY - Gully Emptier / Jetter | Gully emptier/jetter
131596 | THE RIDGES | Finchampstead | 2017-02-07 | Out of Hours - EMERGENCY' Pothole just before Poor Ridge Cottage. Filled in large pothole and cleared debris. | Out of hours | 2017-02-01 | Out of Hours - EMERGENCY | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
131596 | THE RIDGES | Finchampstead | 2017-02-07 | Out of Hours - EMERGENCY' Pothole just before Poor Ridge Cottage. Filled in large pothole and cleared debris. | Out of hours | 2017-02-01 | Out of Hours - EMERGENCY | Ditto outside normal working hours
131596 | THE RIDGES | Finchampstead | 2017-02-07 | Out of Hours - EMERGENCY' Pothole just before Poor Ridge Cottage. Filled in large pothole and cleared debris. | Out of hours | 2017-02-01 | Out of Hours - EMERGENCY | Emergency (2hr) repairs to potholes using Instarmac (25kg tub)
131914 | THE RIDGES | Finchampstead | 2017-02-16 | Overlay Footway (m2)' By tree adjacent to footway as marked. Remove raised tarmac and remains of concrete edgings prior to work. Remove small roots if possible. 2 way lights | 28 Days | 2017-04-26 | Overlay Footway (m2) | 6mm aggregate medium graded bitumen macadam surface course 20mm thick
131914 | THE RIDGES | Finchampstead | 2017-02-16 | Overlay Footway (m2)' By tree adjacent to footway as marked. Remove raised tarmac and remains of concrete edgings prior to work. Remove small roots if possible. 2 way lights | 28 Days | 2017-04-26 | Overlay Footway (m2) | Prepare existing surfaces to receive new paving
131914 | THE RIDGES | Finchampstead | 2017-02-16 | Overlay Footway (m2)' By tree adjacent to footway as marked. Remove raised tarmac and remains of concrete edgings prior to work. Remove small roots if possible. 2 way lights | 28 Days | 2017-04-26 | Overlay Footway (m2) | Apply approved weed killer to footway formation
131914 | THE RIDGES | Finchampstead | 2017-02-16 | Overlay Footway (m2)' By tree adjacent to footway as marked. Remove raised tarmac and remains of concrete edgings prior to work. Remove small roots if possible. 2 way lights | 28 Days | 2017-04-26 | Overlay Footway (m2) | Apply tack coat to flexible footways
131914 | THE RIDGES | Finchampstead | 2017-02-16 | Overlay Footway (m2)' By tree adjacent to footway as marked. Remove raised tarmac and remains of concrete edgings prior to work. Remove small roots if possible. 2 way lights | 28 Days | 2017-04-26 | Overlay Footway (m2) | Prepare edges of existing surfaces to receive a bituminous overlay by cutting & breaking out at edge of kerbs/path edgings nominally 300 wide by 15mm thick key-in-joint
131914 | THE RIDGES | Finchampstead | 2017-02-16 | Overlay Footway (m2)' By tree adjacent to footway as marked. Remove raised tarmac and remains of concrete edgings prior to work. Remove small roots if possible. 2 way lights | 28 Days | 2017-04-26 | Overlay Footway (m2) | two way
132879 | THE RIDGES | Finchampstead | 2017-03-14 | For the attention of Josh Kinge 'Pothole's Approx 13 on bend at Rhodoendron Corner and 1no. opposite Ridgeland House, all marked. 'Reinstate C/Way (HRA)' Works to be carried out at night | 28 Days |  | Pothole | Patching in Existing Surfacing, Type F 100mm thick, 40 mm Rolled Asphalt, 60mm rolled asphalt binder Course
132879 | THE RIDGES | Finchampstead | 2017-03-14 | For the attention of Josh Kinge 'Pothole's Approx 13 on bend at Rhodoendron Corner and 1no. opposite Ridgeland House, all marked. 'Reinstate C/Way (HRA)' Works to be carried out at night | 28 Days |  | Pothole | Provide temporary/emergency directional signs, warning, informatory and regulatory signs and road works delineators and barriers for diversion route (30 signs/barriers).
132879 | THE RIDGES | Finchampstead | 2017-03-14 | For the attention of Josh Kinge 'Pothole's Approx 13 on bend at Rhodoendron Corner and 1no. opposite Ridgeland House, all marked. 'Reinstate C/Way (HRA)' Works to be carried out at night | 28 Days |  | Pothole | Adjustment for variation of previous item for each sign/barrier above or below 30 signs/barriers.
132880 | THE RIDGES | Finchampstead | 2017-03-14 | Reinstate C/way 10mm (DBM)' Patch 1 = 1.0m x 1.0m, Patch 2 = 2.2m x 0.8m, Patch 3 = 3.6m x 1.5m c/w 6.4m, t/c med, 50mph, 2 way lights | 28 Days | 2017-05-11 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
132880 | THE RIDGES | Finchampstead | 2017-03-14 | Reinstate C/way 10mm (DBM)' Patch 1 = 1.0m x 1.0m, Patch 2 = 2.2m x 0.8m, Patch 3 = 3.6m x 1.5m c/w 6.4m, t/c med, 50mph, 2 way lights | 28 Days | 2017-05-11 | Reinstate C/way 10 (DBM) | two way
132882 | THE RIDGES | Finchampstead | 2017-03-14 | Reinstate C/way 10mm (DBM)' c/w 6.4m, t/c med, 50mph, 2 way lights | 28 Days | 2017-05-12 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
132882 | THE RIDGES | Finchampstead | 2017-03-14 | Reinstate C/way 10mm (DBM)' c/w 6.4m, t/c med, 50mph, 2 way lights | 28 Days | 2017-05-12 | Reinstate C/way 10 (DBM) | two way
132883 | THE RIDGES | Finchampstead | 2017-03-14 | Reinstate C/way 10mm (DBM)' Patch 1 = 2.7m x 1.0m, Patch 2 = 5.5m x 1.2m (5.5m of 100mm edge white line on completion of patch) c/w 6.0m, t/c med, 50mph, 2 way lights | 28 Days | 2017-05-11 | Reinstate C/way 10 (DBM) | Patching in existing flexible carriageway, Type J, 40mm thick 10mm aggregate DBM Surface Course, 60mm thick 20mm aggregate DBM binder course
132883 | THE RIDGES | Finchampstead | 2017-03-14 | Reinstate C/way 10mm (DBM)' Patch 1 = 2.7m x 1.0m, Patch 2 = 5.5m x 1.2m (5.5m of 100mm edge white line on completion of patch) c/w 6.0m, t/c med, 50mph, 2 way lights | 28 Days | 2017-05-11 | Reinstate C/way 10 (DBM) | two way
132883 | THE RIDGES | Finchampstead | 2017-03-14 | Reinstate C/way 10mm (DBM)' Patch 1 = 2.7m x 1.0m, Patch 2 = 5.5m x 1.2m (5.5m of 100mm edge white line on completion of patch) c/w 6.0m, t/c med, 50mph, 2 way lights | 28 Days | 2017-05-11 | Reinstate C/way 10 (DBM) | Continuous line in white thermoplastic screed with applied ballotini up to 100mm wide.
132883 | THE RIDGES | Finchampstead | 2017-03-14 | Reinstate C/way 10mm (DBM)' Patch 1 = 2.7m x 1.0m, Patch 2 = 5.5m x 1.2m (5.5m of 100mm edge white line on completion of patch) c/w 6.0m, t/c med, 50mph, 2 way lights | 28 Days | 2017-05-11 | Reinstate C/way 10 (DBM) | Intermittent line in white thermoplastic screed with applied ballotini 100mm wide
133871 | THE RIDGES | Finchampstead | 2017-04-20 | Other Urgent Works. Works to be carried out within 2hrs.' Check for loose kerbs/setts and make safe. Store any loose kerbs/setts. Call Ruth to advise what has been found. | Emergency 2Hr | 2017-04-20 | URGENT - Other Works | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
133871 | THE RIDGES | Finchampstead | 2017-04-20 | Other Urgent Works. Works to be carried out within 2hrs.' Check for loose kerbs/setts and make safe. Store any loose kerbs/setts. Call Ruth to advise what has been found. | Emergency 2Hr | 2017-04-20 | URGENT - Other Works | Emergency (2hr) repairs to potholes using patching materials
133902 | THE RIDGES | Finchampstead | 2017-04-21 | Pothole's Approx 13 on bend at Rhodoendron Corner and 1no. opposite Ridgeland House, all marked. | 7 Days (10%) |  | Pothole | Repairs to Potholes with Patching Material
133959 | THE RIDGES | Finchampstead | 2017-04-25 | Break out/Relay Setts' As marked in five areas opposite Fourwinds | 28 Days | 2017-05-19 | Break out/Relay Setts | Remove from store and relay granite kerbing 100mm x 150mm on edge with 150mm thick ST1 concrete bed and haunching laid straight or curved over 15 metre radius.
133959 | THE RIDGES | Finchampstead | 2017-04-25 | Break out/Relay Setts' As marked in five areas opposite Fourwinds | 28 Days | 2017-05-19 | Break out/Relay Setts | Take up or down &amp; set aside for re-use or remove to store Granite Kerbing
134597 | THE RIDGES | Finchampstead | 2017-05-21 | Pothole' As previously marked 2 way lights as in centre of road | 7 Days (10%) |  | Pothole | Repairs to Potholes with Patching Material
138375 | THE RIDGES | Finchampstead | 2017-09-25 | Inlay the following areas Patch 1 - 21.0mx6.0m Patch 2 - 107.0m x 5.75m Patch 3 - 155.0mx 5.75m adjust ironwork x 4 no, 1m setts Patch 4 - 30.0mx 6.2m Refresh all lines including Centre lines, Double Yellow Lines, Edge of Carriageway lines 'AD-HO | Programmed | 2018-04-04 | OTHER | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
138375 | THE RIDGES | Finchampstead | 2017-09-25 | Inlay the following areas Patch 1 - 21.0mx6.0m Patch 2 - 107.0m x 5.75m Patch 3 - 155.0mx 5.75m adjust ironwork x 4 no, 1m setts Patch 4 - 30.0mx 6.2m Refresh all lines including Centre lines, Double Yellow Lines, Edge of Carriageway lines 'AD-HO | Programmed | 2018-04-04 | OTHER | Thin Bonded Surface Course to Clause 942 with 14mm aggregate 40mm thick in carriageway, hard shoulder, hardstrip, lay-by and bus bay.
138375 | THE RIDGES | Finchampstead | 2017-09-25 | Inlay the following areas Patch 1 - 21.0mx6.0m Patch 2 - 107.0m x 5.75m Patch 3 - 155.0mx 5.75m adjust ironwork x 4 no, 1m setts Patch 4 - 30.0mx 6.2m Refresh all lines including Centre lines, Double Yellow Lines, Edge of Carriageway lines 'AD-HO | Programmed | 2018-04-04 | OTHER | Milling Pavement to 40mm depth.
138375 | THE RIDGES | Finchampstead | 2017-09-25 | Inlay the following areas Patch 1 - 21.0mx6.0m Patch 2 - 107.0m x 5.75m Patch 3 - 155.0mx 5.75m adjust ironwork x 4 no, 1m setts Patch 4 - 30.0mx 6.2m Refresh all lines including Centre lines, Double Yellow Lines, Edge of Carriageway lines 'AD-HO | Programmed | 2018-04-04 | OTHER | Tack Coat type K1-40 at a rate of spread of 0.3 to 0.5 litres per m2.
138375 | THE RIDGES | Finchampstead | 2017-09-25 | Inlay the following areas Patch 1 - 21.0mx6.0m Patch 2 - 107.0m x 5.75m Patch 3 - 155.0mx 5.75m adjust ironwork x 4 no, 1m setts Patch 4 - 30.0mx 6.2m Refresh all lines including Centre lines, Double Yellow Lines, Edge of Carriageway lines 'AD-HO | Programmed | 2018-04-04 | OTHER | Provide temporary/emergency directional signs, warning, informatory and regulatory signs and road works delineators and barriers for diversion route (30 signs/barriers).
138375 | THE RIDGES | Finchampstead | 2017-09-25 | Inlay the following areas Patch 1 - 21.0mx6.0m Patch 2 - 107.0m x 5.75m Patch 3 - 155.0mx 5.75m adjust ironwork x 4 no, 1m setts Patch 4 - 30.0mx 6.2m Refresh all lines including Centre lines, Double Yellow Lines, Edge of Carriageway lines 'AD-HO | Programmed | 2018-04-04 | OTHER | Continuous line in white thermoplastic screed with applied ballotini up to 100mm wide.
138375 | THE RIDGES | Finchampstead | 2017-09-25 | Inlay the following areas Patch 1 - 21.0mx6.0m Patch 2 - 107.0m x 5.75m Patch 3 - 155.0mx 5.75m adjust ironwork x 4 no, 1m setts Patch 4 - 30.0mx 6.2m Refresh all lines including Centre lines, Double Yellow Lines, Edge of Carriageway lines 'AD-HO | Programmed | 2018-04-04 | OTHER | Intermittent line in white thermoplastic screed with applied ballotini 100mm wide
138375 | THE RIDGES | Finchampstead | 2017-09-25 | Inlay the following areas Patch 1 - 21.0mx6.0m Patch 2 - 107.0m x 5.75m Patch 3 - 155.0mx 5.75m adjust ironwork x 4 no, 1m setts Patch 4 - 30.0mx 6.2m Refresh all lines including Centre lines, Double Yellow Lines, Edge of Carriageway lines 'AD-HO | Programmed | 2018-04-04 | OTHER | Raising or lowering the level of cover/grating and frame 0.11sq.m.up to 0.60sq.m. on existing chamber not exceeding 150mm
138375 | THE RIDGES | Finchampstead | 2017-09-25 | Inlay the following areas Patch 1 - 21.0mx6.0m Patch 2 - 107.0m x 5.75m Patch 3 - 155.0mx 5.75m adjust ironwork x 4 no, 1m setts Patch 4 - 30.0mx 6.2m Refresh all lines including Centre lines, Double Yellow Lines, Edge of Carriageway lines 'AD-HO | Programmed | 2018-04-04 | OTHER | Remove from store and relay granite kerbing 100mm x 150mm on edge with 150mm thick ST1 concrete bed and haunching laid straight or curved over 15 metre radius.
138375 | THE RIDGES | Finchampstead | 2017-09-25 | Inlay the following areas Patch 1 - 21.0mx6.0m Patch 2 - 107.0m x 5.75m Patch 3 - 155.0mx 5.75m adjust ironwork x 4 no, 1m setts Patch 4 - 30.0mx 6.2m Refresh all lines including Centre lines, Double Yellow Lines, Edge of Carriageway lines 'AD-HO | Programmed | 2018-04-04 | OTHER | Take up or down &amp; set aside for re-use or remove to store Granite Kerbing
138375 | THE RIDGES | Finchampstead | 2017-09-25 | Inlay the following areas Patch 1 - 21.0mx6.0m Patch 2 - 107.0m x 5.75m Patch 3 - 155.0mx 5.75m adjust ironwork x 4 no, 1m setts Patch 4 - 30.0mx 6.2m Refresh all lines including Centre lines, Double Yellow Lines, Edge of Carriageway lines 'AD-HO | Programmed | 2018-04-04 | OTHER | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
138375 | THE RIDGES | Finchampstead | 2017-09-25 | Inlay the following areas Patch 1 - 21.0mx6.0m Patch 2 - 107.0m x 5.75m Patch 3 - 155.0mx 5.75m adjust ironwork x 4 no, 1m setts Patch 4 - 30.0mx 6.2m Refresh all lines including Centre lines, Double Yellow Lines, Edge of Carriageway lines 'AD-HO | Programmed | 2018-04-04 | OTHER | Continuous line in yellow thermoplastic screed with applied ballotini 100mm wide, to Dia. 1017.
138375 | THE RIDGES | Finchampstead | 2017-09-25 | Inlay the following areas Patch 1 - 21.0mx6.0m Patch 2 - 107.0m x 5.75m Patch 3 - 155.0mx 5.75m adjust ironwork x 4 no, 1m setts Patch 4 - 30.0mx 6.2m Refresh all lines including Centre lines, Double Yellow Lines, Edge of Carriageway lines 'AD-HO | Programmed | 2018-04-04 | OTHER | Restricted hours (17.5% uplift) Adjustment for working outside normal hours (Code: YELLOW) Monday to Friday (inclusive) 0930 - 1600 IMPORTANT - The ""Rate"" needs to be MANUALLY CALCULATED AND ENTERED (Mayrise will otherwise just enter the 17.50!). NO A
142542 | THE RIDGES | Finchampstead | 2018-01-26 | Pothole. Works to be carried out within 2hrs' Plug pothole past the two æslowÆ signs approaching the war memorial and junction, by the 40 mph speed restriction. | Emergency 2Hr | 2018-01-26 | URGENT - Pothole | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
142542 | THE RIDGES | Finchampstead | 2018-01-26 | Pothole. Works to be carried out within 2hrs' Plug pothole past the two æslowÆ signs approaching the war memorial and junction, by the 40 mph speed restriction. | Emergency 2Hr | 2018-01-26 | URGENT - Pothole | Emergency (2hr) repairs to potholes using patching materials
142587 | THE RIDGES | Finchampstead | 2018-01-27 | Type: Pothole Details: I estimate that the pothole is approx one to two feet long and around six inches deep. In daylight it is just possible to avoid it, but in darkness it isn't. The pothole is located on the B3348 coming from The Ridges towards Finc | 28 Days |  | URGENT - Pothole | Repairs to Potholes with Patching Material
142587 | THE RIDGES | Finchampstead | 2018-01-27 | Type: Pothole Details: I estimate that the pothole is approx one to two feet long and around six inches deep. In daylight it is just possible to avoid it, but in darkness it isn't. The pothole is located on the B3348 coming from The Ridges towards Finc | 28 Days |  | URGENT - Pothole | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
142587 | THE RIDGES | Finchampstead | 2018-01-27 | Type: Pothole Details: I estimate that the pothole is approx one to two feet long and around six inches deep. In daylight it is just possible to avoid it, but in darkness it isn't. The pothole is located on the B3348 coming from The Ridges towards Finc | 28 Days |  | URGENT - Pothole | Emergency (2hr) repairs to potholes using patching materials
143228 | THE RIDGES | Finchampstead | 2018-02-16 | Pothole. Works to be carried out within 2hrs' Plug potholes located near bend as road becomes Wellingtonia Avenue on both directions | Emergency 2Hr | 2018-02-19 | URGENT - Pothole | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
143228 | THE RIDGES | Finchampstead | 2018-02-16 | Pothole. Works to be carried out within 2hrs' Plug potholes located near bend as road becomes Wellingtonia Avenue on both directions | Emergency 2Hr | 2018-02-19 | URGENT - Pothole | Emergency (2hr) repairs to potholes using patching materials
143556 | THE RIDGES | Finchampstead | 2018-02-26 | Pothole. Works to be carried out within 2hrs' Type: Pothole Details: Pothole 100mm deep, 900mm wide and 300mm long. Additional location details: Located between Jubilee Rd and Church Lane. Reported via Fix My Street. | Emergency 2Hr | 2018-02-26 | URGENT - Pothole | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
143556 | THE RIDGES | Finchampstead | 2018-02-26 | Pothole. Works to be carried out within 2hrs' Type: Pothole Details: Pothole 100mm deep, 900mm wide and 300mm long. Additional location details: Located between Jubilee Rd and Church Lane. Reported via Fix My Street. | Emergency 2Hr | 2018-02-26 | URGENT - Pothole | Emergency (2hr) repairs to potholes using patching materials
143557 | THE RIDGES | Finchampstead | 2018-02-26 | Pothole. Works to be carried out within 2hrs' Type: Pothole Details: Pothole 100mm deep, 900mm wide and 300mm long. Additional location details: Located between Jubilee Rd and Church Lane. Reported via Fix My Street. | Emergency 2Hr | 2018-02-26 | URGENT - Pothole | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
143557 | THE RIDGES | Finchampstead | 2018-02-26 | Pothole. Works to be carried out within 2hrs' Type: Pothole Details: Pothole 100mm deep, 900mm wide and 300mm long. Additional location details: Located between Jubilee Rd and Church Lane. Reported via Fix My Street. | Emergency 2Hr | 2018-02-26 | URGENT - Pothole | Emergency (2hr) repairs to potholes using patching materials
143557 | THE RIDGES | Finchampstead | 2018-02-26 | Pothole. Works to be carried out within 2hrs' Type: Pothole Details: Pothole 100mm deep, 900mm wide and 300mm long. Additional location details: Located between Jubilee Rd and Church Lane. Reported via Fix My Street. | Emergency 2Hr | 2018-02-26 | URGENT - Pothole | No Charge
143720 | THE RIDGES | Finchampstead | 2018-03-05 | Pothole' Plug all potholes from JN with Dell Road upto and around entrance for Ridge End house. In centre of C/W and near bend/ minor JN. 200KG [not marked] | 7 Days (10%) |  | Pothole | Repairs to Potholes with Patching Material
143965 | THE RIDGES | Finchampstead | 2018-03-09 | Pothole' Plug potholes (heading away from memorial) at below locations:- - After Springwood House by 50mph (not marked) - Further along from above location just past 30mph sign (not marked) - Further along from above location just after sharp | 24 Hours (40%) | 2018-03-10 | Pothole | Repairs to Potholes with Patching Material
144095 | THE RIDGES | Finchampstead | 2018-03-12 | AD-HOC ITEM.' Type: Damaged road, pavement or verge Details: Damaged road surface, vegetation overhanging / encroaching on the highway and footway, debris obstructing footway Additional location details: Various issues from junction of B3348 and B3016 a | 28 Days |  | OTHER | PROVISIONAL ITEM for ad-hoc works items not contained within the Schedule of Rates - ITEM NOT TO BE PRICED
144195 | THE RIDGES | Finchampstead | 2018-03-14 | Pothole. Works to be carried out within 2hrs' Type: Pothole Details: 2 x potholes Additional location details: Located between Jubilee Rd and Church Lane | Emergency 2Hr | 2018-03-14 | URGENT - Pothole | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
144195 | THE RIDGES | Finchampstead | 2018-03-14 | Pothole. Works to be carried out within 2hrs' Type: Pothole Details: 2 x potholes Additional location details: Located between Jubilee Rd and Church Lane | Emergency 2Hr | 2018-03-14 | URGENT - Pothole | Emergency (2hr) repairs to potholes using patching materials
144494 | THE RIDGES | Finchampstead | 2018-03-22 | Siding Footways' Location - From junction of Jubilee Road (where white railings are) to Dell Road Clear sections of footway where there is overgrowing vegetation by siding (approx 0.25m in width in places) in expose footway. | 28 Days | 2019-03-05 | Siding Footways | Siding not exceeding 250mm wide
151479 | THE RIDGES | Finchampstead | 2018-12-10 | Pothole. Works to be carried out within 2hrs' Plug pothole (not marked) reported as located aprroximately 20 yards into The Ridges from the War Memorial on westbound lane near middle of road | Emergency 2Hr | 2018-12-11 | URGENT - Pothole | Call out charge for Emergency Services Unit to carry out urgent or emergency works during normal working hours
151479 | THE RIDGES | Finchampstead | 2018-12-10 | Pothole. Works to be carried out within 2hrs' Plug pothole (not marked) reported as located aprroximately 20 yards into The Ridges from the War Memorial on westbound lane near middle of road | Emergency 2Hr | 2018-12-11 | URGENT - Pothole | Emergency (2hr) repairs to potholes using patching materials