## Project Schedule
Wokingham Borough Council
|  | Date | [7 empty] | Day Total | Running Total | Notes
| Dec-21 | Wednesday, Dec 08 |  | 0 | [5 empty] | 0 | 0
|  | Thursday, Dec 09 | [8 empty] | 0
|  | Friday, Dec 10 | [8 empty] | 0
|  | Saturday, Dec 11 | [8 empty] | 0
|  | Sunday, Dec 12 | [8 empty] | 0
|  | Monday, Dec 13 | [8 empty] | 0
|  | Tuesday, Dec 14 | [8 empty] | 0
|  | Wednesday, Dec 15 | [8 empty] | 0
|  | Thursday, Dec 16 |  | 0 | [5 empty] | 0 | 0
|  | Friday, Dec 17 | [8 empty] | 0
|  | Saturday, Dec 18 | [8 empty] | 0
|  | Sunday, Dec 19 | [8 empty] | 0
|  | Monday, Dec 20 |  | 1 | [5 empty] | 1 | 1 |  | Project kick off
|  | Tuesday, Dec 21 | [8 empty] | 1
|  | Wednesday, Dec 22 | [8 empty] | 1
|  | Thursday, Dec 23 | [8 empty] | 1
|  | Friday, Dec 24 | [8 empty] | 1
|  | Saturday, Dec 25 | [8 empty] | 1
|  | Sunday, Dec 26 | [8 empty] | 1
|  | Monday, Dec 27 | [8 empty] | 1
|  | Tuesday, Dec 28 | [8 empty] | 1
|  | Wednesday, Dec 29 | [8 empty] | 1
|  | Thursday, Dec 30 | [8 empty] | 1
|  | Friday, Dec 31 | [8 empty] | 1
| Jan-22 | Saturday, Jan 01 | [8 empty] | 1
|  | Sunday, Jan 02 | [8 empty] | 1 |  | SPRINT 1 | Included in this Sprint Backlog - in initial draft
|  | Monday, Jan 03 | [8 empty] | 1 |  |  | Setup the Azure environment
|  | Tuesday, Jan 04 |  |  | 1 |  |  |  |  | 1 | 2 |  |  | Establish connectivity to the Wokingham Internal domain
|  | Wednesday, Jan 05 |  | 1 | 1 |  |  |  |  | 2 | 4 |  |  | KPI Workshops - week One
|  | Thursday, Jan 06 |  |  | 1 |  |  |  |  | 1 | 5 |  |  | Setup of the data factory meta data framework
|  | Friday, Jan 07 | [8 empty] | 5 |  |  | Knowledge sharing
|  | Saturday, Jan 08 | [8 empty] | 5
|  | Sunday, Jan 09 | [8 empty] | 5
|  | Monday, Jan 10 |  | 1 | 1 |  |  |  |  | 2 | 7
|  | Tuesday, Jan 11 |  |  | 1 |  |  |  |  | 1 | 8
|  | Wednesday, Jan 12 |  |  | 1 |  |  |  |  | 1 | 9
|  | Thursday, Jan 13 |  |  | 1 |  |  |  |  | 1 | 10
|  | Friday, Jan 14 | [8 empty] | 10
|  | Saturday, Jan 15 | [8 empty] | 10
|  | Sunday, Jan 16 | [8 empty] | 10 |  | SPRINT 2 | Included in this Sprint Backlog - in initial draft
|  | Monday, Jan 17 |  | 1 | [5 empty] | 1 | 11 |  |  | KPI Workshops - week Two
|  | Tuesday, Jan 18 | 1 | [6 empty] | 1 | 12 |  |  | Loading of data into staging area
|  | Wednesday, Jan 19 |  |  | 1 |  |  |  |  | 1 | 13 |  |  | Modelling of data to form KPI's
|  | Thursday, Jan 20 |  |  | 1 |  |  |  |  | 1 | 14 |  |  | Knowledge sharing - Detail please
|  | Friday, Jan 21 | [8 empty] | 14 |  |  | Security and structural changes based on Workshop output
|  | Saturday, Jan 22 | [8 empty] | 14
|  | Sunday, Jan 23 | [8 empty] | 14 |  |  | overview of what is missing per kpi
|  | Monday, Jan 24 |  | 1 | [5 empty] | 1 | 15
|  | Tuesday, Jan 25 |  |  | 1 |  |  |  |  | 1 | 16
|  | Wednesday, Jan 26 |  |  | 1 |  |  |  |  | 1 | 17
|  | Thursday, Jan 27 |  |  | 1 |  |  |  |  | 1 | 18
|  | Friday, Jan 28 | [8 empty] | 18
|  | Saturday, Jan 29 | [8 empty] | 18
|  | Sunday, Jan 30 | [8 empty] | 18 |  | SPRINT 3 | Included in this Sprint Backlog - in initial draft
|  | Monday, Jan 31 |  | 1 | 1 |  |  |  |  | 2 | 20 |  |  | Modelling of data to form KPI's
| Feb-22 | Tuesday, Feb 01 | [8 empty] | 20 |  |  | Testing output and data validation
|  | Wednesday, Feb 02 | 1 |  | 1 |  |  |  |  | 2 | 22 |  |  | Knowledge sharing
|  | Thursday, Feb 03 | [8 empty] | 22 |  |  | Looking at WBC Template and navigation design
|  | Friday, Feb 04 | [8 empty] | 22 |  |  | Starting to develop first draft reports on any areas that we have been able to build in DW
|  | Saturday, Feb 05 | [8 empty] | 22
|  | Sunday, Feb 06 | [8 empty] | 22
|  | Monday, Feb 07 | 1 | 1 | [5 empty] | 2 | 24
|  | Tuesday, Feb 08 | 1 | [6 empty] | 1 | 25
|  | Wednesday, Feb 09 | 1 |  |  | 0.5 |  |  |  | 1.5 | 26.5
|  | Thursday, Feb 10 | 1 | [6 empty] | 1 | 27.5
|  | Friday, Feb 11 | [8 empty] | 27.5
|  | Saturday, Feb 12 | [8 empty] | 27.5
|  | Sunday, Feb 13 | [8 empty] | 27.5 |  | SPRINT 4 | Included in this Sprint Backlog - in initial draft
|  | Monday, Feb 14 |  | 1 |  | 0.5 |  | 0 |  | 1.5 | 29 |  |  | • Test the connectivity to Oracle Pending
|  | Tuesday, Feb 15 | [8 empty] | 29 |  |  | • Further Testing of individual columns of data from csv and excel needed
|  | Wednesday, Feb 16 |  |  |  | 1 |  |  |  | 1 | 30 |  |  | • Remove unused child pipelines to simplify the framework? This task may need further discussion Pending, not an urgent requirement
|  | Thursday, Feb 17 |  |  |  | 1 | 1 |  |  | 2 | 32 | Looking at Templates at Wokingham |  | • Complete the Design Document for the solution ready for discussion with WBC
|  | Friday, Feb 18 | [8 empty] | 32 |  |  | • Security Model needs to be discussed and agreed upon
|  | Saturday, Feb 19 | [8 empty] | 32
|  | Sunday, Feb 20 | [8 empty] | 32
|  | Monday, Feb 21 |  | 1 | [5 empty] | 1 | 33
|  | Tuesday, Feb 22 | 1 |  |  | 1 | 0.5 |  |  | 2.5 | 35.5
|  | Wednesday, Feb 23 | 1 |  |  | 1 |  |  |  | 2 | 37.5
|  | Thursday, Feb 24 | 1 | [6 empty] | 1 | 38.5
|  | Friday, Feb 25 | [8 empty] | 38.5
|  | Saturday, Feb 26 | [8 empty] | 38.5
|  | Sunday, Feb 27 | [8 empty] | 38.5 |  | SPRINT 5 | Included in this Sprint Backlog - in initial draft
|  | Monday, Feb 28 | 1 | 1 |  |  | 1 |  |  | 3 | 41.5 |  |  | The Power BI design template will be looked at on 17th February. Any prep for this should be started. Start to build out some KPI's in Power BI. Add in last few data sources.
| Mar-22 | Tuesday, Mar 01 | 1 |  |  | 1 |  |  |  | 2 | 43.5
|  | Wednesday, Mar 02 | 1 |  |  | 1 |  |  |  | 2 | 45.5
|  | Thursday, Mar 03 | [8 empty] | 45.5
|  | Friday, Mar 04 |  |  |  |  | 1 |  | 0 | 1 | 46.5
|  | Saturday, Mar 05 | [8 empty] | 46.5
|  | Sunday, Mar 06 | [8 empty] | 46.5
|  | Monday, Mar 07 | 1 | 1 |  |  |  |  | 0 | 2 | 48.5
|  | Tuesday, Mar 08 | 1 | [6 empty] | 1 | 49.5
|  | Wednesday, Mar 09 | 1 |  |  | 1 | 1 |  | 0 | 3 | 52.5
|  | Thursday, Mar 10 |  |  |  | 1 |  |  | 0 | 1 | 53.5
|  | Friday, Mar 11 | [6 empty] | 0 | 0 | 53.5
|  | Saturday, Mar 12 | [8 empty] | 53.5
|  | Sunday, Mar 13 | [8 empty] | 53.5 |  | SPRINT 6 | Included in this Sprint Backlog - in initial draft
|  | Monday, Mar 14 | 1 | 1 |  |  |  |  | 0 | 2 | 55.5 |  |  | build
|  | Tuesday, Mar 15 | 1 |  |  | 1 |  |  | 0 | 2 | 57.5
|  | Wednesday, Mar 16 | 1 |  |  | 1 |  |  | 0 | 2 | 59.5
|  | Thursday, Mar 17 |  |  |  |  | 1 |  | 0 | 1 | 60.5
|  | Friday, Mar 18 | [6 empty] | 0 | 0 | 60.5
|  | Saturday, Mar 19 | [8 empty] | 60.5
|  | Sunday, Mar 20 | [8 empty] | 60.5
|  | Monday, Mar 21 | 1 | [6 empty] | 1 | 61.5
|  | Tuesday, Mar 22 | 1 | [6 empty] | 1 | 62.5
|  | Wednesday, Mar 23 | 1 | 1 |  | 1 | 1 |  |  | 4 | 66.5
|  | Thursday, Mar 24 |  |  |  | 1 |  |  |  | 1 | 67.5
|  | Friday, Mar 25 | [8 empty] | 67.5
|  | Saturday, Mar 26 | [8 empty] | 67.5
|  | Sunday, Mar 27 | [8 empty] | 67.5 |  | SPRINT 7 | Included in this Sprint Backlog - in initial draft
|  | Monday, Mar 28 | 1 | 1 | [5 empty] | 2 | 69.5 |  |  | tesing
|  | Tuesday, Mar 29 | 1 |  |  | 1 |  |  |  | 2 | 71.5
|  | Wednesday, Mar 30 | 1 | [6 empty] | 1 | 72.5
|  | Thursday, Mar 31 | [8 empty] | 72.5
| Apr-22 | Friday, Apr 01 | [8 empty] | 72.5
|  | Saturday, Apr 02 | [8 empty] | 72.5
|  | Sunday, Apr 03 | [8 empty] | 72.5
|  | Monday, Apr 04 | 1 | 1 | [5 empty] | 2 | 74.5
|  | Tuesday, Apr 05 | 1 | [6 empty] | 1 | 75.5
|  | Wednesday, Apr 06 | 1 | [6 empty] | 1 | 76.5 | Moved from 14th of Feb
|  | Thursday, Apr 07 | 1 | [6 empty] | 1 | 77.5 | Moved from 15th of Feb
|  | Friday, Apr 08 | [8 empty] | 77.5
|  | Saturday, Apr 09 | [8 empty] | 77.5
|  | Sunday, Apr 10 | [8 empty] | 77.5 |  | SPRINT 8 | Included in this Sprint Backlog - in initial draft
|  | Monday, Apr 11 |  | 1 | [5 empty] | 1 | 78.5 |  |  | testing
|  | Tuesday, Apr 12 | 1 | [6 empty] | 1 | 79.5
|  | Wednesday, Apr 13 | 1 | [6 empty] | 1 | 80.5 | Moved from 16th of Feb & 8th Apr
|  | Thursday, Apr 14 | [8 empty] | 80.5
|  | Friday, Apr 15 | [8 empty] | 80.5
|  | Saturday, Apr 16 | [8 empty] | 80.5
|  | Sunday, Apr 17 | [8 empty] | 80.5
|  | Monday, Apr 18 | [8 empty] | 80.5
|  | Tuesday, Apr 19 | 1 | 0.5 | [5 empty] | 1.5 | 82
|  | Wednesday, Apr 20 | 1 | [6 empty] | 1 | 83
|  | Thursday, Apr 21 | [8 empty] | 83
|  | Friday, Apr 22 | [8 empty] | 83
|  | Saturday, Apr 23 | [8 empty] | 83
|  | Sunday, Apr 24 | [8 empty] | 83
|  | Monday, Apr 25 | 1 | [6 empty] | 1 | 84
|  | Tuesday, Apr 26 | 1 | 0.5 | [5 empty] | 1.5 | 85.5
|  | Wednesday, Apr 27 | [8 empty] | 85.5
|  | Thursday, Apr 28 | [8 empty] | 85.5
|  | Friday, Apr 29 | [8 empty] | 85.5
|  | Saturday, Apr 30 | [8 empty] | 85.5
| May-22 | Sunday, May 01 | [8 empty] | 85.5
|  | Monday, May 02 | [8 empty] | 85.5
|  | Tuesday, May 03 | 1 | [6 empty] | 1 | 86.5
|  | Wednesday, May 04 | [8 empty] | 86.5
|  | Thursday, May 05 |  | 0.5 | [5 empty] | 0.5 | 87
| Total |  | 35 | 17.5 | 14 | 14 | 6.5 | 0 | 0 | 87