## Plan
Actions transferred to RDGL go live plan in PPP main folder 3 March 2022
DIGITAL AND IT WORKSTREAM | Start | Finish | Orgnisation | Team / person | Status
Governance
Set up meetings with workstream and Civica |  |  | WBC | Kate Julie | complete
Create workstream plan | Mon 12/07/21 | Fri 29/09/21 | WBC | Kate Julie | complete
Options appraisal of technology
SWOT analysis workshops | Tue 06/07/21 | Thu 08/07/21 | WBC |  | complete
Recommendations finalised | Mon 12/07/21 | Wed 14/07/21 | WBC |  | complete
Submit SWOT recommendations to Director for sign off | Wed 21/07/21 | Fri 23/07/21 | WBC |  | complete
Procurement
Meet with Procurement | Thu 08/07/21 | Thu 08/07/21 | WBC |  | complete
Draft Material Decision and send to Procurment | Thu 15/07/21 | Thu 15/07/21 | WBC |  | complete
Send Material Decision to AD to secure Director approval | Wed 21/07/21 | Fri 23/07/21 | WBC |  | complete
Sign and send CCN to Civica | Thu 22/07/21 | Fri 23/07/21 | WBC |  | complete
Raise PO and send to Civica | Mon 26/07/21 | Wed 28/07/21 | WBC |  | complete
PPP IMT Survey
Create template | Fri 09/04/21 | Tue 13/04/21 | WBC |  | complete
Draft survey | Wed 14/04/21 | Fri 23/04/21 | WBC |  | complete
Finalise survey | Thu 29/04/21 | Thu 06/05/21 | WBC |  | complete
Send survey to PPP | Fri 07/05/21 | Fri 07/05/21 | WBC |  | complete
Completed survey | Fri 28/05/21 | Fri 28/05/21 | WBC |  | complete
PPP/WBC analysis
Assess volume of data that needs to be migrated - so that correct size known for servers and infrastructure | Thurs 30/09/21 | Fri 29/11/21 | WBC |  | complete
Identify West Berks testers | Thu 19/09/21 | Fri 21/01/22 | WBC West Berks | Paul Ed | complete
Civica pre-reqs/tech prep
Engage with Civica and hold inception meeting | Mon 19/04/21 | Fri 30/04/21 | WBC |  | complete
Workshop with Civica | Thu 17/06/21 | Thu 17/06/21 | WBC West Berks |  | complete
Draft change request document regarding additional licences and instance | Thu 02/09/21 | Thu 02/09/21 | WBC | Kate | complete
Sumbit CR to CAB regarding additional licences and instance | Thu 02/09/21 | Thu 02/09/21 | WBC | Kate | complete
Attend CAB for approval regarding additional licences and instance | Tues 07/09/21 | Tues 07/09/21 | WBC | Kate | complete
Add 20 licences to existing instance | Mon 20/09/21 | Mon 20/09/21 | Civica | Supplier name | complete
Create an additional APP system for Regulatory Services on the APP server: | Mon 20/09/21 | Mon 20/09/21 | Civica | Supplier name | complete
Additional APP Data Web service & application pool in IIS | Mon 20/09/21 | Mon 20/09/21 | Civica | Supplier name | complete
Additional entry in the client configuration file | Mon 20/09/21 | Mon 20/09/21 | Civica | Supplier name | complete
Adding the data integrity check into the existing daily scheduled task for this | Mon 20/09/21 | Mon 20/09/21 | Civica | Supplier name | complete
Adding clean up tasks to the clean up job | Mon 20/09/21 | Mon 20/09/21 | Civica | Supplier name | complete
An additional scheduled task to check the integrity of the new (Sculptor) database at start up | Thur 30/09/21 | Thur 30/09/21 | Civica | Supplier name | complete
If the SQL Mirror database is required, will create the database, connect the system to it & sync the two dbs | Thur 30/09/21 | Thur 30/09/21 | Civica | Supplier name | complete
Transfer an empty APP v 8.8.0 system & client & patch over to the APP server (the WB system is a version behind WBC) | Thur 30/09/21 | Thur 30/09/21 | Civica | Supplier name | complete
Once the system has been created & prior to UAT the 8.8.0 client & patch will need to be installed on to the WBC RDS environment alongside the existing 8.9.0 client |  |  | Civica | Supplier name | complete
Ask West Berks for file structure | Thur 30/09/21 | Thur 30/09/21 | WBC | Kate | complete
Set up same folder structure on the network drive where documents will be stored | Mon 4/10/21 | Fri 29/11/21 | WBC |  | complete
Provide Civica with access to the current APP server which houses the APP planning system, where a new APP instance will be created for APP Regulatory services | Mon 20/09/21 | Mon 20/09/22 | WBC |  | complete
Facilitate a discussion between Civica and the appropriate party in order to produce a detailed specification of the data that is to be cleansed from the APP Regulatory Services system | Weds 22/09/21 | Weds 22/09/21 | WBC |  | complete
Ensure that Civica are provided access to the West Berkshire APP server, where the data currently resides, to ensure that the data can be copied | w/c 27/09/21 | w/c 27/09/21 | West Berks | Phil | complete
Produce a detailed specification of the data cleanse, indicating the data to be cleansed from the new system | Thurs 23/09/21 | Thurs 23/09/21 | Civica | Supplier name | complete
Sign off the specification before the data transfer and cleansing work commences | Tues 28/09/21 | Tues 28/09/21 | WBC West Berks |  | complete
Create an APP system on WBC’s server, along with the necessary connectors/integrations | Thurs 30/09/21 | Fri 15/10/21 | Civica | Supplier name | complete
Create a SQL database, as a mirror of the APP data | Thurs 30/09/21 | Fri 15/10/21 | Civica | Supplier name | complete
Transfer data from WB to WBC via secure FTP | Thurs 30/09/21 | Fri 15/10/21 | Civica | Supplier name | complete
Cleanse non WBC data from the new APP system | Thurs 30/09/21 | Fri 15/10/21 | Civica | Supplier name | complete
Let West Berks know which documents we need | Thurs 30/09/21 | Fri 15/10/21 | WBC |  | complete
Migrate of all documents from West Berks to the new network drive in WBC | Thurs 30/09/21 | Fri 15/12/21 | WBC |  | complete
Amend the document paths to reflect their new location | Thurs 30/09/21 | Fri 28/01/22 | Civica WBC | Supplier name | complete
Actions transferred to RDGL go live plan in PPP main folder 3 March 2022
Full data / documents extract taken and sent to WBC 7 Feb - if tested successfully only a small delta will need transferring w/c 28 March | Mon 07/02/22 | Fri 11/02/22 | WBC | Lucia Ed Kim | in progress
Test the migrated data and sign off a stage gate | Thurs 30/09/21 | Fri 04/03/22 | WBC | Ed and team | in progress
Arrangement for transfer over of documents that sit within emails and personal files of PPP staff and on any hard drives | Fri 28/01/22 | Fri 04/03/22 | Civica WBC WB | Kate Julie James | in progress
Type of storage agreed for service documents and letters (shared drive) | Thurs 13/01/22 | Fri 04/03/22 | WBC | Kate Ed | in progress
Mailboxes setup for Licensing, Environmental Health and ASB and access given to staff | Thurs 27/01/22 | Mon 28/03/22 | WBC | Kate Ed | in progress
Document retention arrangements are in place and signed off | Thurs 27/01/22 | Fri 25/02/22 | Civica WBC | Kate Ed Stuart | complete
Out of hours technical support expectations communicated and agreed with service | Thurs 27/01/22 | Mon 28/03/22 | WBC | Ed Glynn | in progress
APPs team support agreed with service | Thurs 27/01/22 | Mon 28/03/22 | WBC | Ed Glynn Julie | in progress
System owner/admininstrator identified in service for Civica (Kim Bridger) | Thurs 24/02/22 | Fri 25/02/22 | WBC | Ed | complete
Civica APP build & data migration 1
Workshop on data migration with WB and Civica | Weds 22/09/21 | Weds 22/09/21 | WBC WB Civica |  | complete
Creation of new APP Licences on Wokingham's server | Mon 20/09/21 | Mon 20/09/21 | Civica |  | complete
Data cleansing exercise
Deletion of data as per Specification |  |  | Civica |  | complete
Test Run 1 - Civica UAT support / bug fixing - West Berks to agree that all relevant data has been deleted/retained | Fri 01/10/21 | Fri 29/10/21 | Civica |  | complete
Test Run 1 - West Berks User Acceptance Testing - West Berks to agree that all relevant data has been deleted/retained | Fri 01/10/21 | Fri 29/10/21 | WB |  | complete
Test Run 1 - WBC User Acceptance Testing | Mon 11/10/21 | Fri 29/10/21 | WBC |  | complete
Civica APP build & data migration 2
Test Run 2 - Test APP system copy | Fri 10/12/21 | Fri 10/12/22 | Civica |  | complete
Test Run 2 - Test APP system configuration & cleansing | Mo 13/12/21 | Mo 13/12/22 | Civica |  | complete
Test Run 2 - Deletion of data as per Specification | Mon 13/12/21 | Mon 13/12/21 | Civica |  | complete
Test Run 2 - Civica UAT support/bug fixing & QA | Tue 14/12/21 | Fri 04/03/22 | Civica |  | in progress
Test Run 2 - West Berks - User Acceptance Testing | Tue 14/12/21 | Fri 04/03/22 | West Berks |  | in progress
Test run 2 Data UAT Testing - West Berks to agree that all relevant data has been deleted/retained | Tue 14/12/21 | Fri 04/03/22 | West Berks |  | in progress
Civica APP build & live run
Civica build the new sculptor and SQL database in live at WBC | Mon 28/03/22 | Mon 28/03/22 | Civica |  | not started
Civica undertake deletion of West Berks data | Mon 28/03/22 | Mon 28/03/22 | Civica |  | not started
Civica and WBC produce list of documents to send to West Berks | Mon 28/03/22 | Mon 28/03/22 | Civica WBC |  | not started
West Berks run the document extract | Weds 30/03/22 | Weds 30/03/22 | West Berks |  | not started
West Berks SFTP (from their office) the documents to WBC | Thurs 31/03/22 | Thurs 31/03/22 | West Berks |  | not started
WBC move documents | Thurs 31/03/22 | Thurs 31/03/22 | WBC | Colin | not started
Civica repoint when WBC have moved documents | Thurs 31/03/22 | Thurs 31/03/22 | Civica |  | not started
Flare account - Civica to enable us to reset | Thurs 31/03/22 | Thurs 31/03/22 | Civica |  | not started
Set up any new accounts on Civica APP | Thurs 31/03/22 | Thurs 31/03/22 | WBC | APPs team | not started
Live Run - Civica UAT support/bug fixing & QA | Weds 30/03/22 | Thurs 31/03/22 | Civica Consultant |  | not started
Live run - West Berks to agree that all relevant data has been deleted/retained | Weds 30/03/22 | Thurs 31/03/22 | West Berks |  | not started
Live Run - WBC - UAT | Weds 30/03/22 | Thurs 31/03/22 | WBC |  | not started
Infrastructure preparation
Firewalls changes and secure hardware | Weds 01/12/2021 | Weds 02/02/2022 | WBC | Chris | complete
Terminal server plus 8.8.0 and 8.9.0. | Mon 17/01/2022 | Mon 11/02/2022 | WBC | James Jaz | complete
Change board | Tues 04/01/2022 | Tues 04/01/2022 | WBC | James Kate | complete
URLS set up as per Civica instructions | Weds 05/01/2022 | Weds 02/02/2022 | WBC | Sarah James Chris | complete
DNS entries | Weds 01/12/2021 | Tues 25/02/2022 | WBC | James Sarah | complete
Transfer an empty APP v 8.8.0 system & client & patch over to the APP server (the WB system is a version behind WBC) | Weds 01/12/2021 | Mon 31/01/2022 | WBC | James | complete
Prior to UAT the 8.8.0 client & patch install on to the WBC RDS environment alongside the existing 8.9.0 client | Weds 01/12/2021 | Mon 31/01/2022 | WBC | James | complete
Westcot Annex
Refurbishment - dependancy for IT and internet - ensure impact mitigated against | Tue 01/02/22 | Fri 18/02/22 | WBC | Glynn Kate Chris | in progress
Working line at Westcot Annex to be installed | Tue 01/02/22 | Fri 04/03/22 | WBC | Chris | in progress
Set up an internet connection and build corporate connection over the top | Weds 01/12/2021 | Fri 04/03/22 | WBC | Chris | in progress
Purchase and set up firewalls | Mon 03/01/2022 | Tues 25/02/2022 | WBC | Chris | in progress
Test connection | Tues 25/02/2022 | Tues 04/03/2022 | WBC | Chris | in progress
Prep the rack for the new line, move all the patching, sort out the Virgin fibre | Tues 25/02/2022 | Tues 04/03/2022 | WBC | Chris | in progress
Civica Online Forms Portal
Build & Pre-requisites | Wed 03/11/21 | Tue 30/11/21
Pre-requisite information provided | Wed 03/11/21 | Wed 03/11/21 | Civica PM |  | complete
Pre-requisites in place | Mon 22/11/21 | Tue 30/11/21 | Customer ICT Team & Project Team |  | complete
TEST Install | Wed 01/12/21 | Fri 03/12/21
AOM Licenses available | Wed 01/12/21 | Wed 01/12/21 | Civica Technical Team |  | complete
ConnectAll installed | Wed 01/12/21 | Thu 02/12/21 | Civica Technical Team |  | complete
Mobile Solution (OCS) installed | Wed 01/12/21 | Thu 02/12/21 | Civica Technical Team |  | complete
AOM installed | Wed 01/12/21 | Wed 01/12/21 | Civica Technical Team |  | complete
Documentation produced (SDF) | Fri 03/12/21 | Fri 03/12/21 | Civica Technical Team |  | complete
Mobile Solution Configuration | Mon 06/12/21 | Fri 04/02/22 |  |  | in progress
Mobile Solution Configuration | Mon 06/12/21 | Fri 04/02/22 | Civica Consultant |  | complete
Documentation produced (SDF) | Fri 28/01/22 | Fri 04/02/22 | Civica Consultant |  | in progress
Online Forms Configuration | Mon 06/12/21 | Fri 04/02/22 |  |  | in progress
Online Forms Configuration | Mon 06/12/21 | Fri 04/02/22 | Civica Consultant |  | complete
Documentation produced (SDF) | Fri 28/01/22 | Fri 04/02/22 | Civica Consultant |  | in progress
PROJECT STAGE GATE - Ready for UAT | Fri 28/01/22 | Fri 04/02/22 |  |  | in progress
Portals delay - handover took place Mon 14 Feb - testing plan in progress | Mon 14/02/22 | Fri 18/02/22 | WBC Civica |  | in progress
USER ACCEPTANCE TESTING | Mon 03/01/22 | Mon 14/03/22 |  |  | in progress
Testing Preparation | Mon 03/01/22 | Mon 31/01/22 |  |  | in progress
Acceptance criteria defined | Mon 03/01/22 | Fri 04/02/22 | Customer PM |  | in progress
Test scripts prepared | Mon 03/01/22 | Fri 04/02/22 | Customer ICT Team & Project Team |  | in progress
End to End Testing | Tue 01/02/22 | Mon 14/03/22 |  |  | not started
End to End - Testing | Fri 18/02/22 | Fri 04/03/22 | Customer Project Team |  | not started
Issues triaged, added to UAT log & reported at agreed frequency | Mon 07/03/22 | Tue 08/03/22 | Customer PM |  | not started
Defects triaged | Wed 09/03/22 | Thu 10/03/22 | Civica PM,Civica QA Team,Civica Support Team |  | not started
Defect fixing & QA | Thu 10/03/22 | Fri 11/03/22 | Civica QA Team |  | not started
Re-testing - if required | Mon 14/03/22 | Mon 14/03/22 | Civica PM,Customer Project Team |  | not started
PROJECT STAGE GATE - UAT signed off | Mon 14/03/22 | Mon 14/03/22 |  |  | not started
GO LIVE | Mon 14/03/22 | Fri 15/04/22 |  |  | not started
End User Training - if required | Mon 14/03/22 | Fri 25/03/22 |  |  | not started
End user training | Mon 14/03/22 | Fri 25/03/22 | Customer PM,Customer Project Team |  | not started
Pre-requisites | Mon 14/03/22 | Fri 18/03/22 |  |  | not started
Change Board for live
Live servers ready | Mon 14/03/22 | Fri 18/03/22 | Customer ICT Team |  | not started
Downtime agreed - if required | Mon 14/03/22 | Mon 14/03/22 | Customer PM |  | not started
PROJECT MILESTONE - Go (No Go) | Fri 18/03/22 | Fri 18/03/22 |  |  | not started
LIVE | Mon 21/03/22 | Thu 31/03/22 |  |  | not started
ConnectAll configured & enabled in LIVE (APPEHL) | Mon 21/01/22 | Thu 24/01/22 | Civica Technical Team,Civica Consultant
AOM configured & enabled in LIVE | Mon 21/01/22 | Thu 24/01/22 | Civica Consultant,Civica Technical Team
Online forms configured & enabled in LIVE (APPEHL) | Mon 21/01/22 | Thu 24/01/22 | Civica Technical Team
AOM Licenses available | Tue 01/03/22 | Wed 02/03/22 | Civica Technical Team
LIVE AOM install completed | Mon 24/01/22 | Mon 24/01/22 | Civica Technical Team |  | complete
LIVE ConnectAll install completed | Tue 01/03/22 | Wed 02/03/22 | Civica Technical Team
LIVE Mobile Solution (OCS) install completed | Tue 01/03/22 | Wed 02/03/22 | Civica Technical Team
Documentation produced (SDF) | Thu 03/03/22 | Thu 03/03/22 | Civica Technical Team
Final go live configuration | Thu 24/03/22 | Tue 29/03/22 | Civica Consultant
Go Live | Thu 31/03/22 | Thu 31/03/22 | Civica Consultant |  | not started
Support Handover | Fri 01/04/22 | Thu 14/04/22 | Civica PM,Customer PM |  | not started
Confirm handover to support | Fri 01/04/22 | Fri 01/04/22 | Civica Consultant,Civica PM |  | not started
Support Watch | Fri 01/04/22 | Thu 14/04/22 | Civica Support Team |  | not started
Front-end Digital Customer Provision
Workshop | Mon 27/09/21 | Mon 27/09/21 | WBC - Digital | Sarah | complete
Undertake full document audit based on site map | Weds 06/10/21 | Weds 06/10/21 | WBC | Sarah | complete
Review 162 content pages based on page views | Weds 01/12/2021 | Fri 31/12/2021 | WBC | Sarah | complete
Review Tobacco and alcohol education | Weds 01/12/2021 | Fri 31/12/2021 | WBC | Ed Sarah | complete
Review Key policies and documents | Weds 01/12/2021 | Fri 31/12/2021 | WBC | Ed Sarah | complete
Check if real-time monitoring data is published for air quality? | Weds 01/12/2021 | Fri 31/12/2021 | WBC | Ed Sarah | complete
Review Unauthorised encampments | Weds 01/12/2021 | Fri 31/12/2021 | WBC | Ed Sarah | complete
Review Organise an event and contact the Safety Advisory Group | Weds 01/12/2021 | Fri 31/12/2021 | WBC | Ed Sarah | complete
Compare Health and safety with WBC H&S pages | Weds 01/12/2021 | Fri 31/12/2021 | WBC | Ed Sarah | complete
National assistance burials | Weds 01/12/2021 | Fri 31/12/2021 | WBC | Ed Sarah | complete
To check all process mapped licenses (see activity tracker) are on PPP website | Weds 01/12/2021 | Fri 31/12/2021 | WBC | Kelly | complete
Request for Environmental Information - PPP (publicprotectionpartnership.org.uk) Check if an Environmental Information Enquiry form could be included in the simple enquiry form. To look at if this could be a Corporate page, as not service specific. Similar to FOI request. | Weds 01/12/2021 | Fri 31/12/2021 | WBC | Kelly | complete
Food Export Health Certificates – check if there are any for WBC | Weds 01/12/2021 | Fri 31/12/2021 | WBC | Kelly | complete
Licensing - PPP (publicprotectionpartnership.org.uk) David to find Licensing template from other LAs | Weds 01/12/2021 | Fri 31/12/2021 | WBC | Ed | complete
Need to analyse content of documents and review for correctness (187 PDFs and 43 documents) (refs to WB, WBC, Bracknell) | Mon 1 Nov 2021 | Tues 30/11/2021 | WBC | Ed Sarah | complete
Make PDFs accessible via DS | Tues 01/02/2022 | Fri 18/02/2022 | WBC | KW LK | in progress
Undertake content audit (undertake full link audit - where do the links go and are they relevant for WBC) | Mon 13/12/2021 | Fri 14/01/2022 | WBC | ES | complete
Create draft site design (mapping) | Fri 28/01/2022 | Fri 04/02/2022 | WBC | SZ | complete
Create content inventory template | Tues 08/02/2022 | Tues 08/02/2022 | WBC | SZ | complete
Fill in content inventory template with content from website - cut and paste (approx 80 pages) | Thurs 03/02/2022 | Thurs 10/02/2022 | WBC | SME / grad | in progress
Include meta data into content inventory template | Tues 08/02/2022 | Tues 15/02/2022 | WBC | Content specialist /SME | in progress
SEO plan (investigate) | Mon 21/03/2022 | Thurs 24/03/2022 | WBC | potentially consultant | not started
Build content pages | Tues 01/02/2022 | Tues 22/02/2022 | WBC | SZ team | not started
Populate WBC website with new in-house service information & online case processing functionality and change PPP website to remove / sign-post WBC provided services | Weds 03/02/2022 | Thurs 24/03/2022 | WBC | Ed Sarah | not started
Check content pages | Fri 11/03/2022 | Tues 15/03/2022 | WBC | SME | not started
Make changes to content pages | Mon 14/03/2022 | Thurs 17/03/2022 | WBC | SZ team | not started
Final approval of content pages | Tues 22/02/2022 | Thurs 24/03/2022 | WBC | SME | not started
Set up analytics | Tues 22/02/2022 | Thurs 24/03/2022 | WBC | Martin E | not started
Consider buy back services and how to identify these with branding on West Berks website | Thurs 03/02/2022 | Thurs 24/03/2022 | West Berks / WBC | Sarah Ed | not started
Payments
Test Quickpay via online/telephone | Tues 01/02/2022 | Mon 28/02/2022 | WBC | Jackie Ed and team | in progress
Provide Jackie with list of account groups, with relevant cost centre and analysis details, confirm if vatable | Tues 18/01/2022 | Fri 28/01/2022 | WBC | Ed | complete
Confirm list of staff that require access to BWO to review payment transactions | Tues 18/01/2022 | Tues 28/03/22 | WBC | Ed | in progress
Test setting up annual invoicing on BWO for licensing/permit renewals | Tues 01/02/2022 | Mon 28/02/2022 | WBC | Rupert | in progress
Test running debtor reports on BWO | Tues 01/02/2022 | Mon 28/02/2022 | WBC | Jeff | in progress
Training for selected CDO/admin staff | Tues 01/03/2022 | Thurs 31/03/2022 | WBC | Ed | in progress
Supply list of suppliers and payments amounts/schedule | Tues 18/01/2022 | Fri 28/01/2022 | WBC | Ed | complete
Post go live
What external links need to be sent to WBC pages and not West Berks | Fri 01/04/2022 | Fri 08/04/2022 | WBC - Digital | Web team | not started
Design referral process for TS Licensing requests | Fri 01/04/2022 | Fri 08/04/2022 | WBC | Kelly / Shweta | complete
Check payments process for Licensing (i.e. invoicing, use of case ref) | Thurs 30/09/21 | Thurs 30/09/21 | WBC - Digital | David | complete
Netcall
Purchase additional licences and raise PO | Weds 01/12/2021 | Mon 31/01/2022 | WBC | Kate | complete
Allocate licences on system | Mon 17/01/2022 | Mon 31/01/2022 | Netcall | Netcall | complete
Change IVRs | Mon 28/03/2022 | Fri 31/03/2022 | WBC | Pam | in progress
Netcall overflow arrangements in place to determine call flow for unanswered calls | Mon 28/03/2022 | Fri 31/03/2022 | WBC | Pam | not started
CDO’s to have “Netcall WebAgent“ installed by IT | Mon 28/03/2022 | Fri 31/03/2022 | WBC | IT | not started
Issue with a work mobile | Mon 28/03/2022 | Fri 31/03/2022 | WBC | IT | in progress
Supply headsets | Mon 28/03/2022 | Fri 31/03/2022 | WBC | IT | not started
Provide list of staff so they can be set up as a user – including a supervisor | Mon 28/03/2022 | Fri 31/03/2022 | WBC | Pam | not started
New IT equipment
Identify WBC kit (laptops, phones) used by PPP to be returned and identify software/licences PPP use that we need to cease | Mon 10/01/22 | Fri 18/03/22 | WBC | Jon Glynn Kate | in progress
Staff equipment review | Fri 01/10/21 | Fri 19/11/21 | WBC | Jon Glynn Kate | complete
Order new laptops for staff | Fri 01/10/21 | Fri 14/01/22 | WBC | Jon Glynn | complete
Order new phones for staff | Fri 01/10/21 | Fri 14/01/22 | WBC | Jon Glynn | complete
Build equipment for staff | Mon 10/01/22 | Fri 18/03/22 | WBC | Jon | in progress
Issue equipment to staff | Tues 01/03/2022 | Thurs 31/03/2022 | WBC | IMT | in progress
Training
Proposal from Civica | Weds 15/12/2021 | Fri 07/01/2022 | WBC Civica | Kate | complete
Decline proposal prior to March | Mon 10/01/2022 | Mon 10/01/2022 | WBC | Kate | complete
Head of Service to ensure internal training on APP undertaken as part of staff induction | Tues 01/03/2022 | Thurs 31/03/2022 | WBC | Ed | not started
I@W training | Tues 01/03/2023 | Thurs 31/03/2023 | WBC | Ed | not started
ESRI training | Tues 01/03/2022 | Thurs 31/03/2022 | WBC | Ed | not started