## Sheet1
New Allocation Policy - Implementation Project Plan
ACTION | Responsibility | Target Date | Date Completed
NORTHGATE - Project work with NG Consultant
Review all Allocation questions | KF/JB/HOL | end Dec 21 | 2021-12-07
Review Housing Options and Housing Online and confirm any changes | KF/JB/HOL | 2021-12-01 | 2021-12-07
Confirm new Questions req for new Allocation policy - MARAC; Foster Carers, IH Homeless - Officer led Q rather than Customer Q | KF/JB/HOL | 2021-12-01 | 2021-12-07
Run report of all current Banding and new Banding- confirm proposed changes are correct 22/2/22 | KF/JB/HOL | end Feb /beg March | 2022-02-23
Run report of all apps with Category - ERROR and look at each app individually | KF/JB/HOL | end Dec 21 | 2021-12-07
Add Band 5 (added in HOUDEV) | JB | end Dec 21 | 2021-12-07
Split Q 164 - Deprioritise B5 / B4 override -now a combined Q and will add 'explanation' for banding ie OOA B5 | KF/JB/HOL | 2021-12-01 | 2021-12-07
Run report of all apps with DEPRIORITISE -look at each app individually | KF/JB/HOL | end Dec 21 | 2021-12-18
Run report of COMPOUND NEEDs - no longer in new policy | JB | end Dec 21 | 2022-01-23
Run report of OVERRIDE banding - look at each app individually | KF / JB / DW | end Jan 22 | 2022-02-02
Add Q 523 'Applicant prioritised by MARAC' in HOUDEV | JB | end Jan 22 | 2022-01-28
Add Q 526 'Approved Foster Carer' in HOUDEV | JB | end Jan 22 | 2022-01-28
Add Q 528 Non Priority IH Homeless Households | JB | end Jan 22 | 2022-01-28
Fully test Q 523 'Applicant prioritised by MARAC' against both current and new applications | KF | beg Feb | 2022-02-02
Fully test Q526 Approved Foster Carer' against both current and new applications | KF | beg Feb | 2022-02-02
Fully test Q 528 Non Priority IH Homeless Households against both current and new applications | KF | beg Feb | 2022-02-02
Q140 'Tenure Type' and option 'Iprivate -insecure private rented' to be removed -Y in Houdev and will be in Live when cloned | JB | end Jan 22 | 2022-02-02
Check x14 applicants who have selected option 'Iprivate -insecure private rented' for Q140 and confirm new banding | ER | beg Feb | 02/02/20222
HOUDEV to be cloned (data refreshed to match Houlive) 15/2 | JB | 2022-02-15 | 2022-02-15
HOUDEV to be updated to latest Northgate release 21.1 17/2 | JB | 2022-02-17 | 2022-02-17
Jo to complete a full Allocations test in preparation for ‘Go Live’ 22/2 | JB | 2022-02-22 | 2022-02-23
JB to prepare script for Notepad-update Category Start Dates to previous CSD/ Band changes. One off report. To be tested on 22/2 | JB | 2022-02-22 | 2022-02-23
JB to organise Weekly Band Change Report - log BAU ticket if want to change it to monthly | JB | end Feb | 2022-02-28
JB to prepare script to put Message on Notepad for staff 'new band as part of new alloc process' + old/new banding | JB | end Feb | 2022-02-23
JB to prepare report of all Deferred Applicants (not auto deferred) with reason/current banding/date | JB | 2022-02-18 | 2022-02-24
Update Q439 Band 3 for 'Y' to 'Are you a Keyworker' | JB | end Feb | 2022-02-23
JB to prepare report of all Homelessness Applicants | JB | end Feb | 2022-02-28
JB to update wording of Q 528 '‘Part VII applicants who are owed a duty under S190 of the Housing Act 1996’ | JB | end Feb | 2022-02-28
HOL Application Form Add Q 'Are you expected to inherit within the next 6 months' Y/N Q and B5 if Yes | KF / JB | Mid March | 2022-03-11
HOL Application Form Fully test 'Are you expected to inherit within the next 6 months' | KF | Mid March | 2022-03-16
HOL Application Form JB to put new Q into LIVE - when system goes off line on 31/3/2022 | JB | end March | 2022-03-31
HOL Application Form Add Q 'Have you got any unspent convictons' Y/N | KF / JB | Mid March | 2022-03-14
HOL Application Form Fully test 'Have you got any unspent convictons' Y/N | KF | Mid March | 2022-03-16
HOL Application Form JB to put new Q into LIVE -when system goes off line on 31/3/2022 | JB | end March | 2022-03-31
HOL Application Form Add Q 'Do you have any Rent Arrears in your current property' | KF / JB | Mid March | 2022-03-14
HOL Application Form Fully test 'Do you have any Rent Arrears in your current property' | KF | Mid March | 2022-03-16
HOL Application Form JB to put new Q into LIVE -when system goes off line on 31/3/2022 | JB | end March | 2022-03-31
HOL Change of Circumstances Form -Add Q 'Are you expected to inherit within the next 6 months' Y/N | JB | Mid March | 2022-03-22
HOL Change of Circumstances Form Fully test 'Are you expected to inherit within the next 6 months' Y/N | KF | Mid March | 2022-03-22
HOL Change of Circumstances Form Add Q 'Have you got any unspent convictons' Y/N | JB | Mid March | 2022-03-22
HOL Change of Circumstances Form Fully test 'Have you got any unspent convictons' Y/N | KF | Mid March | 2022-03-22
HOL Change of Circumstances Form -Add Q 'Do you have any Rent Arrears in your current property' | JB | Mid March | 2022-03-22
HOL Change of Circumstances Form -JB to put x3 new Q into LIVE -when system goes off line on 31/3/2022 | JB | end March | 2022-03-31
Prepare script to be auto put on Notepad/ and HOL for applicants where there is no change to banding | JB | 2022-03-28 | 2022-03-22
Test above script in Houdev | KF / HOL | 2022-03-28 | 2022-03-22
HOL
Research other LA's re: eligibility info on website - ensure WBC website is clear | KF | end Feb | 2022-01-26
Send DW research on other LA's website and agree way forward -(may utilise J Jones) | KF / DW | end Feb | 2022-02-03
Draft messages for My Messages - changes / no changes to banding | KF | end Feb | 2022-02-11
Get approval for My Messages message - any changes to banding | DW | end Feb | 2022-02-11
Draft letters for applicants we manage in house- changes / no changes to banding | KF | end Feb | 2022-02-11
Get approval for draft letters to be send to applicants we manage in house | DW | end Feb | 2022-02-11
Use 'My Messages' tile to notify applicants of any changes to banding - JB has prepared script to do this | HOL | beg April as we Go Live | 2022-04-01
Send letters to small cohort of applications we manage in house (59) -to notify of any changes to banding - IT can prepare a script | HOL | beg April as we Go Live | 2022-04-04
FAQ for team use re: main changes in new policy | KF /HOL | end March | 2022-02-11
Go through list of all K/W (275 applicants) and confirm B3 - if OOA its B5 | KF | beg March | 2022-02-24
Update HOL messages to be sent to applicants when need more info | KF / HOL | end March | 2022-03-29
Update B1 and B2 applicants to 'all areas of choice' | All TEAM | w/c 29th March | 2022-03-30
KERRY / DANIELLE
Update Allocation Banding Leaflet -Revisions needed 29/3 - will be done by 30/3 | KF | beg March | 2022-02-02
Send Banding Leaflet to Digital Solutions to make it corporate -revised as per comments from D Carter on 16/2 | KF | beg March | 2022-03-01
Provide Digital Solutions with cost code for work 60705 | KF | beg March | 2022-02-03
Get approval at Communications Group for new Allocation Banding Leaflet | DW | mid March | 2022-03-08
Order 100 hard copies of new banding leaflet via Digitial Solutions -collected 14/3 | KF | mid March | 2022-03-14
Get Web version of Banding leaflet from Digital Solutions | KF | mid March | 2022-03-09
Update Document list - 3/2 confirmed with DW no changes necessary. More officer investigations once app submitted | KF | mid March | 2022-02-03
Draft letter Templates - No Local connection / Cancelled Apps | KF | mtg arranged 17/2 | 2022-02-17
DW to update letter templates with relevant Alloc leg | DW | beg March | 2022-03-07
DW to add Translation strapline to letters - (confirm with Comms top 6-7 language) - part of a wider WBC project | DW | mid March | ONGOING
Get approval at Communications Group re: letter templates- sent to KJ 7th March DW happy to proceed as they contain all relevan leg. | DW | mid March | 2022-03-30
DW to look at template for message HOL use when customer answers 'Y' to 'Unspent Convictions' - use same wording as PRAH | DW /KF | mid March | 2022-03-31
DW to look at providing updates for web site ready for 1st April | DW | mid March | 2022-03-17
Diarise 3 month review for new policy - any work req by NG Consultant (JB) | KF / DW | end March | 2022-07-05
Diarise 6 month review for new policy | KF / DW | end March | 2022-10-04
Request for Reviews - to go through to JT - (Confirm with DW) | DW | mid Feb | 2022-02-11
Need a phased approach - maybe look at updating highest HN applcants first B1-B2 etc-confirm with DW / ZM | KF /DW / ZM | end Feb | 2022-02-11
Go through list of applicants banded due to 'Compound Need' | KF / DW | mtg arranged 3/2 | 2022-02-07
Check Deferred Report-look at apps on individual basis (shouldn't move band until deferral is lifted) - 630 applicants | KF / HOL | mid March | 2022-03-11
Update paper application (and Transfer) with the new Q -Rent Arrears / Inheritance and Unspent Convictions | SM | 2022-03-31 | 2022-03-31
Check NEW / UE report look at apps on individual basis and update from New / UE status - 430 applicants | KF / HOL | end March | 2022-03-15
Log call with IT - set up new mailbox housingreviews@wokingham.gov.uk- SR00130435 logged 28/3 | KF | end March | 2022-03-28
Team to update email signature -include link to new Alloc policy | WHOLE TEAM | by 1st April | 2022-03-31
VICKY
Update Equality Assessment - ie have provision for customers with no IT access | VH | end March | 2022-03-29
Publish Alloc Policy on website - will need to use Digital Solutions to design it | VH | end March | 2022-04-01
Newsletter style overlay to notify applicants of new Alloc policy + links to Alloc policy (like consultation Rebecca Birdworked on) | VH | end Feb / beg March | 2022-03-31
Will need Cost Code for work - 60705 | VH / DW | ASAP | 2022-02-03
Send RPs final version of Allocation Policy | VH | end March | Next mtg 13/4
Share consultation feedback doc - ensure we update all those that fedback | VH | ASAP | 2022-03-31
Update Allocation Policy with further clarifications as per emails w/c 4th Feb | VH | ASAP | 2022-02-04
To redraft Allocation policy with amendments suggested by David Carter 16/2 and republish to all | VH | end Feb | 2022-02-23
Update Policy to reflect Keyworkers are B3 | VH | end Feb | 2022-02-22
To organise Press Release with Rebecca Bird -15/3 RB confirmed pre elc so no members to be involved in any promotion | VH | end March | 2022-03-31
HOMELESSNESS TEAM
Homeless team to contact vulnerable applicants who may need further explanation if moving out of B1 | Sridevi and team | w/c 28th March | 2022-03-30
Homeless team to confirm those applicants who have been prioritised by MARAC and should be B1 | Sridevi and team | w/c 28th March | 2022-03-30
Ask Homelessness team to confirm list of x76 current B1 applicants and proposed new banding - archived as new report run 28/2/22 | Sridevi and team | end Jan | n/a
Send report of Banding Changes to DW and KL re: proposed changes to Accepted Homeless applicants | KF | end Feb | 2022-02-28
To update all B1 and B2 with 'all areas of choice' with any exceptions notes | KL and Team | w/c 28th March | 2022-03-30
WEBSITE MESSAGING - web team
Draft message for website - HOL unavailable due to system changes | KF | mid March | 2022-02-15
Message approved by DW | DW | end March | 2022-02-17
Raise IT request for message to be applied to website-has to done the day the message is to be made active | HOL | end March | 2022-04-01
Message applied to website | IT TEAM | end March | 2022-03-31
Update WBC Website with links to new Alloc policy and make criteria /policy more visible from the outset | IT TEAM | end March | 2022-03-31
Remove old policy (and links from website) | IT TEAM | end March | 2022-03-31
Remove old policy and links from HOL | IT TEAM | end March | 2022-03-31
Raise request on Applications Support Portal re: new banding leaflet on website | KF | mid March | 2022-02-11
Put flasher on HOL for applicants - check My Messages for new Alloca policy and impact on the customer (like T+C Message) BAU /JB? | TBC | end March | n/a
1/2/22 - ZM confirmed we can use Jenny Jones for website work | KF/DW | mid Feb | n/a
LEGAL
Successful sign off of Policy from Legal - Mtg with David Carter 16th Feb/ amendments made / to be returned to D Carter for approval | ZM | ASAP | 2022-03-31
Final meeting with David Carter | VH / ZM | w/c 16 / 21 March | 2022-03-29
TRAINING
Organise in house training to update teams on new policy -Localities; Customer Service; Here 4U; Childrens, Transform; CAB | DW / KF | mid March | Rents 16/3
CT /KJ 31/3/22
RISKS | Mitigation
NG 21.1 upgrade will have impact on Alloc Policy work - w/c 17th -24th Jan - testing required in HOUTEST | All Testing completed 21/1/22
Annual Leave - Emp1 w/c 31st Jan and will impact on Testing / Emp2 end Feb | Emp2 cancelled A/L
Annual Re Registration project - 1st March T+C - labour intensive to manually update all Renewal Dates to 1/3/23 | prioritise work
Emp3 (D Solutions) on A/L from 14-28th Feb | 25/2 Resent updated Banding leaflet
Legal Conference with David Carter 16/2 - need to add new Q to HOL application (inheritance / unspent convictions)-will need TESTING | JB starting work on Application w/c 28/2
VH needs to redraft policy again - aim to do by w/e 25th Feb | Re circulated 24/2
22/2 - No testing as Jo has to make changes to the scripts - lost an afternoon of testing | All Testing completed 24/02/2022
23/2-HOL team to test NG upgrade to 21.1 so time lost on testing IT for new alloc policy changes | All Testing completed 24/02/2022
NOTES
c 594 apps in Band 4 / Band 5 -new Alloc policy affects B4 applicants more as it is now split into 2 bands
c 143 applicants in B 1-3 will move around
Cost Code is
Jo Bailey contract to end May / June so ensure regular weekly meetings post Go Live to resolve any issues
NG and HOL to be taken off line 5pm 31st March and 1st April