## Slide 1
Project Initiation Document
DATE
Name: Jo Veitch
Programme: Data & insight – phase 1
Ref Number: IT-PD- 003

## Slide 2
Version | Date | Description of change | Author | Project Sponsor
V1 |  |  |  | 
Name | Role | Date
Will Roper | Data and insight - Manager | 
Role | Name | Directorate | Date of PID Approval
Steering group | Mark Gwynne |  | 13.1.22
Steering Group | Glynn Davies |  | 13.1.22
Steering Group | Paul Ohsen Ellis |  | 13.1.22
Version Control
Contributors/Reviewers
Authorisation/Approval
Project Initiation Document| Sign Off

## Slide 3
Project Initiation Document| Contents
Overview
Objectives
Scope
Milestones
Governance
Sizing & QA
Benefit Realisation
Acceptance Criteria
Budget
Risks
Project Stakeholders
Climate Change Assessment
Assumptions
Comms
EIA
PIA

## Slide 4
Project Initiation Document| Overview
Recent efforts have improved performance reporting, but we know we can enhance this significantly further. The current performance dashboard faces delays in getting performance management information into the hands of decision makers
Reporting is static, often manually aggregated data which gives us some insight, but is often out of date, due to delays in getting the data, reliance on individuals having capacity to do analysis and present the data back to those who need it, when they need it. Reports are produced in numerous formats, making it difficult to interpret accuracy, the integrity and quality of information needs to be improved and how it is presented should be consistent.
This project is the first phase in a potential wider programme. We will take the learning from this project and feed it into the development of a business case for the wider programme.
Phase one will establish the feasibility and foundations for the wider programme to be considered.

## Slide 5
Project Initiation Document| Objectives
To become an insight driven data backed organisation, that embeds data and research across our services to fully understand resident needs and our performance, and how we can improve – to be the best we can be…to change the way we work
Improving our Corporate performance reporting, by building a visual, intuitive, interactive dashboard, that over the longer duration will enable senior leaders to drill down into the detail to see route cause issues.
Establish the foundation of our data bank with the aim of providing a single scalable source of truth for reporting over the duration of the wider programme.
To determine the full costs and timescales for delivery of the wider project which will create a scalable self-service platform which automates or standardises data.
Ensure our data and insight is secure, relevant, authorised, compliant and appropriately accessible.
Roll out the foundations (technology, PowerBI & skills) to enable us to accelerate our data insight journey
Service specific reporting dashboards for corporate KPI’s and drill down ability to each Directorate and set the foundations and skills training to enable us to maintain and continue on our insight journey and development of our insight.

## Slide 6
Project Initiation Document| Scope
In Scope
Build a corporate KPI dashboard with Simpsons available for Q1/Q2 2022
Corporate dashboard finalisation and automation (where possible) Q2
Simpsons -Powerbi specialist to train our nominated data leads (6) and create templates for now and future build of dashboards.
Recruitment, training and upskilling needs planned and understood
Insight strategy -draft foundation , key principles and activities to manage the security and governance of use DIGG.
Data bank foundation set up and management - training and guidance and data feed knowledge
Simpsons to support the delivery of a Technological roadmap to support the programme which includes financial governance ​
Review of current KPI set​ -ensure they are relevant and understand which link to our corporate plan , understand how and where they derive from, and what is missing.
As is review of reporting and data what we have, compliance, why we have it and ID our data gaps – where we want to be
Integrate with applicable tier A applications, e.g., Mosaic​ -Note integration will be incremental development throughout the Programme.
Directorate dashboard design and pilot
Out of Scope phase 1
Dash boards for teams/public/managers dash boards phased approach(phase 2)
Insight for future - strategy phase 2.
Data feeds incremental development (key systems based on business agreement/business cases) part of IT road map.
User cases for each directorate phase 2.
Data cleansing on going through all phases - business ownership.
GIS (Esri() phase 2 (geographical maps)
Phase 3 /4-competitor/public outcome

## Slide 7
Project Initiation Document| Milestones
January/February
March /April
Build commence
Knowledge share starts/ powerbi APP rollout
Dashboard template
Data as is findings survey
November/December
As is data survey completed
Simpson training and build
July/August/Sept
Dual run pack and dashboard
Corporate dashboard presented scrutiny and overview
Phase 2 business case finalisation
Phase 1 closure
Simpsons on boarding/ pre work/planning
Governance established
Draft PID/plan
KPI data mapped
Data as is mapping starts
Insight strategy prework
Superusers engagement
May /Jul
Corporate dash board finalised and data pool automation where possible complete phase 1 (it road map)
IT road map phase 2 planning and costs
Draft business case commences
Notes: Project will be agile and work activities planned within standups

## Slide 8
Project Initiation Document| Governance
Fortnightly
Steering Group Meeting
Directorate / workstream updates Interdependencies, Key Risks & Issues
Budget, Change Control
Project Manager
GD
POE
MG
WR
Weekly
Project Group Meeting
Progress reporting
Risk register/depdencies
Project plan
Opportunities/Challenges
Project Manager
Workstream Leads
Monthly / 6 weeks
Steering Group Meeting
Programme Highlights
Risk escalation / Change control
Budget
DIGG
Project Manager
Project Board
DIGG - phase 1
Notes: Sally requested DIGG as project board due to phase 1 focus not SRO/Sponsor level for phase 1.

## Slide 9
Project Initiation Document| Project Sizing and Quality Assurance
Scoring | Duration | People | Dependencies | Risk & Complexity | Operation & Process Impact | Customer & Service Impact | Environmental / Climate Change Impact | Costs / Savings
Each box on this row = 1 | < 6 months | Up to 4 project team members | No major dependencies or inter-related projects | Solution achievable, understood | Impacts a single area, No training, minimal staff impact | Minor impact on customers, no political interest | Low, scoring above 0 in the climate impact assessment tool | <£100k
Each box on this row = 2 | > 6 < 12 mths | 4 - 8 project team members | >3 dependencies on projects / multiple workstreams but low risk | Technical solution unclear, difficult to understand | Impacts a number of business areas, SME support required, some training, low staff impact | Some political interest, Impact on >1 stakeholder base | Medium, scoring from 0 to -10 in the climate impact assessment tool | >£100k <£500k
Each box on this row = 3 | > 12 months | Over 8 project team members | High risk dependencies with multiple workstreams / inter-related projects | Difficult to achieve, hard to define problem | Impacts on the whole organisation, Expert resource required, training required, large staff impact | Major political interest, Large impact on >3 stakeholder bases | High, scoring below -10 in the climate impact assessment tool | >£500k
Sizing will support the efficient use of resources and meet the changing needs of the project in order to allow a suitable level of QA
  Under 12 = Small / JDI
  12 – 17 = Medium
  Over 17 = Large
Notes: Phase 1 only sizing

## Slide 10
Project Initiation Document| Benefit Realisation – through insight
Customer focus - what we do and how we do it is driven by insight, creates efficiency's, savings, enriches lives, enables us to plan, commission and monitor our services to deliver value for money and be transparent. Phase 1 will set foundations in place to support this vision and provide the as is base line
Being ambitious – Insight enables forward-thinking, innovative, entrepreneurial services and teams.
One team – Insight provides one version of the truth, supports us being accountable for our service delivery in the context of our community wellbeing and Council objectives.
Corporate Priorities:
Insight will inform and inspire us to achieve and improve against our priorities n
up
Equality Impact: Improvements to data and insight will result in a better monitoring and information regarding equalities impacts both within the organisation and borough resulting in targeted action to drive improvements.
Social Value: A better understanding of residents through data will resulting in tailored services to meet their needs and better outcomes for communities including environmental, social and economic benefits.
Sustainability: Utilising data sets and insights to make changes to drive sustainability across service areas
Climate Crisis: Utilising our data and insights to make data led decisions around our climate change action plan and monitoring how we measure its success.
Reduction in time and effort to produce and organise data, to simplify record keeping and enable a holistic view of our borough, people and activities, as we roll out the project over the coming phases. To enable our data teams to be proactive, providing predictive insight to inform our actions and decisions.
Notes: What financial benefits are we measuring/ influence in the programme – what are the goals for each directorate within the forward plan ? Business cases for phase 2 ?

## Slide 11
Project Initiation Document| Acceptance Criteria
Corporate Dashboard with Automation (of pre agreed level) KPI results are the same as is method
KPI for corporate dashboard are valid and add value to corporate plan or mandatory reporting
Data Bank - approach, foundation, security is in place and KPI data source feeds are automated into bank.
Powerbi superusers are trained to agreed level in contract, including but not limited to data team, and those involved in the corporate dashboard.
Technical / phase 2 plan is drafted, and business case can be produced
Data and Insight strategy outline approved by DIGG/SW.
Cultural shift is visible, superusers engagement and production of data shows positive movement and recommendations to demonstrate this shifting.
Notes: What is acceptance criteria

## Slide 12
Project Initiation Document| Costs & Budgets
Component | Cost item | Costs
Licenses) on going cost | Enterprise mobility & security Azure | £
Sub total |  | £-504
Data – on going cost | Azure data refesh estimate 10 gb (estimated) Example | £
Sub total |  | £-1600
External expert phase one cost | Simpsons - Phase 1 project directorate and corporate dash boards | £ £
Sub total |  | £-122000
Resource | Resource to deliver and support corporate dash boards Resource for future stages | £-
Phase one total costs |  | £- 124104
Notes: Simpson is a 4 stage payment plan -
25% on completion of Requirements Gathering & Design stage (10% if break clause exercised)
o 40% on completion of Environment Setup and Data Export & Modelling stage
o 25% on completion of Reporting stage
o 10% on completion of Release Activities stage and sign-off

## Slide 13
Project Initiation Document| Project Stakeholders
Apprenticeships
Name | Area of work | Role | Responsibility
Graham Ebers | Director corporate services | Sponsor | Accountable for delivery
Steve Moore | Director place and growth | sponsor | Accountable for delivery
Sally Watkins | Assistant director Digital and Design | SRO | Responsible for delivery
Mark Gwynne | Interim head of insight, strategy and inclusion | SRO | Responsible for delivery
Paul Ohsan-Ellis | Strategic Development and Commercialisation Governance Services Resources and Assets | SME | Responsible for data and information integrity
Will Roper | Customer insight and performance manager | SME | Data and insight Programme lead
Glynn Davis | Head of IT | SME | Responsible for delivery of Systems and cyber security.
Julie Teague | Data and development manager | SME | Responsible for data development/source
James Bull | Infrastructure Architect | SME | Responsible for infrastructure architect
Louise Griffin | Performance Analysist | SME | Responsible for corporate performance KPI (insight)
Paula Hatch | Infrastructure team lead | SME | Responsible for infrastructure team
Lisa Ma | Internal communications and engagement | SME | Responsible for internal Communications
Simpsons | External expert partner for data platform and Powerbi rollout | Project | Responsible for the support to design and deliver - Wokingham’s Corporate Dashboard, Directorate dash boards and supporting Data Platform.
Notes: Andrew /

## Slide 14
Project Initiation Document| Climate Change Assessment
WBC declared a climate emergency in 2019 committing to net zero by 2030.
There is a recommendation for the Council to consider the impact of climate change on all its actions and decisions. This must include a transparent, calculated carbon impact assessment of each proposal/project. New government commitments and upcoming policies in this area which will need to be followed. There is a need to embed climate change within council operations and decisions from the early stages.
The tool:
Outlines the expected impacts across a number of areas.
Assesses potential mitigation options, helping demonstrate both internally and externally that we are taking such into consideration throughout.
It is not designed to replace or duplicate environmental impact assessments.
This project will support our climate emergency plan – by providing insight to inform its progress and actions. It does not directly impact the climate or effect our climate goals due to the nature of the project scope. It will put in place foundations for data to provide insight into our efforts.
Notes: No impact as far as project is aware.

## Slide 15
Project Initiation Document| Assumptions
Apprenticeships
Simpsons will be our expert and will start be on board by 13/12
Key staff are available to support and achieve project deliverables within agreed timescales and we fund staffing needs or back fill
BA/project support will be available as and when required
Service BAU does not impact on project delivery
Delivery will be prioritised across directorates
Internal communications resource will be available
Any necessary budget for the project is made available
Timeline will go beyond Q1.
EIA and PIA will be considered through out the project - each report / system we look at data for and who can look and see it- we will present and agree back with DIGG project group, as data owners and the project team will be monitored by POE / WR throughout to achieve this.

## Slide 16
Project Initiation Document| Comms
Apprenticeships
Communication Objective: to embed the foundation of a cultural change to use of insight to inform our decisions – how powerbi can aid and speed up analysis enabling our experts to spend less time extracting data and more time looking at the insight it provides to help shape how we work and what we do.
Key Communication Points
Overview and objectives of the programme how we will be using the business experts and what we are aiming to achieve (see comms plan)
Communication Plan: will be drafted

## Slide 17
Project Initiation Document| EIA
Apprenticeships
Protected characteristics​​ | Impact score​​ | Please detail what impact will be felt by the protected group:​​ | Reason for Impact Score​​
Race:​​ | N |  | ​Project / activities does not specifically request/retain this information so no impact​
Gender:​​ | N |  | Project / activities does not specifically request/retain this information so no impact​
Disabilities:​​ | N |  | Project / activities does not specifically request/retain this information so no impact​
Age:​​ | N |  | Project / activities does not specifically request/retain this information so no impact​
Sexualorientation:​​ | N |  | Project / activities does not specifically request/retain this information so no impact​
Religion/belief:​​ | N |  | Project / activities does not specifically request/retain this information so no impact​
Gender re-assignment:​​ | N |  | Project / activities does not specifically request/retain this information so no impact​
Pregnancy and Maternity:​​ | N |  | Project / activities does not specifically request/retain this information so no impact​
Marriage and civil partnership:​ | N |  | Project / activities does not specifically request/retain this information so no impact​
Notes: Project needs to consider this for every report/ data feed – DIGG/ IAO /Project to agree based on data injestion.

## Slide 18
Project Initiation Document| PIA
Apprenticeships
 | Y/N
Will the project involve the collection of new information about individuals? | N
Does the project/process include the processing of "special categories of personal data"? | Y
Will the project compel individuals to provide information about themselves? | N
Will information about individuals be disclosed to organisations or people who have not previously had routine access to the information? | Y
Are you using information about individuals for a purpose it is not currently used for, or in a way it is not currently used? | Y
Does the project involve you using new technology which might be perceived as being privacy intrusive? For example, the use of biometrics or facial recognition? | N
Will the project result in you making decisions or taking action against individuals in ways which can have a significant impact on them? | N
Is the information about individuals of a kind particularly likely to raise privacy concerns or expectations? For example, health records, criminal records or other information that people would consider to be particularly private. | Y
Will the project require you to contact individuals in ways which they may find intrusive? | N
Has this project/process already been started as a pilot without a screening or PIA being undertaken? | N
Notes: We will need to define a set of principals on PIA for each data set – and we need to look permissions around it – with security levels to be agreed – what are the powerbi data levels of control and how we apply that. This is in the project plan. We will agree and review with DIGG group through our journey/Data leads.

## Slide 19
Project Initiation Document| PIA
Apprenticeships
All projects must consider their Privacy Impact Assessment (PIA) A Privacy Impact Assessment (PIA) is a process which helps assess privacy risks to individuals in the collection, use, and disclosure of personal information. A failure to properly embed appropriate privacy protection measures may result in a breach of legislation.​
​
The purpose of a PIA assessment is to identify the risks that may arise through the project and propose methods to mitigate against the risks.​
Some examples when to complete a PIA; you introduce a new or make changes to a system to collect and hold personal data, collecting personal data for a new purpose, transferring personal data between organisations, significant change in process operation involving personal data. ​
​
This template is a practical tool to help identify and address the data protection and privacy concerns at the design and development stage of a project, building data protection compliance in from the outset rather than bolting it on as an afterthought.​
​
Next Steps​
There are 10 screening questions in there to see if a PIA is required. ​
The Data Protection Officer can provide advice and guidance, review the completed PIA template, and advise on the need for completing a PIA if the screening questions are borderline or minor.​ You can contact the information governance team via this email address :
PIA documents can be requested by the Information Commissioners Office (ICO) to be provided to them at any time. ​
Data and its use will be aligned to each dept and team as currently operated and only be used to report to those who would already see and use that information.
​
Notes: Yes separate assessment within plan and full PIA form – under constant review with project team and POE