## Go Live Items (hidden)
Item | Day 1 Essential (Yes / No) (if "No" use notes in column G) | Ready for Live testing (if applicable) | Live testing complete | Who signed this off ? | Signed off date | Notes / Comments

## Implementation Schedule
Project | Area | Description | Lead contact | Other People | Start Date | Finish Date | Status | Comments
Data Migration
| Digital / IT | Full data / documents extract taken and sent to WBC 7 Feb - if tested successfully only a small delta will need transferring w/c 28 March | Ed Kim | Julie Kate | Mon 07/02/22 | Fri 18/03/22 | complete
| Digital / IT | Test the migrated data and documents and sign off a stage gate | Ed and team |  | Thurs 30/09/21 | Fri 25/03/22 | complete
| Digital / IT | Arrangement for transfer over of documents that sit within emails and personal files of PPP staff and on any hard drives | Kate | James Colin Jaz | Fri 28/01/22 | Fri 29/04/22 | complete
| Digital / IT | Type of storage agreed for service documents and letters (shared drive) | Kate Ed |  | Thurs 13/01/22 | Fri 04/03/22 | complete
| Digital / IT | Mailboxes setup for Licensing, Environmental Health and ASB and access given to staff as part of laptop build | Jon | Ed Kate | Thurs 27/01/22 | Fri 1/04/22 | complete
| Digital / IT | Out of hours technical support expectations communicated and agreed with service | David | Glynn Ed | Thurs 27/01/22 | Mon 28/03/22 | complete
| Digital / IT | APPs team support agreed with service | Julie | Ed Ginny | Tues 15/03/22 | Mon 28/03/22 | complete
Test Runs
| Digital / IT | Test Run 2 - Civica UAT support/bug fixing & QA | Civica | supplier name | Tue 14/12/21 | Fri 18/03/22 | complete
| Digital / IT | Test Run 2 - West Berks - User Acceptance Testing | West Berks | Matthew Phil | Tue 14/12/21 | Fri 18/03/22 | complete
| Digital / IT | Test run 2 Data UAT Testing - West Berks to agree that all relevant data has been deleted/retained | West Berks | Matthew Phil | Tue 14/12/21 | Fri 25/03/22 | complete
| Digital / IT | Confirmation from West Berks that all documents have been migrated that are in their system or not but that there are 5061 missing ones that cannot be found manually as too resource intensive | West Berks | George | Thurs 03/03/22 | Fri 25/03/22 | complete
| Digital / IT | Civica APP build & live run
| Digital / IT | Build the new sculptor and SQL database in live at WBC; download sculptor data and sync to SQL | Civica | supplier name | Mon 28/03/22 | Mon 28/03/22 | complete
| Digital / IT | Confirmation from WBC of location of SQL mirror | James Julie |  | Fri 25/03/22 | Fri 25/03/22 | complete | We have this although James asked why needed, as already known!
| Digital / IT | Shut down APP (including stopping DataMotion for CAB downloads) | West Berks | Phil | Mon 28/03/22 | Mon 28/03/22 | complete
| Digital / IT | West Berks team to not enter any data at all including M drive | West Berks | Phil | Mon 28/03/22 | Mon 28/03/22 | complete
| Digital / IT | West Berks back up of system | West Berks | Phil | Mon 28/03/22 | Mon 28/03/22 | complete
| Digital / IT | West Berks zip up database files | West Berks | Phil | Mon 28/03/22 | Mon 28/03/22 | complete
| Digital / IT | West Berkshire to upload APP system to Civica SFTP site by 3pm | West Berks | Phil | Mon 28/03/22 | Mon 28/03/22 | complete
| Digital / IT | Check files | Civica | supplier name | Mon 28/03/22 | Mon 28/03/22 | complete
| Digital / IT | Advise West Berks system can be used again (as close to 0900 as poss) | Civica | supplier name | Tues 29/03/22 | Tues 29/03/22 | complete
| Digital / IT | Civica undertake deletion of West Berks data | Civica | supplier name | Tues 29/03/22 | Tues 29/03/22 | complete
| Digital / IT | Civica to repoint document paths within APP (this does not require the documents to exist at this stage as the paths are already known | Civica | supplier name | Tues 29/03/22 | Tues 29/03/22 | Complete
| Digital / IT | Civica produce list of delta documents to send to West Berks via WBC | Civica | supplier name | Tues 29/03/22 | Tues 29/03/22 | complete
| Digital / IT | Wokingham send list of delta documents to West Berks | WBC | Julie | Tues 29/03/22 | Tues 29/03/22 | complete
| Digital / IT | Flare account - Civica to enable us to reset | Civica | supplier name | Tues 29/03/22 | Tues 29/03/22 | Complete
| Digital / IT | West Berks run the delta document extract | West Berks | Matthew Phil | Weds 30/03/22 | Weds 30/03/22 | Complete
| Digital / IT | WBC provide connection details to West Berks | WBC | Julie Colin | Weds 30/03/22 | Weds 30/03/22 | Complete | Same location as before - no need to resend.
| Digital / IT | West Berks SFTP (from their office) the delta documents to WBC | West Berks | Matthew Phil | Weds 30/03/22 | Weds 30/03/22 | Complete
| Digital / IT | WBC move delta documents | WBC | Julie Colin | Thurs 31/03/22 | Thurs 31/03/22 | complete
| Digital / IT | Test delta documents and reconciliation | WBC | JT LD ES GF | Thurs 31/03/22 | Thurs 31/03/22 | complete
| Digital / IT | Set up any new accounts on Civica APP | WBC | Leigh Ginny | Weds 30/03/22 | Weds 30/03/22 | Complete
| Digital / IT | Live Run - Civica UAT support/bug fixing & QA | All |  | Weds 30/03/22 | Thurs 31/03/22 | complete | Ed doing and speaking with others
| Digital / IT | West Berks to agree that all relevant data has been deleted/retained | West Berks | Matthew Phil | Weds 30/03/22 | Fri 29/04/22 | complete
| Digital / IT | Final go live configuration - join databases in EH Live | Civica Consultant | supplier name | Mon 15/08/22 | Thurs 18/08/22 | not started | complete
| Digital / IT | Sign off testing of delta documents and data | All | Ed Gina | Weds 30/03/22 | Thurs 31/03/22 | complete | 4.30pm meeting 31/03
| Digital / IT | Go / no go | Project team | Ed, Glynn, Simon | Thurs 31/03/22 | Thurs 31/03/22 | complete | 4.30pm meeting 31/03
| Digital / IT | Copy out test documents uploaded and delete them | Civica | supplier name |  | closed | not started | closed
| Digital / IT | HR documents - transfer SFTP documents from West Berks ‘HR’ to Wokingham – to be agreed | Andree | Kate Kelly | Thurs 31/03/22 | Tues 19/04/22 | complete | Andree managing this - IT have provided advice but different option being followed
| Digital / IT | SFTP documents on West Berks ‘drive’ to Wokingham | West Berks | Phil | Thurs 31/03/23 | Fri 01/04/22 | complete | Also with Phil - will notify WBC later
| Digital / IT | QMS folders - move missing files | West Berks Wham | Karen Julie | Thurs 24/3/22 | Fri 01/04/22 | complete | With Phil - will notify WBC later
| Digital / IT | Westcott Annexe / Infrastructure |  |  |  |  | complete
| Digital / IT | Refurbishment - dependancy for IT and internet - building ready for IT set up | Chris | Glynn Kate | Tue 01/02/22 | Fri 18/03/22 | complete
| Digital / IT | Working line at Westcot Annex to be installed | Chris | Muhammad | Tue 01/02/22 | Fri 18/03/22 | complete
| Digital / IT | Set up an internet connection and build corporate connection over the top; set up printer | Chris | Muhammad | Weds 01/12/2021 | Fri 18/03/22 | complete
| Digital / IT | Purchase and set up firewalls | Chris | Muhammad | Mon 03/01/2022 | Tues 25/02/2022 | complete
| Digital / IT | Test connection | Chris | Muhammad | Tues 25/02/2022 | Fri 18/03/22 | complete
| Digital / IT | Prep the rack for the new line, move all the patching, sort out the Virgin fibre | Chris | Muhammad | Tues 25/02/2022 | Fri 18/03/22 | complete
| Digital / IT | Set up monitors SE (Jon to talk to BS) and WA (Fri 25 March) | Jon Chris Steve Property/BC | James | Mon 07/03/22 | Fri 25/03/22 | complete
| Digital / IT | Test connection with user from service | Ed | Ed's team | Mon 21/03/2022 | Fri 25/03/22 | complete
| Digital / IT | Set up GFast as roll back provision | Chris | Muhammad | Mon 28/03/22 | Thurs 14/04/22 | complete
| Digital / IT | Remove TS02 icons | James team | Jaz | Tues 15/03/22 | tbc | complete
| Digital / IT | Remove users (not system testers) from TS02 and add to TS03 | APPs team |  | Weds 30/03/22 | Weds 30/03/22 | complete
| Digital / IT | Change icon to E&S not PPP | James team |  | Tues 15/03/22 | Fri 18/03/22 | complete
| Digital / IT | Terminal server built - EH live and Test to dop down | James team |  | Tue 08/03/22 | Wed 09/03/22 | complete
| Digital / IT | Resize server for number of users in service | James team |  | Mon 28/03/22 | Fri 31/03/22 | complete
| Digital / IT | Restart service every morning at 0200 ongoing | James team |  | Thurs 24/03/22 | Fri 31/03/23 | complete
| Digital / IT | Enforcement and Safety group in Active Directory to be added; map the J drive to E&S | Paula | Jaz | Thurs 24/02/22 | Thurs 31/03/22 | complete
| Digital / IT | Provide instrcutions for 'tethering' from phones 4g or mobile hotspot | Jon | Simon | Thurs 24/02/23 | Thurs 31/03/22 | complete
| Digital / IT | End to End - Testing Portals & Mobile
| Digital / IT | Issues triaged, added to UAT log & reported at agreed frequency | System Testers |  | Fri 18/02/22 | complete | in progress | complete
| Digital / IT | Defect fixing & QA | Civica QA Team | supplier name | Fri 04/03/22 | complete | in progress | complete
| Digital / IT | Re-testing fixes | System Testers |  | Mon 07/03/22 | complete | in progress | complete
| Digital / IT | Defect fixing & QA | Civica QA Team | supplier name | Fri 11/03/22 | complete | in progress | complete
| Digital / IT | Change Board for live | Simon Civica CAB | Kate | Mon 07/03/22 | Tue 22/03/22 | complete
| Digital / IT | Live servers ready | James team |  | Mon 14/03/22 | Fri 18/03/22 | complete
| Digital / IT | Downtime agreed - if required | CAB |  | Mon 14/03/22 | Tue 22/03/22 | complete
| Digital / IT | ConnectAll configured & enabled in LIVE (APPEHL) | Civica Consultant,Civica Technical Team | supplier name | Mon 21/01/22 | Weds 09/03/22 | complete
| Digital / IT | AOM configured & enabled in LIVE | Civica Technical Team | supplier name | Mon 21/01/22 | Weds 09/03/22 | complete
| Digital / IT | Online forms configured & enabled in LIVE (APPEHL) | Civica Technical Team | supplier name | Mon 21/01/22 | Weds 09/03/22 | complete
| Digital / IT | AOM Licenses available | Civica Technical Team | supplier name | Tue 08/03/22 | Wed 09/03/22 | complete
| Digital / IT | LIVE AOM install completed | Civica Technical Team | supplier name | Mon 24/01/22 | Wed 09/03/22 | complete
| Digital / IT | LIVE ConnectAll install completed | Civica Technical Team | supplier name | Tue 08/03/22 | Wed 09/03/22 | complete
| Digital / IT | LIVE Mobile Solution (OCS) install completed | Civica Technical Team | supplier name | Tue 08/03/22 | Wed 09/03/22 | complete
| Digital / IT | Documentation produced (SDF) | Civica Consultant | supplier name | Tue 08/03/22 | Wed 09/03/22 | complete
| Digital / IT | Go live | Project team | Ed Glynn Simon | tbc | 2022-08-18 | in progress | 2022-11-01
| Digital / IT | Sign off functional testing | Project team | Ed Glynn Simon | tbc | complete | in progress | complete
Website
| Digital / IT | SEO plan (investigate) | SZ team |  | Mon 21/03/2022 | Thurs 24/03/2022 | complete
| Digital / IT | Build content pages | SZ team |  | Tues 01/02/2022 | Fri 18/03/2022 | complete
| Digital / IT | PDFs added (provided by DS) | SZ team |  | Mon 15/03/22 | Fri 18/03/2022 | complete
| Digital / IT | Populate WBC website with new in-house service information & online case processing functionality and change PPP website to remove / sign-post WBC provided services | Ed Sarah |  | Weds 03/02/2022 | Thurs 24/03/2022 | complete
| Digital / IT | Check content pages | Ed Shaylor |  | Fri 11/03/2022 | Tues 29/03/2022 | complete
| Digital / IT | Make changes to content pages | SZ team |  | Weds 23/03/2022 | Thurs 24/03/2022 | complete
| Digital / IT | Final approval of content pages | Ed |  | Tues 22/02/2022 | Tues 29/03/2022 | complete
| Digital / IT | Set up analytics | Martin |  | Tues 22/02/2022 | Thurs 24/03/2022 | complete
| Digital / IT | Web pay - APPs team | Ginny Kelly Kate |  | Thurs 10/03/2022 | Thurs 17/03/2022 | complete
| Digital / IT | Make web pages / content live | Web team |  | Weds 30/03/22 | Weds 30/03/22 | complete
| Digital / IT | Add buttons to web content | Web team |  | Thurs 18/08/22 | Thurs 18/08/22 | in progress | 2022-11-01
|  | Netcall |  |  |  |  | complete
| Digital / IT | Change IVRs | Pam Vicky |  | Mon 07/03/2022 | Tues 29/03/2022 | complete | Being done at 5pm
| Digital / IT | Netcall overflow arrangements in place to determine call flow for unanswered calls | Pam Vicky |  | Mon 07/03/2022 | Fri 31/03/2022 | complete
| Digital / IT | CDO’s to have “Netcall WebAgent“ installed by IT | Jon & team |  | Mon 07/03/2022 | Fri 31/03/2022 | complete
| Digital / IT | Issue a work mobile | Jon & team |  | Mon 07/03/2022 | Fri 31/03/2022 | complete | Planned for Friday
| Digital / IT | Supply headsets | Jon & team |  | Mon 07/03/2022 | Fri 31/03/2022 | complete
| Digital / IT | Provide list of staff so they can be set up as a user – including a supervisor | Ed |  | Mon 07/03/2022 | Mon 07/03/2022 | complete
| Digital / IT | Order Dynamics licences for CDOs & ASBs | Brian | Kate Ed Kelly Jon | Mon 07/03/2022 | Tues 19/04/22 | complete
| Digital / IT | Redacting licence for Adobe required for some users | Kelly | Kate | Mon 15/03/22 | Fri 25/03/2022 | complete
| Digital / IT | Advise Ruth of numbers for adobe for budget costs | Kate |  | Mon 15/03/22 | Fri 25/03/2022 | complete
|  | Equipment |  |  |  |  | complete
| Digital / IT | Build equipment for staff | Jon & team |  | Mon 10/01/22 | Thurs 31/03/2022 | complete
| Digital / IT | Issue equipment to staff | Jon & team |  | Tues 01/03/2022 | Thurs 31/03/2022 | complete
| Digital / IT | New starters - 14 March slots from 1030 for 5 people; 21 March slots from 1030 for 8 people | Jon & team |  | Mon 14/03/2022 | Mon 14/03/2022 | complete
| Digital / IT | SDD / documentation | Infrastructure APPs | James Colin Jaz Ginny Leigh | Thurs 10/03/2022 | Fri 29/04/22 | complete | handed to APPs team for review
| Digital / IT | Users names of allonmobile (ASB) to be supplied to Ed | Ed |  | Thurs 10/03/2022 | Thurs 10/03/2022 | complete
| Digital / IT | Add users to APP | Leigh Kim | Ginny | Thurs 10/03/2022 | Thurs 31/03/2022 | complete | Ginny making sure comms are also complete and shared
| Digital / IT | Remove former West Berks team from Active Directory | Paula | Kate | Thurs 31/03/2022 | Fri 31/05/22 | complete - BAU
| Digital / IT | Update APP portal for reporting issues to reflect new environments | Civica | supplier name |  | closed | in progress | closed
| Digital / IT | Resize server | James | Jaz | Mon 21/03/22 | Fri 25/03/2022 | complete
|  | Training |  |  |  |  | complete
| Digital / IT | Declaration of interest forms signed by all users of I@W | Ed | Kelly | Tues 01/03/2022 | Thurs 31/03/2022 | complete | reminder sent
| Digital / IT | I@W access / training | Ed | Kate | Tues 01/03/2022 | Thurs 31/03/2022 | complete
| Digital / IT | ESRI access / training | Ed | Kate | Tues 01/03/2022 | Thurs 31/03/2022 | complete
| Digital / IT | HIMS - set up licences | Kate |  | Weds 16/03/2022 | Thurs 31/03/2022 | complete
| Digital / IT | Templates /codes | Kim | Ed | Thurs 31/03/2022 | Mon 12/04/22 | complete / BAU
| Digital / IT | Reporting from Civica | Ed |  | Thurs 31/03/2022 | tbc | Phase 2 plan
| Systems & Data Ready | Sign off that all critical data is in place (including any historical data held on spreadsheets, shared drives and email) and is considered fit for purpose (cleansed, audited, reconciled and migrated as appropriate). Data governance arrangements are in place and signed off | Glynn |  |  | 2022-03-31 | in progress | Final data transfer to be completed
| Systems & Data Ready | UAT and BRT results reported and signed off by the service | Kate |  |  | 2022-03-30 | complete | Final live run UAT
| Systems & Data Ready | Email addresses agreed, set up and access given to CDOs responsible for monitoring mailboxes | Kate |  |  | 2022-03-31 | complete | Mailboxes set up - check staff have been given access
| Systems & Data Ready | Infrastructure complete with firewalls in place and internet connection at facility with corporate connectivity | Chris |  |  | 2022-03-04 | complete | Purchase and set up due 25 Feb and testing due 4 Mar
| Systems & Data Ready | All access and permissions have been granted and delivered into live systems for Civica, Mobile APP and Netcall | Glynn |  |  | 2022-03-14 | complete | See workplan
| Systems & Data Ready | All required system licences issued (Civica APP, Mobile solution, Netcall) | Glynn |  |  | 2022-03-14 | in progress | Users and required licences identified and shared with IMT Dynamics issued 01/04
| Systems & Data Ready | Website launch date agreed | Sarah Z |  |  | 2022-03-21 | complete | See workplan
| Systems & Data Ready | All web content and PDF editable forms correct, complete and signed off | Sarah Z |  |  | 2022-03-21 | complete | Web migration in progress
| Systems & Data Ready | Existing duplicate web pages reviewed and deleted/redirected/updated as required | Ed |  |  | 2022-03-21 | complete | testing in progress
| Systems & Data Ready | All new required assets allocated - laptops, tablets, mobile phones, headsets (Netcall users), printer | Glynn |  |  | 2022-03-18 | complete | Equipment allocation in progress
| Systems & Data Ready | PPP have updated their website to redirect customers to WBC | Ed |  |  | 2022-04-01 | complete | Banner on site 04/04

## Go Live Schedule (hidden)
Date & Task Description | Start time | Duration in days | Who | Notes / Requirements

## New Starter Schedule (hidden)
IT New Starter List
Enforcement and Safety Service
Name | Job Title | Current email | Personnel number | Start date
Gina Frost | Anti Social Behaviour Service Manager |  |  | 2022-03-01
Keiran Hinchliffe | Licensing and Processing Service Manager |  |  | 2022-03-01
Marcus Herbert | Environmental Health Service Manager |  |  | 2022-03-23
Michael Heslehurst | Environmental Health Officer Commercial | Michael.Heslehurst@westberks.gov.uk |  | 2022-04-01
Ann Heslehurst | Environmental Health Officer Commercial | Ann.Heslehurst@westberks.gov.uk |  | 2022-04-01
Kim Bridger | System Administrator | Kim Bridger (West Berks) <Kim.Bridger@westberks.gov.uk> |  | 2022-04-01
Karen Court | Licensing Officer | Karen Court (West Berks) <Karen.Court@westberks.gov.uk> |  | 2022-04-01
Linda Taylor | Licensing Processing Officer | Linda Taylor (West Berks) <Linda.Taylor@westberks.gov.uk> |  | 2022-04-01
Jayne Squires | Licensing Processing Officer | Jayne Squires (West Berks) <Jayne.Squires@westberks.gov.uk> |  | 2022-04-01
Vacant | Licensing Processing Officer |  |  | 14/3/2022 TBC
Vacant | Customer Delivery Officer |  |  | 14/3/2022 TBC
Vacant | Customer Delivery Officer |  |  | 14/3/2022 TBC
Vacant | Customer Delivery Officer |  |  | 2022-04-01
Emma Choules | Environmental Health Officer Residential and Environmental | Emma Choules (West Berks) <Emma.Choules@westberks.gov.uk> |  | 2022-04-01
Sophie Needs | Environmental Health Officer Residential and Environmental | Sophie Needs (West Berks) <Sophie.Needs@westberks.gov.uk> |  | 2022-04-01
Georgina Wady | Environmental Health Officer Residential and Environmental | Georgina Rosso (West Berks) <Georgina.Rosso@westberks.gov.uk> |  | 2022-04-01
David Bridle | Environmental Health Officer Residential and Environmental | David Bridle <David.Bridle1@westberks.gov.uk> |  | 2022-04-01
Bill Hickson | Anti Social Behaviour Officer |  |  | 2022-03-21
David Hare | Anti Social Behaviour Officer |  |  | 2022-03-21
Chris Long | Anti Social Behaviour Officer |  |  | 2022-03-21
James Phillips | Anti Social Behaviour Officer | James Phillips (West Berks) <James.Phillips1@westberks.gov.uk> |  | 2022-03-21
Abid Khan | Anti Social Behaviour Officer |  |  | 2022-03-21
Vacant | Anti Social Behaviour Officer |  |  | TBC
Caroline Parker | Animal Warden |  |  | 2022-03-21
Mandy Dorman | Animal Warden |  |  | 2022-04-01
Vacant | NSL Contractor |  |  | 2022-03-21
Vacant | NSL Contractor |  |  | 2022-03-22
Vacant | NSL Contractor |  |  | 2022-03-23
Vacant | NSL Contractor |  |  | 2022-03-24

## Comms Plan (hidden)
What | When | How | Who to/Who By | Completed? Y/N

## Key Contacts (hidden)
Team | Name | Email | Phone | Location | Available | Include in progress emails | Include in Escalation Emails | Include in Checkpoint calls | Include in Escalation Calls
PMO
Technical Leads
Critical Resources - Day 1
Suppliers
Escalations/Sign Off