## Slide 1
Public Protection Partnership (PPP) Programme
Project Initiation Document
June 2021

## Slide 2
Version | Date | Description of change | Author | Head of Digital and PMO | Project Sponsor
0.2 |  | Sign off Version 1 |  |  | 
Name | Role | Date
Philip Osborne | Project Manager | 27 May 21
Kelly Withers | Business Change Specialist | 30 June 21
Independent Consultant | Lead SME and PPP Consultant | 5 July 21
Lewis Borges | Head of Business Change | 22 July 21
Name | Role | Organisation/Dept | Date
Lewis Borges | Head of Business Change | Digital & Change | 22 July 21
Stephen Brown | Senior Responsible Officer | Place & Growth | 23 July 21
Steve Moore | Programme Sponsor | Place & Growth | 26 July 21
Version Control
Contributors/Reviewers
Authorisation/Approval
PPP Project Initiation Document | Sign Off

## Slide 3: PPP Project Initiation Document | Contents
Contents |  |  | 
1 | Overview and Background | 11 | Assumptions
2 | Scope | 12 | Communications
3 | Milestones | 13 | Equality Impact Assessment
4 | Objectives and Benefits | 14 | Privacy Impact Assessment Background
5 | Benefits Map | 15 | Privacy Impact Assessment
6 | Acceptance Criteria | 16 | Change Control Process
7 | Project Costs | 17 | Change Control
8 | Initial Risks | 18 | Appendices:
9 | Governance and Control | Appen. 1 | Programme Structure
10 | Project Team | Appen. 2 | Roadmap

## Slide 4: PPP Project Initiation Document | Overview & Background
Background
The Public Protection Partnership (PPP) is a shared service that delivers Environmental Health, Licensing and Trading Standards across Bracknell Forest, West Berkshire and Wokingham Borough Councils.
The shared service agreement was originally commissioned in 2010 and a new partnership was extended in 2017 to include Bracknell Forest Council for a ten-year term. The shared service staff are employed by West Berkshire, and management of the service is via a ‘Joint Committee’ which aims to meet four times a year. The Committee provides strategic direction and makes key decisions regarding the Joint Public Protection Service.
Programme Objective
An Executive decision has been taken to exit the shared service agreement and formal notice has been given to leave by 31 March 2022. There is a desire to bring regulatory PPP functions back in-house, with an enhanced out of hours Anti-Social Behaviour Service, commissioning functions that result in a better outcome over an in-house service.
This Programme will oversee the delivery of:
Designing a new regulatory service to enable PPP functions to be brought back to WBC.
Activity to support negotiations with PPP and mobilisation arrangements.
Activity to enhance the customer experience, and review resource alignment.

## Slide 5: PPP Project Initiation Document | Phase 1 Scope (To 31 March 2022)
 | In scope | Out of Scope
COMMS | Internal comms to PPP staff, management and Members External comms to residents and partners Recruitment campaign | Public consultation
DESIGN | Best practice research, information and data gathering Design a new regulatory in-house PPP service (lift and shift replica of existing service from West Berks) with an enhanced out of hours ASB service Design a new customer front door Process redesign for new service KPI review and development Mobilisation of new service | Delivery of any new PPP services, except for an ASB service The inclusion of Building Control (this will be delivered as part of a new project) Commissioned service call handling Localities synergies
TECHNOLOGY & DIGITAL | Civica APP functionality review, including customer portal and mobile APP Civica data and document migration​ Website design and development D365 development​ and forms | 
FINANCE | Project costs ​ Budget review and investigation of grants and costs Commercialisation – identify desire for revenue increase ​ Actuarial Exit valuation​ and liabilities | PPP target operating model (this is being undertaken as part of a separate review)
HR | Staffing structure & transfers Development of a Training Plan, ​and an Induction and On-boarding Process JD reviews​ and evaluation Contract revisions, including uniform wearing & 24/7 shift deployment Manage redeployment & redundancies (if any) | 
LEGAL | Contract review, negotiations and development of a bilateral exit plan​ Subcontracted services review ​ Procurement & commissioning​ In-house enforcement delegation & authorisation scheme creation​ | 
PROPERTY | Infrastructure & office accommodation​ Staff locations and space​ Specialist storage​ Review of 24/7 building access​ Fleet vehicle parking | 

## Slide 6: PPP Project Initiation Document | Phase 2 Scope (Post 1 April 2022)
 | In scope | Out of Scope | To be determined
COMMS | Internal comms to PPP staff, management and Members External comms to residents and partners Recruitment campaign (if required) |  | Customer feedback survey Staff feedback survey
DESIGN | Best practice research, information and data gathering for enhanced PPP service offer Service review to scope areas for enhancement and continuous improvement Design an enhanced customer front door Town and Parish Council partnership arrangements Enhanced process redesign for new service Service performance review Mobilisation of service enhancements |  | Synergies with localities, waste, housing, community safety and other WBC regulations
TECHNOLOGY & DIGITAL | New system and functionality Procurement of new system Data and document migration Enhanced customer experience development |  | 
FINANCE | Financial review to identify opportunities for income generation and savings |  | 
HR | Recruitment of new staff ​(if required) |  | 
LEGAL | Contract management review of commissioned services (if any) |  | 
PROPERTY | Property review of infrastructure, office accommodation​, locations, specialist storage and fleet |  | 

## Slide 7: PPP Project Initiation Document | Milestones
KPI development
Staff structure agreed
Staff transfer process agreed
Staff Comms
IT requirements and user stories
Service costing
Determine commissioning needs
August 2021
Civica APP build and data migration
Determine accommodation needs
Design Pack approval
Process redesign
Exit valuation (Pensions)
Consultation Process
HoS recruitment
October 2021
Staff equipment review
Equipment and infrastructure transfer
KPI setting
ESRI development (tbc)
Resident comms
Service commissioning
Contract transfers
July 2021
November 2021
Specialist storage
Recruitment and redeployment
December 2021
Website interface build
Mobilisation planning
Staffing
Document migration
Power Bi
Fleet vehicle parking
Establish safety advisory group
January 2022
February 2022
Go-live comms
Suppliers set up
Third party contracts
New IT equipment
Mobilisation start
Skills audit
Accounts receivable mapping
Netcall build
Redundancies (if any)
March 2022
Acceptance into Service
Run down to Go-live
Service launch
Training plan
Tablets
June 2021
Bilateral Exit Plan
Draft Design Pack
IMT Survey
Civica engagement
Staff comms
Data analysis and activity tracking
September 2021
Training and induction plan development
Design implementation
D365 development
Budget setting
HoS onboarding
Staff location planning
April 2022
Post go-live support
Benefits realisation
Phase 1 closure
Phase 2 initiation

## Slide 8
PPP Project Initiation Document | Objectives and Benefits
Corporate Objective | Driver | Objective / Benefit description | How will this be measured (SMART) |  | Owner
CH BB | Provide an in-house Public Protection Service | Objective: To design a new in-house regulatory Public Protection Service, with enhanced ASB offer | S | Launch a like-for-like in-house Public Protection Service, with enhanced ASB out of hours offer on 1 April 2022 | SM
 |  |  | M |  | 
 |  |  | A |  | 
 |  | Benefit: Enable WBC to secure improved levels of service |  |  | 
 |  |  | R |  | 
 |  |  | T |  | 
BB | Provide a specialist and scientific Public Protection Service | Objective: To commission highly technical and scientific services from specialist providers | S | Commission specialist providers to deliver highly technical and scientific services, as part of our Public Protection Service from 1 April 2022 | SM
 |  |  | M |  | 
CH | Enhanced customer experience | Objective: To design an efficient and responsive customer journey for residents to enhance the customer experience and improve visibility of council staff in the localities | S | The out of hours ASB service is able to respond to high priority customer requests within 2 hours & handle a wider range of customer concerns over a 7 day week | SM
 |  |  | M |  | 
 |  |  | A |  | 
 |  | Benefit: Ensure high levels of customer satisfaction | R |  | 
 |  |  | T |  | 
BB | One Team approach | Objective: To fully integrate Public Protection within WBC and ensure One Team approach with other key services | S | Processes have been designed to enable Public Protection to integrate with existing customer-facing services from 1 April 2022 | SM
 |  |  | M |  | 
 |  |  | A |  | 
 |  | Benefit: Improved integration with WBC Localities, Community Safety, Housing and other place services | R |  | 
 |  |  | T |  | 

## Slide 9
PPP Project Initiation Document | Objectives and Benefits
Corporate Objective | Driver | Objective / Benefit description | How will this be measured (SMART) |  | Owner
CH | Enhanced customer journey through technology | Objective: Enabling systems to work together to simplify transactions and underpin process efficiencies | S | Integrated systems and good customer useability design from 1 April 2022 | GD NS
 |  |  | M |  | 
 |  |  | A |  | 
 |  | Benefit: Improved and partly automated customer journey with streamlined processes and simplified transactions for staff. |  |  | 
 |  |  | R |  | 
 |  |  | T |  | 
CH | Enhance customer experience | Objective: Consolidate food & food standards hygiene inspection's into one visit wherever possible | S | The number in a percentage of combined inspections from April 1st 2022 | SM
 |  |  | M |  | 
 |  |  | A |  | 
 |  | Benefit: increased efficiency for WBC and a reduction in regulatory burden for the trader | R |  | 
 |  |  | T |  | 

## Slide 10
PPP Project Initiation Document| Benefits Realisation Map
Benefit ID | Benefit description | Aligned To MTFP? | Target Date | During / Launch or Post Project
01 | Improved customer journey | No | 1 April 2022 | Launch
02 | Faster response to reported nuisance for residents | No | 31 March 2023 | Post
03 | Improved connectivity with other council services | No | 1 April 2022 | Launch
04 | Improved customer service and satisfaction | No | 31 March 2023 | Post
06 | Improved performance standards and ways of working | No | 31 March 2023 | Post
08 | Branding of service delivery as WBC | No | 1 April 2022 | Launch
09 | Robust Contract management of commissioned services | No | 31 March 2023 | Post

## Slide 11
PPP Project Initiation Document | Acceptance Criteria
Deliverable | Current Level (Prior to Project) | Acceptance Level (Acceptable at Handover)
A new in-house regulatory Public Protection Service, with enhanced ASB offer | Regulatory Public Protection Service delivered by West Berks PPP | Regulatory Public Protection Service delivered by WBC, with an enhanced out of hours ASB offer
A new customer front door | Customer front door currently delivered through West Berks PPP | Online access to PPP service through forms on council website and telephone access through Customer Delivery
Processes designed for new service | Key processes currently delivered through West Berks PPP | New service fully integrated into WBC with streamlined processes ensuring One Team approach with other key services
KPIs developed for new service | KPIs developed by West Berks PPP | New KPI’s developed for service
Civica APP and mobile access | Civica APP in use by West Berks PPP | Improve visibility of council staff in the borough and staff ability to access customer case information remotely

## Slide 12
PPP Project Initiation Document | Project costs & budget
Component | Cost item | Costs
Resources | SME – assumed 12 months cost 20 days per month Technology Project Manager – 1 FTE for 12 months – Jul to Jun ESRI Developer 1 FTE for 6 months @G8 Implementation Officer 1 FTE for 6 months Oct to March Business Analyst 1 FTE for 12 months @G8 HR Support 0.7 FTE for 10 months June to March UX Specialist External Legal Counsel | 
Sub total |  | £ 375,617
Hardware | Hardware for 30 staff £1500 per head (phone & laptop/tablet) (Capital Bid) | £45,000
Sub total |  | £45,000
Other | Licences D365, E5, Netcall for 30 people West Berks IT costs (TBC) | 
Sub total |  | £87,240
Total costs |  | £507,857

## Slide 13
PPP Project Initiation Document | Initial risks
Ref | Risk Description | RAG | Owner | Mitigations
1 | Due to receiving no response to the IT survey sent to West Berks on 7th May, there is a risk that this will result in unnecessary delay to programme progress and timescales​ |  | GD | Senior management escalation
2 | Due to document exchange progressing slowly between WBC and PPP for key negotiating issues, there is a risk that this will result in unnecessary delay to programme progress and timescales​ |  | DT, SO | Request anticipated date for provision of requested documents Tri-borough Exec Director meetings underway​ Greater Director oversight of management decisions-making Commitment to alignment of joint workstream plans

## Slide 14
JPPC Quarterly PPP
Tri-Borough Board Meeting
High level status updates
Decision making & Agreements
Comms
Weekly / Fortnightly
Individual Workstream Meetings
Progress reports
Project plan
Risk register
Issues resolution
Project Manager: Mandy Holdstock Sponsor: Steve Moore
SRO: Stephen Brown
SME Consultant: David Thrale
Digital & Change AD: Sally Watkins
Head of Business Change: Lewis Borges
Sponsor: Steve Moore
SRO: Stephen Brown
WB & BF Directors
WBC, WB & BR Members
Fortnightly
Steering Group Meeting
Programme updates
Individual workstream updates Interdependencies, Risks & Issues
Budget, Change Control
Project Manager: Mandy Holdstock
Technical and Digital Project Manager: Kate Hutchings
SME & Consultant: David Thrale
Workstream Leads
Agreed SME’s and business representation
Business Change Specialist: Kelly Withers, Freya Donohue-Hall
Monthly
Programme Board Group
High level Programme status update
High level individual workstream updates
Escalations, Issues, Budget, Change Control
Discussion ahead of CLT
Project Manager: Mandy Holdstock
SRO: Stephen Brown
SME & Consultant: David Thrale
Workstream Leads
Agreed SME’s and business representation
Business Change representation
Six Weekly CLT Report
Escalations
Budget approval
High level status Updates
Comms
Sponsor: Steve Moore
SRO: Stephen Brown
SME & Consultant: David Thrale
Corporate Leadership Team
Monthly Members
Update
High level status Updates
Decision making
PPP Project Initiation Document | Governance & Controls

## Slide 15
PPP Project Initiation Document | Project Team
Name | Area of work | Role | Responsibility
Mandy Holdstock | PMO | Project Manager | Manages Project day-to-day
Kate Hutchings | PMO | Technology & Digital Project Manager | Manages Project for Technology & Digital Workstream
Steve Moore | Director P&G | Sponsor | Programme Sponsor
Stephen Brown | AD P&G | SRO | Programme Senior Responsible Officer
Lewis Borges | Head of Business Change | Head of Business Change | Business Change decisions and Design SME
Kelly Withers | Business Change | Business Change Specialist | Design SME
Freya Donohue-Hall | Business Change | Business Change Specialist | Design & Project Support
Independent Consultant | Consultant | Regulatory SME | Design Workstream Lead
Glynn Davies | Head of IMT | IMT Technical Lead | Technology & Digital Workstream Lead
Sean Murphy | West Berks PPP | PPP Lead Specialist | PPP Lead
Paul Anstey | West Berks PPP | PPP Specialist | PPP Project Manager
Rebecca Bird | Communications | Communications Lead | Comms Workstream Lead
Sean O’Connor | Legal | Legal Specialist | Legal Workstream Lead
Keith McKenzie / Shaheen Patel | Finance | Project Finance Accountant | Finance Workstream Lead
Valentina Velcheva | Procurement | Procurement & Contracts Specialist | Legal SME
Andree Cantale | Human Resources | HR Specialist | HR Workstream Lead
Rodney Hing | Property | Head Operational Property | Property Workstream Lead
Jackie Whitney | Customer Delivery | CD SME | Design SME

## Slide 16
PPP Project Initiation Document | Assumptions
Full political support and engagement for the project will ensure desired outcomes
The Project Team will be provided with full access to relevant information and data to understand the existing PPP arrangements
Costs related to the PPP Exit Plan will be managed effectively
IT and process changes will be manageable within existing licenses
Transfers to back office systems can be undertaken automatically by use of interfaces
Any process changes will be implementable with current telephony platforms
Staff can be recruited to all new service posts
Accommodation can be accessed by staff during the new 7 day a week service hours

## Slide 17
PPP Project Initiation Document | Communications
Communications Objectives
To raise awareness of the relocation of the Public Protection Partnership services in the Wokingham Borough and how to contact them by ensuring key messages are articulated around proposals, outcomes, key milestones and benefits
For all employees of the PPP to understand why Wokingham Borough Council is leaving the partnership, its benefits, process and timeline
To ensure the communications activities support the delivery of the PPP relocation

## Slide 18: PPP Project Initiation Document | Equality Impact Assessment
Brief description on what the project is and how it may affect the protected characteristics.
Protected characteristics​ | Impact score​ | Please detail what impact will be felt by the protected group | Reason for Impact Score​
Race:​ | High | The new 7 day a week service will enable the council to protect communities & individuals to a greater extent and at a benefit to those individuals. Often minority, disabled, deprived and women are disproportionately affected by ASB | Assisted delivery will be offered to enable access to service with language barriers
Gender:​ | High | The new 7 day a week service will enable the council to protect communities & individuals to a greater extent and at a benefit to those individuals. Often minority, disabled, deprived and women are disproportionately affected by ASB | ​
Disabilities:​ | High | The new 7 day a week service will enable the council to protect communities & individuals to a greater extent and at a benefit to those individuals. Often minority, disabled, deprived and women are disproportionately affected by ASB | Assisted delivery will be offered to enable access to service through web forms for visually-impaired
Age:​ | Low | ASB reports may be related to protected characteristics | Assisted delivery will be offered to enable access to service for anyone without access to the internet
Sexual orientation:​ | Low | ASB reports may be related to protected characteristics | ​
Religion/belief:​ | Low | ASB reports may be related to protected characteristics | ​
Gender re-assignment:​ | Low | ASB reports may be related to protected characteristics | ​To consider use of language and pronoun options for web forms
Pregnancy and Maternity:​ | High | The new 7 day a week service will enable the council to protect communities & individuals to a greater extent and at a benefit to those individuals. Often minority, disabled, deprived and women are disproportionately affected by ASB | ​
Marriage and civil partnership: | Low | ASB reports may be related to protected characteristics | 

## Slide 19: PPP Project Initiation Document | Privacy Impact Assessment
All projects must consider their Privacy Impact Assessment (PIA) A Privacy Impact Assessment (PIA) is a process which helps assess privacy risks to individuals in the collection, use, and disclosure of personal information. A failure to properly embed appropriate privacy protection measures may result in a breach of legislation.​
​
The purpose of a PIA assessment is to identify the risks that may arise through the project and propose methods to mitigate against the risks.​
Some examples when to complete a PIA; you introduce a new or make changes to a system to collect and hold personal data, collecting personal data for a new purpose, transferring personal data between organisations, significant change in process operation involving personal data. ​
​
This template is a practical tool to help identify and address the data protection and privacy concerns at the design and development stage of a project, building data protection compliance in from the outset rather than bolting it on as an afterthought.​
​
Next Steps​
There are 10 screening questions in there to see if a PIA is required. ​
The Data Protection Officer can provide advice and guidance, review the completed PIA template, and advise on the need for completing a PIA if the screening questions are borderline or minor.​ You can contact the information governance team via this email address :
PIA documents can be requested by the Information Commissioners Office (ICO) to be provided to them at any time. ​
​
​

## Slide 20: PPP Project Initiation Document | Privacy Impact Assessment*
 | Y/N
Will the project involve the collection of new information about individuals? | Y
Does the project/process include the processing of "special categories of personal data"? | Y
Will the project compel individuals to provide information about themselves? | Y
Will information about individuals be disclosed to organisations or people who have not previously had routine access to the information? | Y
Are you using information about individuals for a purpose it is not currently used for, or in a way it is not currently used? | Y
Does the project involve you using new technology which might be perceived as being privacy intrusive? For example, the use of biometrics or facial recognition? | Y – photo evidence
Will the project result in you making decisions or taking action against individuals in ways which can have a significant impact on them? | Y
Is the information about individuals of a kind particularly likely to raise privacy concerns or expectations? For example, health records, criminal records or other information that people would consider to be particularly private. | Y
Will the project require you to contact individuals in ways which they may find intrusive? | Y – OOH visits
Has this project/process already been started as a pilot without a screening or PIA being undertaken? | N

## Slide 21
How will requests for change be managed?
PPP Project Initiation Document | Change Control
Project Manager
Completes Change Control Request
Senior Project Manager
Reviews request takes to Board
SRO
Reviews Change request signs off

## Slide 22
Total Change Requests | 0 | Open Change Requests | 0 | Approved Change Requests | 0
ID | Change Description | Requester | Date Raised | Decision | Comments
1 |  |  |  |  | 
2 |  |  |  |  | 
3 |  |  |  |  | 
PPP Project Initiation Document | Change Control

## Slide 23
PPP Project Initiation Document | Appendices
Appendices contents | 
Appendix 1 | Programme structure
Appendix 2 | Programme workstreams
Appendix 3 | Roadmap

## Slide 24: PPP Project Initiation Document | Programme Structure
PPP Programme Workstreams
Design
Property
Technology & Digital
Finance
Legal
Comms
HR
Responsible for the overall design of bringing the PPP services back in house
Accommodation requirements for the PPP team moving back to WBC office space
Review, redesign and integration of IT systems and processes
Costing/budget for programme and review of all financial aspects
Legal review and engagement for current and future PPP services, including procurement and commissioning
Internal & External Communications for PPP and WBC
HR processes for PPP staff and recruitment
Lead:
Glynn Davies
SMEs:
Julie Teague
Lead:
Keith McKenzie
SMEs:
Shaheen Patel
Lead:
Sean O’Connor
SMEs:
Valentina Velcheva
Lead:
Rebecca Bird
SMEs:
David Allen
Lead:
Andree Cantale
SMEs:
Sharon Willis, Sarah Brown
Lead:
Rodney Hing
SMEs:
Sharon Kirk
Project Management – Mandy Holdstock
Lead:
Independent Consultant
SMEs:
Lewis Borges, Kelly Withers, and Jackie Whitney

## Slide 25: PPP Project Initiation Document | Programme Workstreams
PPP Programme Workstreams
Design | Technology & Digital | Finance | Legal | Comms | HR | Property
Responsible for the overall design of bringing the PPP services back in house | Review, redesign and integration of IT systems and processes | Costing/budget for programme and review of all financial aspects | Legal review and engagement for current and future PPP services | Internal & External Communications for PPP and WBC | HR processes for PPP staff and recruitment | Accommodation requirements for the PPP team moving back to WBC office space
Lead: Independent Consultant | Lead: Glynn Davies | Lead: tbc | Lead: Sean O’Connor | Lead: Rebecca Bird | Lead: Andree Cantale | Lead: Rodney Hing
SMEs Lewis Borges, Kelly Withers, Jackie Whitney | SME Julie Teague | SMEs Keith McKenzie | SME Valentina Velcheva | SME David Allen | SME Sharon Willis & Sarah Brown | SME Sharon Kirk
Scoping & activity analysis Data gathering Policy review Process redesign Workshops PPP negotiations Provided exit plan to PPP Establish new KPI’s Subcontracted services review Partnerships – internal & external JD’s written Mobilisation | Engagement with PPP IT and survey Establish IT costs Civica APP review Review ‘lift and shift’ options Development and integration of ESRI Data migration Dynamics development Power BI mobilisation Tablet/IT reporting/comms tools | Project costs Budget review Commercialisation – identify desire for revenue increase Target Operating model Investigate grants and costs Fees and Charges review Actuarial Exit valuation Liabilities | Legal Review & engagement Contract transfer Subcontracted services Review Procurement & commissioning Ensuring SLA and contract management compliance | Internal comms - PPP staff / WBC Staff Liaise with West Berks Comms team External comms – residents Members Partners | Staffing structure & transfers Training Plan JD reviews Recruitment Redundancies (if any) Contract revisions | Infrastructure & office accommodation Staff locations and space Specialist storage Review of 24/7 building access Fleet vehicle parking

## Slide 26
PPP Project Initiation Document | Roadmap
PPP Service Extraction
Governance
Scoping
Project costs
Data gathering
IMT engagement
Process redesign
Budget review
Target Operating model
Investigate grants and costs
Legal Review & engagement
Exit plan to be provided to PPP
Establish new KPIs
Accommodation
Contract transfer
Subcontracted services Review
Procurement/commissioning
Staffing structure & transfers
Training Plan
New Regulatory Service
Establish safety advisory group
Statutory duties review
Policy review
Fees and Charges review
Commercialisation – identify desire for revenue increase
Process Redesign
Review of services – reduce or stop (e.g. to allow prioritising ASB)
ASB & Localities Collaborative Service
Vision of how Localities to fit into PPP
Engagement with Localities
Agreement with P&G Director and Localities
Restructuring
Infrastructure – office accommodation etc.
Tablet/IT reporting/comms tools
Community engagement with members, town and parish councils
Move away from OOH – complications
Partnerships – internal