## HOL Rents
Risk ID | Status | Programme | Risk Description | Risk or Issue | Likelihood | Impact | Risk Score | Project Manager | Date Reviewed | Date Raised | Workstream | Project | Mitigations | Mitigation Owner | Mitigation Due Date | Title | Score
HOLR1 | Closed | IT | There is a risk that if Paypoint integration is required then bespoke NEC consultancy might be required resulting in extra costs to pay for licensing and professional services. | Risk | 2 | 2 | 4 | Daniel Sabaroche | 2022-08-19 | 2022-08-11 |  | HOL Rents Implementation | 1. Seek assistance from Applications Officer on what work might be involved. 2. Obtain confirmation from Lead SME if integration was overlooked but required. 3. Communicate with NEC representative in September. | Harrison Wilks;#302 | 2022-08-19 | Costs and Dependencies | 0

## Chip & Pin
Risk ID | Status | Programme | Risk Description | Risk or Issue | Likelihood | Impact | Risk Score | Project Manager | Date Reviewed | Date Raised | Workstream | Project | Mitigations | Mitigation Owner | Mitigation Due Date | Title | Score
CandP1 | Closed | IT | Prior to the implementation of Azure SSO using the HeyCentric payment solution, the supplier confirmed that a code needs to be deployed into the environment. This was scheduled for completion on Thursday 28th July OOH in the evening with an email sent the following morning to confirm status. No correspondence has been received despite emails sent to the Head of Ops and v/mails left as at 01 08 2022. Julie Teague informed of status on 01 08 2022 and IT Leads informed via chat messaging group on the same day. | Issue |  |  | 0 | Daniel Sabaroche | 2022-08-01 | 2022-07-29 |  | Chip & Pin Replacement | Raised with IT Leads - Julie Teague and Simon Beasley | Daniel Sabaroche;#30 | 2022-08-05 | Dependencies | 0
CandP2 | Closed | IT | Due to HeyCentric not supplying any system or operational user guides to distribute to internal users and super users coupled with a non-working test system, it has, is and will lead to a lack of confidence / assurance in the system as users will have less confidence as they do not understand system functionality and could lead to payment errors and data protection outcomes. | Issue | 1 | 2 | 2 | Daniel Sabaroche | 2022-11-02 | 2022-09-09 |  | Chip & Pin Replacement | 1. HeyCentric initially produced a video that was sent to the responsible Team Leads in the Library Service, The Ambleside Centre, Dinton Activity Centre and the Cashiering team to distribute to their team members. 2. PM is working with Business Analyst and Cashiers team to develop a user guide for chip and pin payments and the 'to be' process mapped in MS Visio - still requires time away from normal BAU work to develop and test. 3. PM requires Business Analyst throughout the implementation to work with stakeholders to capture and produce user guides for C&P activities, ATP activities, ARP (MOTO) activities and functionality that sits outside of MasterCard dependent functionality. | Julie Teague;#138 | 2023-03-31 | Training: User Guides and System documentation | 0
CandP3 | Closed | IT | Due to receipt cancellation not working in the HeyCentric solution (support ticket raised) the Senior Cashiers are unable to self-service these requests to cancel and refund a customer transaction if a customer sends a request. The HeyCentric Consultant has stated that users should use the 'Cancel and Refund' menu function, however, our prod environment does not have this functionality and will only be added when the 'Web Payments' module is implemented. Impact: WBC is reliant on HeyCentric tech support to cancel and refund any transactions. | Issue | 6 | 6 | 36 | Daniel Sabaroche | 2022-10-07 | 2022-09-13 |  | Chip & Pin Replacement | Daniel S has communicated with location leads at Libraries, Dinton Activity Centre, The Ambleside and Cashiers team not to use the 'Cancel Receipt' menu item but if used to raise a ticket on the IT Self-Service portal so that the applications team raise a HeyCentric ticket on their support portal to complete a customer refund as the Senior Cashiers also do not have admin access to the Stripe account to self service. | Julie Teague;#138 | 2022-12-31 | Software | 0
CandP4 | Closed | IT | Due to changes to van access and availability of team members, there is a likelihood that a few libraries might not be completed and work rollover to Jan 2023. | Issue | 3 | 2 | 6 | Daniel Sabaroche | 2022-12-16 | 2022-12-01 |  | Chip & Pin Replacement | Will seek additional van access for a longer timeframe. | Julie Teague;#138 | 2022-12-16 | Schedule and Resources | 0

## DI
Risk ID | Status | Programme | Risk Description | Risk or Issue | Likelihood | Impact | Risk Score | Project Manager | Date Reviewed | Date Raised | Workstream | Project | Mitigations | Mitigation Owner | Mitigation Due Date | Title | Score
DI-0025 | Closed | Business Intelligence | Simpsons seem reluctant to provide a time line with activities to finalise build resulting in us not being able to plan appropriately resource and activities our side. | Issue |  |  | 0 | Joanne Veitch | 2022-06-24 | 2022-05-09 |  | Data and insight | Raised 3 times in this weeks standups simpsons have advised they will provide by 18.5 WR to raise with Tom if not forthcoming | Joanne Veitch;#33 | 2022-06-17 | Dependencies | 0
DI-0026 | Closed | Business Intelligence | Children's services - there is a risk with CS to any future DI project due to their wish to not be reliant on central IT / Data team to be able to manage their data and insight. Resulting in their data and insight being produced outside of our data warehouse | Risk |  |  | 0 | Joanne Veitch | 2022-06-24 | 2022-05-11 |  | Data and insight | WR to raise with MG JT attending meeting with CS to discuss their other data warehouse project LB aware WR /SW to join up ASC to project more meeting planned WR/JV meeting with Sudeshna/Shanoor to join up benefits and projects GD – meeting with RO to align to our project and what IT will allow – including offering CS to fund a data lead within JT team to super charge them CS/ASC work added to timeline for DI overview for up and coming work - to be discussed further with SW/LB 10.6 shanoor working with us to select trainer and we are aligning DI time lines with CS/ASC priorities to support - Shanoors team will be able to do a lot of the work and we can also support a more from their team into JT so they have more access, if needed and we are not seen to hold them back. | Will Roper;#248 | 2022-06-30 | Scope | 0
DI-0028 | Closed | Business Intelligence | there is a risk due to financial process to release interim monies not being in place (while waiting for funding) that we will not be able to up skill start during the summer within PowerBI resulting in us not having the necessary skill set to deliver PowerBI dashboards without significant external support | Risk |  |  | 0 | Joanne Veitch | 2022-06-24 | 2022-05-27 |  | Data and insight | Meeting planned with LB/GD/WR and finance June Training needs and costs collected | Ruth Watkins;#227 | 2022-06-23 | Costs | 0
DI-0029 | Closed | Business Intelligence | – there is a risk that due to the rapidly developing political position, the restructure of the change program and the desire to deliver meaningful results quickly that the operational delivery vs the strategic delivery will not be aligned. | Risk |  |  | 0 | Joanne Veitch | 2022-06-10 | 2022-05-26 |  | Data and insight | Ensure good communication lines via steering and board to CLT. Meetings planned for assets, procurement and workforce. Work sizing and priorities need to be understood for priorities to be agreed- link back initial work to Business intelligence project - discuss further with Lewis once ready | Joanne Veitch;#33 | 2022-06-26 | scope, costs, schedule | 0
DI-0030 | Closed | Business Intelligence | Simpson have failed to deliver build to agreed timelines again, resulting in delays in UAT . Despite escalations over the last two weeks with the account manager simpsons have resource on other projects and struggling to move them to our project despite our meetings and discussions on the volume of work they have to complete. | Risk |  |  | 0 | Joanne Veitch | 2022-06-10 | 2022-05-27 |  | Data and insight | Daily meetings with account manager – acknowledgement from Simpsons poor planning on their side. Resource diverted back to our project 2/3 weeks delay on build – replan of UAT. | Will Roper;#248 | 2022-07-31 | schedule | 0
DI-0031 | Closed | Business Intelligence | Due to change in leadership and potentially change in corporate KPIs we need to decide how we land this and use it going forward. We need to replan accordingly | Risk |  |  | 0 | Joanne Veitch | 2022-06-24 | 2022-05-26 |  | Data and insight | WR to progress how Corporate dashboard board will land Steering /Board. 10.6 discussed at steering & board - no quick changes full scoping and data needs will need to occur and heavy steer to not change things too quickly or mid year. | Will Roper;#248 | 2022-06-30 | scope | 0
DI-0031 | Closed | Business Intelligence | WBC do not have the Powerbi skill set currently in place to deliver Powerbi requirements for next phase-Training needs to take place and resource needs to be agreed for priorities/ recruitment needs to occur | Risk |  |  | 0 | Joanne Veitch | 2022-06-24 | 2022-05-26 |  | Data and insight | Discuss with LB/Steering Secure funding for training Back up plan – simpsons Meetings with 3 training providers underway | Will Roper;#248 | 2022-06-24 | Schedule/dependies | 0
DI-0032 | Closed | Business Intelligence | – WBC data team needs to set up a prioritisation, sizing agile process for insight to enable work priorities and schedules to be managed. Staff need some upskilling and we need to recruit a lead to manage this with the Azure data lake /warehouse and BI knowledge. | Risk |  |  | 0 | Joanne Veitch | 2022-06-24 | 2022-05-26 |  | Data and insight | Steering/Board to agree resource and budget to recruit Meeting planned with LB/GD/WR and finance June SW to approve | Lewis Borges;#120;#Will Roper;#248 | 2022-06-24 | scope - phase 2 | 0
DI-0032 | Closed | Business Intelligence | Due to the political changes new KPI's and changes to KPI's are being requested combined with Changes for mandatory inspections within ASC services resulting in requests to alter the current performance pack. Resulting in our recommendation to not go live with the kpi performance dashboard but postpone until new KPI's are defined and agreed and built. We recommendation the build continues to complete the UAT and handover from simpsons. But we do not use the dashboards and process's to publish the report for Q1/Q2 and revert to the as is process of manual report. | Risk |  |  | 0 | Joanne Veitch | 2022-06-24 | 2022-06-16 |  | Data and insight | Steering and SW advised and aligned to hold off using dashboard - SW to discuss and agree with SP - wider coms can be issued. Project Team Aware | Will Roper;#248 | 2022-06-30 | Scope | 0
DI-005 | Closed | Business Intelligence | There is a risk on length of signoff for UAT due to the number of owners of the corporate KPI's- Resulting in project overrun and late changes. | Risk |  |  | 0 | Joanne Veitch | 2022-06-24 | 2021-12-10 |  | Data and insight | We will take super users on the development journey and design decisions. Project will be sprint based so mini UAT will be throughout the project. We will ensure AD's/Directors and members are included in communications and overviews on progress to ensure buy in and agreement for acceptance signoff and ensure these are planned into the project plan.. 10.1 - phase one is dashboard of the current slide deck so sign off and testing should be straightforward as its matching data and output to a manually produced report. Louise is working on the UAT detail and plan due by 20.3. | Will Roper;#248;#Joanne Veitch;#33 | 2022-06-24 | Schedule | 0
DI-009 | Closed | Business Intelligence | There is a risk that knowledge transfer will not be in place for the technical side of the project due to work loads and lack of resource. The project aim is to transfer skills but initial outline on approach does not cover this from Simpsons Simpsons to deliver our data foundation and feeds and dashboard with or without our team working along side them. Reminder issued to simpsons we need knowledge transfer daily standups to understand work planned to enable our resources to attend, Meeting planned With Ruth to discuss budget to enable recruitment across teams for project. | Risk |  |  | 0 | Joanne Veitch | 2022-06-24 | 2021-12-13 |  | Data and insight | MG and WR aware - Risk regarding resource flagged to MG to escalate. Risk Flagged to GD - JT & JB also raising resource and workload issues separately with GD. Simpsons have agreed to add in a days technical training. | Joanne Veitch;#33 | 2022-06-20 | Scope | 0
DI-015 | Closed | Business Intelligence | There is a risk due to Simpsons Agile project working vs our waterfall project style that WBC has no reassurance on timeline due to lack of visibility resulting in resource requests at last min and project timeline shifts. | Risk |  |  | 0 | Joanne Veitch | 2022-06-24 | 2022-02-14 |  | Data and insight | Discussed with Simpsons – agreed they would replan as waterfall to ensure we have the visibility we need plan should be with us by 14.2.22 , JV to review plan Incorporate with Overall project plan discussed with Simpsons- additional resource added - simpsons timeline is longer but overall time lines not effected for project/- planned CLT /Go live 24.6 SW met with Simpsons and now more focus has been applied to get us to the end line as Director at simpsons is working with us. | Joanne Veitch;#33 | 2022-06-24 | Schedule | 0
DI-018 | Closed | Business Intelligence | Whilst we have conducted a comprehensive discovery phase there is a risk that we still have unknown requirements that until they are discovered cannot be accounted for within the build | Risk |  |  | 0 | Joanne Veitch | 2022-06-24 | 2022-02-25 |  | Data and insight | If we find this situation, we will work with Simpsons to mitigate but we cannot pre-empt - sprint working with simpsons does not enable us to see what may come. until we access data and build starts we don't know data issues to resolve | Joanne Veitch;#33 | 2022-08-31 | Schedule | 0
DI-022 | Closed | Business Intelligence | There is a risk that Simpsons may start to push back on work -and length of time project is taking - they estimated the project would take 101 days to complete and due to the size and complexity they are likely to need more days they have used 73 % of the estimated days and they expected to have completed the majority of the build at this stage, but we are only 1/4 of the KPI's build so far. | Risk |  |  | 0 | Joanne Veitch | 2022-06-24 | 2022-04-01 |  | Data and insight | Contract is fixed price to deliver the agreed scope regardless of effort on their part - we paid a premium price for the contract to be at a fixed price. Will Roper is managing the relationship and needs to manage any push back on from Simpsons by using the contract. We will continue to monitor. | Will Roper;#248 | 2022-06-30 | scope | 0
BI-0031 | Closed | Business Intelligence | Due to a candidate rejecting the role, there is a risk that the recruitment of an Insight Analyst needed to support the team will be delayed, resulting in a reduction in the Power BI skills needed to meet BI requests. This is made worse by the loss of skilled BAU team members who have left the organisation. | Risk | 3 | 6 | 18 | Joanne Veitch | 2022-10-11 | 2022-09-26 |  | Business Intelligence | Members of the technical team are being upskilled with training to backfill and support. | Andrew Moulton;#300 | 2022-10-31 | Dependencies | 0
BI-005 | Closed | Business Intelligence | There is a risk around the project technical delivery team due to difficulty in recruiting a PowerBi data analyst due to the competitive market for these skills and salaries being offered. resulting in our reliance for Powerbi and reporting needs for BI programme to be produced by the Data team and ISI team neither of who have the capacity to do this across of the programme otherwise the role would not have been sort. resulting in delays and potentially the need to employ 3rd party to deliver outcomes on our behalf. | Risk | 2 | 2 | 4 | Joanne Veitch | 2022-10-14 | 2022-09-27 |  | Business Intelligence | Re-Advertising Role for BI DA - was offered but declined as better offer else where. Understand the impact on IT Data team to support and cover in the short term | Will Roper;#248;#Julie Teague;#138 | 2022-10-28 | Scope | 0
BI-R001 | Closed | Business Intelligence | There is a risk due to unknown requirements that we have not identified all the costs and needs for Resource (People) resulting in the need to back fill or ask for additional monies which may not be possible or cause delays | Risk |  |  | 0 | Joanne Veitch | 2022-08-03 | 2022-08-03 |  | Business Intelligence | Use existing resource both in the project and within business where possible being flexible. Dedicated technical resource being funded to deliver data needs | Joanne Veitch;#33;#Debra Peddle;#43 | 2022-09-30 | Scope | 0
BI-R003 | Closed | Business Intelligence | CLT to agree controls around purchasing reporting tools and renewal - need support around the end goal for one version of the truth and using BI/Data lake as a priority | Risk |  |  | 0 | Joanne Veitch | 2022-08-03 | 2022-08-03 |  | Business Intelligence | raise with Procurement program - this should be joined up with IT who should make the decision based on business case to agree. Regardless of business area. | Andrew Moulton;#300 | 2022-08-03 | Dependencies | 0
BI-R003 | Closed | Business Intelligence | Due to poor data quality, there is a risk that proposals may not be validated effectively, resulting in inaccurate insight and decisions. Data is owned by the business and the quality of the data and its maintenance is under business ownership. | Risk | 4 | 6 | 24 | Joanne Veitch | 2023-01-02 | 2022-08-03 |  | Business Intelligence | Understand interdependencies and how BI can support the business to assure their data and automate where possible. Insight strategy which includes data quality and improvement plan . Data Quality reports to be part of builds where possible to help reduce quality issues and improve upkeep of the data. | Andrew Moulton;#300;#Ngozi Fakeye;#307 | 2022-09-30 | Dependancies | 0

## PPP
Risk ID | Status | Programme | Risk Description | Risk or Issue | Likelihood | Impact | Risk Score | Project Manager | Date Reviewed | Date Raised | Workstream | Project | Mitigations | Mitigation Owner | Mitigation Due Date | Title | Score
DO5 | Closed | P&G | Due to the Civica reporting portal being in care and maintenance there is a issue that changes requested to improve or change the forms built will not be developed by Civica, resulting in a reporting portal that customers and the business find unsatisfactory but can’t be improved which will negatively impact customer perception of the Council and staff perception of internal services | Issue | 2 | 2 | 4 | Kate Hutchings | 2022-04-27 | 2022-01-05 |  | Public Protection Partnership | Plan and project to move to the next solution as quickly as possible as reviewing the overall Civica solution put in place for launch as soon as possible is on the roadmap | Nicholas Spencer;#23 |  | Care and maintenance | 0
DO6 | Closed | Place & Growth | Due to the Civica reporting portal not being optimised to be mobile responsive there is an issue that customers using the portal to report problems with have a unsatisfactory experience, resulting in bad experience for customers which will negatively impact their perception of the Council and an increase in using other methods to report problems (phone or other forms on the website that are mobile responsive but are not designed for public protection reporting, eg: Contact Us form) | Issue | 2 | 2 | 4 | Kate Hutchings | 2022-04-27 | 2022-01-05 |  | Public Protection Partnership | Plan and project to move to the next solution as quickly as possible as reviewing the overall Civica solution put in place for launch as soon as possible is on the roadmap | Glynn Davies;#31 |  | Mobile responsive | 0
DO7 | Closed | P&G | Due to the Civica reporting portal not complying with WCAG AA accessibility standards there is a risk that the reporting system for public protection will not be accessible to all customers to use, resulting in a digital channel that is not accessible to all, does not align to the Council’s equalities agenda and does not meet legal requirements which could lead to legal action against the Council | Risk | 2 | 2 | 4 | Kate Hutchings | 2022-04-27 | 2022-01-05 |  | Public Protection Partnership | Identify where the problems with WCAG AA accessibility are, work with Civica to fix these before launch, if Civica refuse change the risk to an issue and escalate / explore different solutions to deliver digital reporting forms for launch / use but amend accessibility statement with risk acknowledged at senior levels | Nicholas Spencer;#23 |  | Accessibility | 0
DO8 | Closed | Place & Growth | Due to the Service Area now requesting that 'reallocation' be switched on in the ALLONMOBILE system, there is a risk that Civica will need to redesign elements of the system which will need thorough retesting, resulting in another long delay to the go live. | Risk | 2 | 2 | 4 | Kate Hutchings | 2022-12-15 | 2022-10-03 |  | Public Protection Partnership | Meeting with Service Area on Thurs 6 Oct to encourage use of system without this functionality turned on for monitoring to see how large the problem is or not? | Simon Beasley;#24 |  | Scope | 0
DO9 | Yellow | Place & Growth | Due to the intermittent nature of the functionality working (and the need for training on the use of the system), there is a risk that the service will not accept the application into service, resulting in a waste of time, effort and money. | Risk | 3 | 2 | 6 | Kate Hutchings | 2023-02-08 | 2022-12-15 |  | Public Protection Partnership | Training undertaken (cost shared by IMT and E&S), and additional work by Civica undertaken. E&S accepted functionality into service as a trial on 30 January when the web links were turned on. Monitoring of activity by service and IMT with a further decision on 23 Feb (prior to web change freeze) as to whether to maintain web links or remove, based on officer and customer feedback. | Simon Beasley;#24 | 2023-02-23 | Scope / Schedule / Costs / Benefits | 0
PPP-R16 | Closed | P&G | Due to the delay in Civica releasing the portals for testing, there is a risk that not enough time will be left for testing and resolution of issues, resulting in a delay to the project. | Risk |  |  | 0 | Kate Hutchings | 2022-04-27 | 2022-02-09 |  | Public Protection Partnership | Escalate within Civica to arrange earlier release of portals (11 / 14 Feb) if possible. | Glynn Davies;#31 |  | Civica Portals | 0
PPP-R26 | Closed | P&G | Due to having two databases with migration in one and development in the other there is a risk that the testing won’t be end to end resulting in not all issues being picked up and resolved before go live. | Risk |  |  | 0 | Kate Hutchings | 2022-04-27 | 2022-02-22 |  | Public Protection Partnership | Civica assure WBC this is not an issue and is always set up in this way - there is no other way for this to be set up | Julie Teague;#138 |  | Databases | 0