## DI
Risk or Issue | Programme | Status | Project Manager | Risk ID | Date Raised | Date Reviewed | Project Title | Title | Additional Category | Risk Description | Likelihood | Impact | Risk Score | Mitigations | Mitigation Owner
Issue | CE | Closed | Joanne Veitch | DI-011 | 2022-01-21 | 2022-05-20 | Data and insight | Benefits | Implementation | There is a risk due to lack of engagement for success and future success (phase2) of the project - we need a robust communication plan and assistance in CLT/ECLT engagement -MG/WR/POE to explore . without this we will not be able to achieve our longer term goals | 2 - Likely | 1 - Low | 4 | Comms plan review and revision with Lisa M to include case study on how insight through powerbi use within their team has changed how they work and the benefits it has brought to coms team. | Joanne Veitch;#33
Terms of Reference for DIGG group (revised DIGG group )
Meeting with Key areas for permissions to access data and support for engagement and resource– finance/ HR/ASC/CS.
Amber status still due to DIGG and need to rollout more communication & SME engagement for Programme
POE/WR to discuss with Bus Change for guidance and assistance
DIGG challenged purpose of group with WR/POE and if the attendees are the right attendees.
Javeria is assigned back to project to help with Pillar 3 work and engagement
show and tell story boards and dashboards being prepared for eclt/clt
Issue | CE | Closed | Joanne Veitch | DI -011 | 2022-01-21 |  | Data and insight | Benefits | Quality | Rolled this one up into DI-o11Some engagement from existing KPI data owners is resistant to allow access to source data. They are also not willing to allow drill down and insight into the data. The project needs to look at ways to ensure all insight is available and access the source data where ever possible to do so (time cost) and seek aprpriate approvals . Whilst working with those resistant to get more buy in (show case how it can be a positive change)> | 2 - Likely | 2 - Medium |  | Within project activities for insight team to work alongside and also as part of the wider coms/ engagement need | Will Roper;#248
Issue | CEO | Closed | Joanne Veitch | DI-0027 | 2022-05-09 | 2022-05-20 | Data and insight | Benefits | Quality | CLT do not see the benefits of what we have built -corporate KPI dashboard. Therefore there is a risk that future D & I project resulting in DI phase 2 not being approved | 2 - Likely | 1 - Low | 6 | 20.5 closed - DI is seen as a requirement via powerbi to to aid savings of 18m and to provide oversight to CLT on our corporate priorities for delivery. It will be ran under one of the 6 - business intelligence | Will Roper;#248
Lessons learnt – dashboard of corporate KPI’s does not bring benefits to CLT in retrospect to sell to CLT we should have provided workforce or contracts dashboard.
Project should have had a review when CLT member for originally pushed the proposal (Keeley) left.
DIGG collection As is picture to help CLT understand current reporting and what DI project can do (benefits of automation) - lack of responses.
Digg to gather benefits for key priorities and work with their DLT to gain buy in and support - waiting updates.
Lewis B to include phase 2 into business intelligence program – external consultants to aid and CLT sponsor being agreed.
WR to Work with Rob Bradfield /simpsons with creation of contracts dashboard
Team to work with ASC/CS to supercharge them- better together and management reports
Other priority focus to be workforce and assets- await scoping

## PPP
Risk or Issue | Programme | Status | Project Manager | Risk ID | Date Raised | Date Reviewed | Project Title | Title | Additional Category | Risk Description | Likelihood | Impact | Risk Score | Mitigations | Mitigation Owner
Risk | P&G | Closed | Kate Hutchings | PPP-R15 | 2022-02-09 | 2022-03-07 | Public Protection Partnership | Westcot Annex |  | Due to the refurbishment of Westcot Annex not yet starting, there is a risk that this will impact on the IT implementation (internet, rack, etc), resulting in a delay to the project. | 2 - Likely | 2 - Medium | 4 | Contract to be awarded this week and visits to the annex organised to assess impact on IT. | Glynn Davies;#31
Risk | P&G | Closed | Kate Hutchings | PPP-R17 | 2022-02-09 | 2022-03-07 | Public Protection Partnership | Training |  | Due to the cost of training proposed by Civica, there is a risk that the new starters will not be trained before they start in their roles. | 1 - Unlikely | 1 - Low | 2 | Head of Service will organise internal / in house training prior to go live. | Glynn Davies;#31
2. Martin to allocate member of team to attend business requirement sessions with BA & IT Technical Lead in Jan 2021.
is a risk that the project will be delayed, resulting in keeping with the current product and running dual systems for longer period of time.
2. To resource a BA to document all reports, surveys, structure of Keystone for build of new northgate modules.
2. Daniel to find out if consultant is willing to travel to Shute End on Jan 25th to collect laptop
Risk | CE | Closed | Joanne Veitch | DI-007 | 2021-12-10 | 2022-05-30 | Data and insight | scope | Implementation | Legislation changes from Central Government may impact on project scope (KPI) and changes will need to be allowed via the agreed change process. | 3 - Very Likely | 1 - Low | 4 | Simpsons have been made aware legislation changes may change scope however it should not change the overall number of KPI's. Change process will be in place which will enable this to be proposed. JV meeting with Simpsons to discuss in more detail change process. | Joanne Veitch;#33
Issue | CE | Closed | Joanne Veitch | DI-003 | 2021-12-13 |  | Data and insight | Scope |  | There is an issue that we don’t choose the right directorate to progress first dashboard with ie preference with some is AS but AS are busy with Covid response work so would CS be better placed and we know they are keen to have this where as there is a reluctance in AS. Mosaic would be good initial feed to progress to warehouse as we have cleaned up data, we have permissions and access to data feeds now. | 2 - Likely | 2 - Medium | 4 | MG to discuss with Sally. | Mark Gwynne;#244
WR has made decision we prioritise CS as first dashboard.
Risk | CEO | Closed | Joanne Veitch | ID- 012 | 2022-01-27 | 2022-04-22 | Data and insight | Scope | Quality | There is a risk that due the lack of direct source access, around the amount of spread sheets used to provide the data for the KPI’s ,resulting in issues with the data's ability to automate through the feed due to format issues. Resulting in potential reduced benefits and less automation - Assumption was 66% automate from source, 33% spreadsheet). | 2 - Likely | 2 - Medium | 7 | Requested best practice for formats from simpsons | Joanne Veitch;#33
[10 empty] | How some of this data is stored and shared is also concerning. |  |  |  | Meeting with JT to discuss options for mitigations -
[10 empty] | Lack of systems in place in some areas to support the work being done and how manual it is. |  |  |  | - Volume and costing to get to more data from source
[10 empty] | The need for further work to be able to clean up data. |  |  |  | - sizing of issue (forward fix and historic fix) - resource needs
- Powerapp form so owners of KPI key in required figures we dont automate or improve the process
POE aware of governance issue (including share of data with 3rd parties not agreed with IT).
Contract changes to include request for direct access (cost may be hire or it may not be agreeable )
Can a 3rd party fill the lake on our behalf ie instead of sendinig a file they send via powerapp ?
Powerapp meeting arranged.
Accept and recognise that it is a journey to access our data direct and that the ratio of spread sheets will reduce over time,
Best practice for Excel files and automation of feeds underway and will be shared with Data owners and data teams.
Phase 2 of project will look to get more direct access to reduce the risk down
Issue | CE | Closed | Joanne Veitch | DI-013 | 2022-02-04 |  | Data and insight | scope |  | There is an issue re BWO to take current reports (view look) due to number of staff who can access and amend, which could mean failure for data to load and feed through resulting in KPI information not displaying. | 1 - Unlikely | 1 - Low | 3 | We are loading BWO source data into lake so we can build KPI's reports from source data rather than files | Will Roper;#248
This will work for HR
For Finance they do not update all information back into BWO as its forecast - we will load what they provide for phase 1 and look to improve in phase 2 when we look at building finance dashboards.
Risk | CE | Closed | Joanne Veitch | DI-014 | 2022-02-01 |  | Data and insight | scope |  | There is an issue due to our fire wall which is preventing some of the build work due to different azure environment set ups between current estate and data factory. (North Eurpore / UK south) | 1 - Unlikely | 2 - Medium | 6 | James Bull and Siva are working on a solution but not causing any issues for our project as workaround in place. | Siva Shankar;#145
Risk | CE | Closed | Joanne Veitch | DI-021 | 2022-03-21 | 2022-04-22 | Data and insight | Scope | Quality | There is a risk due to priorities and workloads (Ukraine/FYE/statutory reporting) that detailed requirements and sizing can not be undertaken against the business plan resulting in estimated costs which will need a tolerance applied. | 2 - Likely | 1 - Low | 8 | Work with Ruth to design a D &I model projection over 5 years as skills grow and more data feeds is accessible within the lake. | Joanne Veitch;#33
Review super A contract renew dates – ensure procurement allows
DIGG/SME’s corporate priority must haves and size with Data Team
Agree CLT priorities and must haves with CLT/Sponsor
Issue | CE | Closed | Joanne Veitch | DI-024 | 2022-04-14 | 2022-04-22 | Data and insight | Scope | Implementation |  | 2 - Likely | 2 - Medium | 15 | • WR to present to CLT and discuss with SW for greater clarification. | Joanne Veitch;#33
[10 empty] | There is an issue due to the Benefits for phase 2 business case we need CLT guidance / confirmation of the model, and the benefits to pursue (Data team head count reduction/ system savings, benefits to enable savings commercialisation project/ contract management/ joined up partnering automation of mandatory reporting).​ |  |  |  | WR waiting to discuss with Lewis - initial convo - more to be progressed
WR /MG to Discuss with SW
Working with Lewis on Business intelligence and phase 2 will form part of that if agreed as scope
2. The Project Lead SME has given details of another officer who in the team that has been given protected time to work on the project when the consultant is working (Tuesdays and Fridays) to review and assist with project related activities.
2. Cancel potential NEC Consultancy sessions.
3. Sponsor to agree MVP for go-live of modules so Energy module is implemented otherwise it will not be implemented.
4. PM to review all spend to date in finance system.
Carole to liaise with Heidi to check availability and schedule a date when the assets universe can be added to houlive ahead of project go-live.
Paula has been sent a list of requirements to be passed to Northgate (via Ginny) to ensure the migration is a success
This issue has been highlighted as a dependency to the Housing Leads
Risk | P&G | Closed | Kate Hutchings | D02 | 2021-11-02 | 2022-03-07 | Public Protection Partnership | Schedule |  | Due to the potential lack of support from West Berks for testing or technical solutions, there is a risk milestones will slip, resulting on an overall delay to the Programme implementation. | 2 - Likely | 2 - Medium | 4 | testing now complete | Glynn Davies;#31
Issue | CE | Closed | Joanne Veitch | DI -004 | 2021-12-09 |  | Data and insight | Schedule |  | Due to contracts not being finalised there is a risk that pre work will not be completed so work loads will be heavier in January to compensate due to christmas and new year holiday period. | 2 - Likely | 1 - Low | 2 | WR to push for contract to be completed by 13/12/21 to enable work to progress and be planned | Will Roper;#248
Issue | CE | Closed | Joanne Veitch | DI-006 | 2021-12-10 |  | Data and insight | schedule |  | Simpsons working assumption phase 1 finishes April 22 - they need to be aware that timeline for completion of phase 1 is Q2 (July) for scrutiny committee members and to adjust their project plan/ resource to this final approval - elections in May will not enable a shorter end date. | 2 - Likely | 1 - Low | 2 | Discussed with Simpsons kickoff meetings and adjustments will be made within their plan | Joanne Veitch;#33
Risk | CE | Closed | Joanne Veitch | DI - 008 | 2021-12-13 |  | Data and insight | Schedule | Reputation | There is a risk that resource will be impacted due to Omicron variant of Covid-19 – also that engagement with teams may be effected due to staff sickness and work priorities due to the variant. | 3 - Very Likely | 1 - Low | 3 | Contract with Simpsons includes clause for Covid response work to allow us to stop project. | Joanne Veitch;#33
Short term impacts of covid can be worked around and plan adjusted to support ie one directorate or resource sickness.
Risk | CE | Closed | Joanne Veitch | DI-010 | 2022-01-21 | 2022-05-06 | Data and insight | Schedule | Implementation | There was a risk due to lack of project management engagement by Simpson's to the project detail that the project was slipping behind and resource allocated to project to commence work would not be able to, due to the under resourcing vs build needs by Simpsons resulting in potential delays | 3 - Very Likely | 2 - Medium | 8 | Emergency planning meeting held with Simpson's PM | Joanne Veitch;#33
Resource timeline adjustment in place for Simpson's
Our resource to back fill Simpson's resource to keep discovery phase KPI workshops on track and aid data bank feeds.
Reformatted Morning stand ups
Meeting with Simpsons Account manager to discuss -WR
increased monitoring against simpsons deliverables
New resource on project but slippage on build and data feeds appears to be happening as resource only on project 2 day's a week and knowledge transfer is not happening - WR to discuss 7/3 with account manager
Risk | CE | Closed | Joanne Veitch | DI-016 | 2022-02-14 | 2022-05-20 | Data and insight | Schedule |  | There is a risk that PPP project may impact our resource availability due to the hard deadline of 31/3/22 for everything to be in place. Resource may need to be diverted if needs be as PPP project is the highest priority project within WBC. Which could result in delays to our build. | 2 - Likely | 2 - Medium | 12 | On going monitoring with PPP project | Simon Beasley;#24
Risk | CE | Closed | Joanne Veitch | DI- 017 | 2022-02-21 |  | Data and insight | Schedule |  | There is a risk that due to change in resource and the lack of requirements being passed over when resource changes that rework will be needed at each phase they share information with us. Resulting in Simpsons needing to commit more resource time than they currently have in plan to the project to deliver our build. | 2 - Likely | 2 - Medium | 10 | JV has drafted a requirement's document to aid simpsons, which the WBC team are reviewing - due to share with simpsons - 23/2. | Joanne Veitch;#33
Walk through of data lake rework required, - now complete 28/02.
Rework and change in resource effectively has pushed project back 2/3 weeks - being discussed 7/3 with account manager.
Risk | CE | Closed | Joanne Veitch | DI-019 | 2022-03-04 |  | Data and insight | Schedule |  | The Previous development consultant was working a minimum of 3 days a week to the project, the new consultant is only working 2 days a week - resulting in Simpsons project milestones not being realistic. | 3 - Very Likely | 1 - Low | 8 | Will be discussed by WR with account manager monday. | Will Roper;#248
WBC staff will back fill to keep overall plan on track once knowledge share is carried out which will help mitigate Simpsons Risks.
Risk | CE | Closed | Joanne Veitch | DI-020 | 2022-03-16 | 2022-05-20 | Data and insight | Schedule |  | There is risk due to our time lines for Phase 2 business case and strategy due to the Ukrainian refugee support as we accept them into borough - key resources are being diverted to support how we will support and aid the refugees as they come into the borough and this will impact some of our co producers / DIGG members availability and the amount they can contribute to the D & I - strategy and business case/actions . | 3 - Very Likely | 2 - Medium | 10 | We will evaluate the impact as we discuss the next steps with the DIGG members. | Joanne Veitch;#33
We will flag with Simpsons there is a potential risk to our project.
We will monitor impacts and report back
Risk | CE | Closed | Joanne Veitch | DI-025 | 2022-04-15 | 2022-05-30 | Data and insight | Schedule | Implementation | There is a risk to the project long term aims for data within the data lake as files are being locked down and adjusted to pass only information into the data lake relevant to a KPI rather than filling the lake to enable reporting of one truth via PowerBi phase 2 work | 2 - Likely | 1 - Low | 6 | • Digg agreement to security controls - need agreement | Joanne Veitch;#33
• Present to CLT security controls access proposal and workflow– need agreement
• Present to superusers / data teams security and access controls
• Give admin writes to data champions to manage access to data for IAO
On going advise to data teams on best practise - part of strategy, All files which were password protected needed for phase 1 are now resolved so closing risk
Risk | P&G | Closed | Kate Hutchings | PPP-R25 | 2022-02-22 | 2022-04-27 | Public Protection Partnership | Resources for testing data and document migration and the online forms portals and mobile solution |  | Due to the lack of resources in WBC and West Berkshire for testing there is a risk that the testing will not be sufficient and / or will miss something resulting in the go live being hampered by elements of the system that are untested or not working as they should. | 2 - Likely | 2 - Medium | 4 | Risk escalated to Head of Service | Glynn Davies;#31
Risk | CE | Closed | Joanne Veitch | DI-001 | 2021-11-26 | 2022-04-22 | Data and insight | Resource | Implementation | Due to size of project there is a risk due to lack of resource we will not be able to deliver and learn the skills necessary to deliver phase 1 . Additional resource is needed in the 4 key streams - data and insight team, infrastructure/ data team/ there is a risk we have in sufficient resource to support the project in the time frames required due to other projects and priorities (review of corporate plan). As the project is in start up there is a real risk that the time line will be stretched to enable all other works to progress, which will result in a stretched time line and we may not be able to deliver in the advised timeline the outputs (first dash boards) resulting in overall time frame delays to being insight driven, transparent council. | 3 - Very Likely | 2 - Medium |  | WR/MG to discuss with CLT work loads and get confirmation on priorities and timelines. JV to discuss resource with Simpsons and also get overview of other resource needs for project from SME;s JT/JB raised resource with GD/ POE raised with AM. | Mark Gwynne;#244
Risk | P&G | Closed | Kate Hutchings | DO3 | 2021-11-09 | 2022-03-07 | Public Protection Partnership | Dependencies |  | Due to the risk of having the PPP and Planning environments on the same server, there is a risk of interruption to service during upgrades, problem resolution, resulting in customer dissatisfaction | 1 - Unlikely | 1 - Low | 1 | Thinking through how to manage this with Supplier | Glynn Davies;#31
Risk | CE | Closed | Joanne Veitch | DI- 002 | 2021-11-26 | 2022-04-22 | Data and insight | Dependencies | Security | There is a issue to the project if BWO establishment is not accurate and maintained data security control will not be achievable with out recruitment of an administrator to control and protect access to our data. if Establishment is not maintained and accurate ongoing . Powerbi ideally will link to active directory which ideally will run off BWO and an accurate establishment. -access rights based on the establishment and roles within the establishment in BWO which will enable data to be seen based on current permissions within the business area.. The Establishment has been a continual challenge to maintain and be accurate, We will need to consider this and the impact on data and its security as we progress with the project/ through DIGG and with Finance for Budget to employ resource if necessary.. | 2 - Likely | 2 - Medium |  | Meeting with Jacqui B - BWO Project manager to discuss establishment and plans regarding its accuracy and on going maintenance and management to gage impact | Jacqui Benton;#162
Risk | P&G | Closed | Kate Hutchings | PPP-R14 | 2022-02-09 | 2022-03-07 | Public Protection Partnership | Data migration |  | Due to the data extract having to be re-run by West Berks, there is a risk that the document checking will be delayed, adding additional time to the testing plans. | 1 - Unlikely | 2 - Medium | 3 | Documents have been re-run (5 Feb) and the size is acceptable for the SFTP server. This will mean that only a smaller ‘delta’ needs to be run at the point of go live week, mitigating risk with the data / documents. | Glynn Davies;#31