## Sheet1
Action | Who | End Date | Status | Notes
Review go live date with Ed | Kate | 2022-08-03 | Complete
Review go live plan with Civica | Kate Civica | 2022-08-04 | Complete | Consider any oustanding actions
Ensure document size for upload increased to 10 mb | Kate Civica | 2022-08-04 | in progress
Agree go live date with Nick Head of Digital | Kate | 2022-08-08 | Complete
Agree go live date at IMT Change Board | Kate | 2022-08-09 | Complete
Brief E&S team on elements of training for portal and allonmobile | Ed Gina | 2022-08-12 | Complete
Ensure access to network for Civica | Infrastructure | 12 Aug to 26 Aug | Complete
Civica make changes for go live | Civica | 2022-08-15
Undertake testing on live system | Ed Gina | 15 Aug to 17 Aug | Complete
Monitor Civica IT portal for problems | Infrastructure | 15 Aug to 22 Aug | Complete
Attend E&S management team meeting | Kate | 16 Aug and 22 Aug | Complete
Web team make links live on web site | Harry | 2022-08-18
Monitor customer service requests | Ed Gina | 18 to 22 Aug | Complete
Initial review of service requests / issues | Kate Gina | 2022-08-22 | Complete
Web team remove links on web site | Harry | 22 Aug or 31 Aug |  | if necessary due to problems arising from customer service requests
Further review of service requests / issues two weeks from go live | Kate Ed | 2022-08-31 | Complete
Annual leave employee 1 |  | 22 to 26 Aug | Complete
Annual leave employee 2 |  | 25 Aug to 5 Sept | Complete