## 44700153
Inspections In Date Order - Latest First
| Road Name: |  |  | 44700153 - Binfield Road - Binfield, 44700153
|  | Date Due: 01/04/2023 00:00:00 |  |  | Date Completed: 24/03/2023 11:06:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 7 (3 Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: No |  |  | Inspection Comments: 2 x 28 day defect raised D2233959 D2233956 ( Stuart 2 hr D2233953) Enquiry sent to Highways Assets W2349231/ W2249229
|  | Date Due: 01/01/2023 00:00:00 |  |  | Date Completed: 12/12/2022 14:14:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 7 (3 Monthly) |  |  | Surface Condition: SNOW
|  | Defects Found: Yes |  |  | Inspection Comments: ?
|  | Date Due: 01/10/2022 00:00:00 |  |  | Date Completed: 16/09/2022 11:20:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 7 (3 Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: Yes |  |  | Inspection Comments: ?
|  | Date Due: 01/07/2022 00:00:00 |  |  | Date Completed: 21/06/2022 12:40:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 7 (3 Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: Yes |  |  | Inspection Comments: W2238110
|  | Date Due: 07/04/2022 00:00:00 |  |  | Date Completed: 31/03/2022 13:51:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 7 (3 Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: No |  |  | Inspection Comments: Highways Assets advised of off edge of carriageway defects. Noticable differences in levels between verge and carriageway present Consideration for remedy requested
Defects In Date Order - Latest First
| Road Name: |  |  | 44700153 - Binfield Road - Binfield, 44700153
|  | Defect Number : D2126236 |  |  |  | Source:
|  | Date Raised:10/03/2022 09:37:00 |  |  |  | Date Completed:10/03/2022 13:45:57
|  | Location: |  |  |  | Priority : 2 Hour - Emergency
Description: Pallets etc in road. Can we please claer
|  | Defect Number : D2126795 |  |  |  | Source:
|  | Date Raised:31/03/2022 12:21:00 |  |  |  | Date Completed:08/04/2022 12:10:07
|  | Location: Opposite top gate of Stokes Cottage |  |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 Repair DBM carriageway defect - damaged gully and surrounding carriageway structure Located to nearside of carriageway Width of carriageway 5.0m National Speed Limit 60mph On approach to right hand bend No footway present Traffic count low to medium Two way TM / Closure may be required
|  | Defect Number : D2227618 |  |  |  | Source:
|  | Date Raised:01/05/2022 17:10:00 |  |  |  | Date Completed:04/05/2022 09:16:54
|  | Location: ? |  |  |  | Priority : 3 Days
Description: Carpets and chairs
|  | Defect Number : D2228340 |  |  |  | Source:
|  | Date Raised:07/06/2022 11:22:00 |  |  |  | Date Completed:27/06/2022 10:10:00
|  | Location: Binfield Road |  |  |  | Priority : 3 Days
Description: Armchair
|  | Defect Number : D2230600 |  |  |  | Source:
|  | Date Raised:27/10/2022 17:36:00 |  |  |  | Date Completed:31/10/2022 11:08:00
|  | Location: Binfield Road in ditch on side of road, 100 mtrs after Manor Farm House. What 3 words effort.picked.burn |  |  |  | Priority : 3 Days
Description: 7 x Black refuse bags. 5 contain chip board, electrical lighting, building sand. 1 with a type of pressure cleaner and 1 with grass cuttings. Also a microwave and cardboard box.
|  | Defect Number : D2231934 |  |  |  | Source:
|  | Date Raised:10/01/2023 11:39:00 |  |  |  | Date Completed:11/01/2023 14:07:00
|  | Location: Binfield Road, Binfield. |  |  |  | Priority : 3 Days
Description: Comments from reporter as below; "There are 4 large bags of fresh butchery bones at intervals on Binfield Rd First bag is at the junction of Forest Rd B3034, on west side of road, 2 near bridge on bend and one outside Stokes Farm"
|  | Defect Number : D2232451 |  |  |  | Source:
|  | Date Raised:25/01/2023 13:40:00 |  |  |  | Date Completed:07/02/2023 10:37:00
|  | Location: Binfield Road, Wokingham 50 yards after Mowers and More machinery |  |  |  | Priority : 3 Days
Description: 7 x blue bags full of bricks and stone
|  | Defect Number : D2233484 |  |  |  | Source: Inspection Area 3
|  | Date Raised:09/03/2023 13:45:00 |  |  |  | Date Completed:05/04/2023 22:00:00
|  | Location: A329m Bravo between Mile marker 7/5 & 7/4. Towards Winnersh turn off. |  |  |  | Priority : 24 Hours - Urgent
Description: L3 S3 CAT 1B. **A329m** Enquiry from member of public. 1 of 3 at this location, TM set up. Please make safe cway pothole, not marked, see photos. On centre line on Lane 1 and 2. Will need Traffic Management. Road Speed: 70MPH Approx Road Width: 8M Approx Traffic Flow: HIGH Approx HGV / Bus Traffic Flow: HIGH Approx pedestrian volume along Footways: nil Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: no Other hazard: TM recommended YES.
|  | Defect Number : D2233953 |  |  |  | Source:
|  | Date Raised:24/03/2023 08:40:00 |  |  |  | Date Completed:24/03/2023 11:17:43
|  | Location: Binfield Rd, by entrance to Stokes Farm. |  |  |  | Priority : 2 Hour - Emergency
Description: L4 S4 cat 1a. Please make safe edge of cway damage marked. 3 x cones left at edge of cway. Please remove after make safe. Place Advance signs well back on bends. Road Speed: National Speed Limit Approx Road Width: 5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: medium Approx pedestrian volume along Footways: low Near Bend: yes Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: no Other hazard: TM recommended yes
|  | Defect Number : D2233956 |  |  |  | Source:
|  | Date Raised:24/03/2023 09:25:00 |  |  |  | Date Completed:01/01/9999 00:00:00
|  | Location: Approx 50yrds from Forest Road junction |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx 1.5sq mtr ( 3mth inspection) Road Speed: National speed limit Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume along Low Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: No Other hazard: temp Road closure 28th March ( see detail in attached) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2233959 |  |  |  | Source:
|  | Date Raised:24/03/2023 09:32:00 |  |  |  | Date Completed:01/01/9999 00:00:00
|  | Location: Approx 10yrds from Junction with Forest Road |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx 2sq mtr ( 3mth inspection) Road Speed: National speed limit Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume along Low Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: No Other hazard: temp Road closure 28th March ( see detail in attached) TM recommended: May require 2 way temp traffic lights
Enquiries In Date Order - Latest First
| Road Name: |  |  | 44700153 - Binfield Road - Binfield, 44700153
|  | Enquiry Number: W2235018 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 31/03/2022 13:51:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Length of carriageway at various locations
Description: Please forward for the attention of Highways Assets Noted as part of driven 3mth inspection 31.03.2022 - SN As with many of this borough's rural type DBM carriageways with a National Speed Limit of 60mph, a width of 5.0m and with no footway present, multiple area's to the edge of carriageway where there is a noticable difference in level between the back of carriageway edge and the adjoining soft verge/hedgerows are apparent. This difference in levels is caused by those vehicles who pull over to the extreme nearside and off the edge of carriageway to facilitate the passing of larger oncoming vehicles and as a result the compressed non metalled verged surface is considerably lower than the abutting carriageway. Traffic count medium Further investigation/consideration for possible remedy required
Recomended Action:
|  | Enquiry Number: W2236199 |  |  |  | Assigned CSO:
|  | Date Raised: 30/04/2022 16:31:00 |  |  |  | Date Completed: 04/05/2022 09:16:54
Location: ?
Description: There are bags, some chairs and other waste.
Recomended Action:
|  | Enquiry Number: W2236636 |  |  |  | Assigned CSO:
|  | Date Raised: 12/05/2022 13:25:00 |  |  |  | Date Completed: 13/05/2022 08:32:00
Location: Car park of keephatch meadows close to the pedestrian entrance to the meadow
Description: Disgusting slimy builders waste which I have just slipped over on, hurting my hands, knees and ankle! These car parks are meant to be Maintained! I will be putting In for a compensation claim !
Recomended Action:
|  | Enquiry Number: W2237409 |  |  |  | Assigned CSO: Antisocial behaviour Team
|  | Date Raised: 01/06/2022 21:50:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Along the Binfield Rd, sorry not sure exact location but by a public pathway leading to farmer fields (on Wokingham side of the road, as opposed to Bracknell side)
Description: Single sofa dumped with other household waste
Recomended Action:
|  | Enquiry Number: W2238110 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 21/06/2022 11:26:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: End of Binfield Road heading into Forest Road
Description: Please send to Highways Assets as part of Highways Inspection SH Please repaint faded white lines at Junction
Recomended Action:
|  | Enquiry Number: W2240854 |  |  |  | Assigned CSO: Tree Management
|  | Date Raised: 07/09/2022 07:54:00 |  |  |  | Date Completed: 09/09/2022 16:04:00
Location: Where Binfield Road meets Forest Road
Description: Big branch on left side of road when joining Forest Road
Recomended Action:
|  | Enquiry Number: W2241222 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 16/09/2022 10:20:00 |  |  |  | Date Completed: 07/02/2023 09:31:00
Location: Binfield Rd just past Road Bridge over A329m, heading North towards Forest Road.
Description: Please forward to Highways Assets. As part of Highways inspection found large area of cway degradation. Would need to be assessed for dimension of any remedial works. SB
Recomended Action:
|  | Enquiry Number: W2241224 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 16/09/2022 10:26:00 |  |  |  | Date Completed: 22/11/2022 10:17:00
Location: Binfield Rd between entrance to Stokes Farm and public car park.
Description: Please forward to Highways Assets. As part of Highways inspection found cway markings faded for 30mph. SB.
Recomended Action:
|  | Enquiry Number: W2242636 |  |  |  | Assigned CSO:
|  | Date Raised: 26/10/2022 21:05:00 |  |  |  | Date Completed: 31/10/2022 11:08:00
Location: ?
Description: In ditch at side of road What 3 words: effort.picked.burn
Recomended Action:
|  | Enquiry Number: W2345440 |  |  |  | Assigned CSO:
|  | Date Raised: 10/01/2023 11:21:00 |  |  |  | Date Completed: 11/01/2023 14:07:00
Location: See above
Description: There are 4 large bags of fresh butchery bones at intervals on Binfield Rd First bag is at the junction of Forest Rd B3034, on west side of road, 2 near bridge on bend and one outside Stokes Farm
Recomended Action:
|  | Enquiry Number: W2345464 |  |  |  | Assigned CSO:
|  | Date Raised: 10/01/2023 14:55:00 |  |  |  | Date Completed: 10/01/2023 15:14:00
Location: Starts from the entrance to Binfield Road off Forest Road all the way up to Stokes Farm barn. Multiple bags full but less than a car boot.
Description: There is bags of carcass's from the pin all the way up the road to Stokes farm.
Recomended Action:
|  | Enquiry Number: W2346628 |  |  |  | Assigned CSO:
|  | Date Raised: 30/01/2023 14:30:00 |  |  |  | Date Completed: 13/02/2023 12:58:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2349229 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 24/03/2023 09:06:00 |  |  |  | Date Completed: 11/04/2023 10:56:00
Location: Left hand side of carrigeway between Stokes Farm & Stokes cottage
Description: Please send to Highways Assets as part of 3mth Highways Inspection SH There is a section of grass verge that has worn away from the carrigeway over 5 sq mtr.
Recomended Action:
|  | Enquiry Number: W2349231 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 24/03/2023 09:17:00 |  |  |  | Date Completed: 24/03/2023 09:17:34
Location: At Junction with Forest Road
Description: Please send to Highways Assets as part of 3mth Highways Inspection SH &#10;&#10;Please add to program for repainting of faded white road markings
Recomended Action:
Orders In Date Order - Latest First
| Road Name: |  |  | 44700153 - Binfield Road - Binfield, 44700153
|  | Order Number: ORD2200822 |  |  |  | Originator:
|  | Date Raised: 27/04/2022 11:44:26 |  |  |  | Date Completed: 22/07/2022 09:07:44
|  | Location: 44700153 - BINFIELD ROAD - BINFIELD |  |  |  | Date Instructed: 27/04/2022 11:46:24
|  | Description: Remove all vegetation from the deck, parapet posts & sweep or jet clean the deck. As applicable & required: clear debris from abutment bearing shelves, drainage channels & rod drainage outlet pipes, clean & grease up (corrosion inhibiting product) steel bridge bearings.) Jet clean all parapets. Check sturdiness of parapet assembly & if required adjust/replace any missing fixings to achieve a sturdy fit. Remove any obstructions to the water flow, e.g. branches within the invert or trapped against pier supports. Dispose of debris. Provide Job data sheet and date stamped photographic evidence of effective work completion (2-3 image files), ideally the images to be pre/post completion of works. Report any defect encountered on site during RM activities that require further action: e.g. pot holes, missing or damaged expansion joints or sealants, impact damage, any minor remedial works etc. |  |  |  | Priority: 338 Days
|  | V18 | 28/06/2023 08:04:09
Page 9 of 9