## 44700154
Inspections In Date Order - Latest First
| Road Name: |  |  | 44700154 - Binfield Road - Wokingham, 44700154
|  | Date Due: 01/04/2023 00:00:00 |  |  | Date Completed: 24/03/2023 11:28:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 7 (3 Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: Yes |  |  | Inspection Comments: Customer Enquiry W2348891
|  | Date Due: 01/01/2023 00:00:00 |  |  | Date Completed: 12/12/2022 14:14:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 7 (3 Monthly) |  |  | Surface Condition: SNOW
|  | Defects Found: Yes |  |  | Inspection Comments: ?
|  | Date Due: 09/01/2023 00:00:00 |  |  | Date Completed: 06/12/2022 09:47:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Walked Route 99 (12 Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: Yes |  |  | Inspection Comments: Report sent to HA - crack on carrigeway at Bridge
|  | Date Due: 01/10/2022 00:00:00 |  |  | Date Completed: 16/09/2022 11:21:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 7 (3 Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: Yes |  |  | Inspection Comments: ?
|  | Date Due: 01/07/2022 00:00:00 |  |  | Date Completed: 21/06/2022 12:42:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 7 (3 Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: Yes |  |  | Inspection Comments: ?
|  | Date Due: 07/04/2022 00:00:00 |  |  | Date Completed: 01/04/2022 14:14:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 7 (3 Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: No |  |  | Inspection Comments: ?
Defects In Date Order - Latest First
| Road Name: |  |  | 44700154 - Binfield Road - Wokingham, 44700154
|  | Defect Number : D2125325 |  |  |  | Source:
|  | Date Raised:02/02/2022 11:05:00 |  |  |  | Date Completed:03/02/2022 08:20:48
|  | Location: Marked opposite number 2 |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe pothole marked opposite 2 (Pip-a-den) on carriageway Road Speed: 30MPH Approx Road Width: 6.0M. Approx Traffic Flow: med, depending on time of day. Approx HGV / Bus Traffic Flow: med Footways: yes Near Bend: Yes Near Pedestrian Crossing: Yes Near Traffic Signals: Yes Near Junction: Yes Near School: Yes Near Roundabout: No
|  | Defect Number : D2125326 |  |  |  | Source:
|  | Date Raised:02/02/2022 11:09:00 |  |  |  | Date Completed:03/02/2022 08:16:16
|  | Location: Marked opposite 43 outside number 4 |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe pothole marked opposite 43(Maret) on carriageway Road Speed: 30MPH Approx Road Width: 6.0M. Approx Traffic Flow: med, depending on time of day. Approx HGV / Bus Traffic Flow: med Footways: yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: Yes Near Roundabout: No
|  | Defect Number : D2125654 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:10:00 |  |  |  | Date Completed:21/02/2022 13:05:30
|  | Location: Directly outside number 2. |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125656 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:15:00 |  |  |  | Date Completed:22/02/2022 13:58:53
|  | Location: Directly outside number 2A |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125657 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:20:00 |  |  |  | Date Completed:22/02/2022 13:58:09
|  | Location: Directly outside number 2A |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125658 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:23:00 |  |  |  | Date Completed:22/02/2022 13:59:18
|  | Location: Directly outside number 2A |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125659 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:25:00 |  |  |  | Date Completed:22/02/2022 13:59:46
|  | Location: Directly outside number 2A |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 (pothole number 5) Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125660 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:26:00 |  |  |  | Date Completed:22/02/2022 14:00:34
|  | Location: Directly outside number 2A |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 ( PH number 6) Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125661 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:28:00 |  |  |  | Date Completed:22/02/2022 14:00:11
|  | Location: Directly outside number 2A |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 ( PH number 7 ) Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125662 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:30:00 |  |  |  | Date Completed:22/02/2022 14:01:01
|  | Location: Directly outside number 2A |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 ( PH8) Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125663 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:31:00 |  |  |  | Date Completed:22/02/2022 14:02:01
|  | Location: Directly outside number 2B |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 ( PH NUMBER 9) Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125664 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:33:00 |  |  |  | Date Completed:22/02/2022 14:01:33
|  | Location: Directly outside number 2B |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 (PH NUMBER 10) Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125665 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:34:00 |  |  |  | Date Completed:22/02/2022 14:02:29
|  | Location: Directly outside number 2C |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 (PH NUMBER 11) Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125667 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:36:00 |  |  |  | Date Completed:22/02/2022 14:06:58
|  | Location: Directly outside number 2C |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 ( PH number 12 ) Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125668 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:37:00 |  |  |  | Date Completed:22/02/2022 14:02:59
|  | Location: Directly outside number 2C |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125669 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:39:00 |  |  |  | Date Completed:22/02/2022 14:08:27
|  | Location: Directly outside number 2C |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125670 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:40:00 |  |  |  | Date Completed:22/02/2022 14:07:37
|  | Location: Directly outside number 4 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125672 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:41:00 |  |  |  | Date Completed:22/02/2022 14:07:59
|  | Location: Directly outside number 4 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125673 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:42:00 |  |  |  | Date Completed:22/02/2022 14:09:16
|  | Location: Directly outside number 4 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125674 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:43:00 |  |  |  | Date Completed:22/02/2022 14:08:52
|  | Location: Directly outside number 4 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125675 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:44:00 |  |  |  | Date Completed:22/02/2022 14:09:39
|  | Location: Directly outside number 6 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125676 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:46:00 |  |  |  | Date Completed:22/02/2022 14:10:00
|  | Location: Directly outside number 10 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125677 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:47:00 |  |  |  | Date Completed:22/02/2022 14:10:32
|  | Location: Directly outside number 10 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125678 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:48:00 |  |  |  | Date Completed:22/02/2022 14:13:23
|  | Location: Directly opposite number 47 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: No TM required: if Needed
|  | Defect Number : D2125679 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:50:00 |  |  |  | Date Completed:25/02/2022 09:01:32
|  | Location: Directly outside number 47 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125681 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:51:00 |  |  |  | Date Completed:22/02/2022 14:12:12
|  | Location: Directly opposite number 47 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125682 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:52:00 |  |  |  | Date Completed:22/02/2022 14:14:17
|  | Location: Directly opposite number 49 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125683 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:53:00 |  |  |  | Date Completed:22/02/2022 14:11:32
|  | Location: Directly opposite number 49 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125684 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:54:00 |  |  |  | Date Completed:22/02/2022 14:15:50
|  | Location: Directly opposite number 49 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125685 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:55:00 |  |  |  | Date Completed:22/02/2022 14:15:17
|  | Location: Directly opposite number 49 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2125686 |  |  |  | Source:
|  | Date Raised:17/02/2022 13:56:00 |  |  |  | Date Completed:22/02/2022 14:14:47
|  | Location: Directly opposite number 51 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L12 (total of 26 Ph ) Local school, cars are forced into the centre of the carriageway with cyclists. Please make safe pothole in the middle of the carriageway. Road Speed: 30 MPH Approx Road width: 6.0M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: Yes Near Roundabout:No Other Hazards: footway one side TM required: if Needed
|  | Defect Number : D2126238 |  |  |  | Source:
|  | Date Raised:10/03/2022 10:17:55 |  |  |  | Date Completed:10/03/2022 13:15:00
|  | Location: has just reported possible hazardous material which has fallen out of a lorry and in the middle of the road in Binfield road Wokingham RG40 5PR, I asked for the exact location and she said if you come from the Binfield side you'll see it a lot quicker, she would clear it herself but said it looks like it is hazardous?. Should you need her telephone number it's . |  |  |  | Priority : N/A
Description: Please clear hazardous material on road.
|  | Defect Number : D2226837 |  |  |  | Source:
|  | Date Raised:02/04/2022 21:44:00 |  |  |  | Date Completed:06/04/2022 08:22:53
|  | Location: As per map |  |  |  | Priority : 3 Days
Description: Sounds like a mattress
|  | Defect Number : D2228153 |  |  |  | Source:
|  | Date Raised:26/05/2022 13:42:00 |  |  |  | Date Completed:21/11/2022 10:00:00
|  | Location: By Lamp No.39 |  |  |  | Priority : 28 Days - Standard Response
Description: 1 of 2, Please patch in CW where marked. Size: 1.1 x 1.2 Material: HRA Recommended TM: two way lights. Road Speed: 30MPH Approx Road Width:5M. Approx Traffic Flow: low, depending on time of day. Approx HGV / Bus Traffic Flow: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: Yes, approx 30m away.
|  | Defect Number : D2228155 |  |  |  | Source:
|  | Date Raised:26/05/2022 13:51:00 |  |  |  | Date Completed:21/11/2022 10:00:00
|  | Location: By Lamp 39 |  |  |  | Priority : 28 Days - Standard Response
Description: 2 of 2, Please patch in CW where marked. FYI, this is repairing an old patch within an area of anti skid. Size: 1.6 x 3.7 Material: HRA Recommended TM: two way lights. Road Speed: 30MPH Approx Road Width:5M. Approx Traffic Flow: low, depending on time of day. Approx HGV / Bus Traffic Flow: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: Yes, approx 30m away.
|  | Defect Number : D2229510 |  |  |  | Source:
|  | Date Raised:18/08/2022 11:07:00 |  |  |  | Date Completed:18/08/2022 12:42:00
|  | Location: Binfield Road Behind the seat and bin between Barrett crescent and Binfield Road |  |  |  | Priority : 3 Days
Description: TV flat screen
|  | Defect Number : D2230635 |  |  |  | Source:
|  | Date Raised:31/10/2022 11:20:31 |  |  |  | Date Completed:31/10/2022 13:15:00
|  | Location: Lamp Column 030 R/o 25 De-Vitre Grn 65m west of Plough L Asset Id:25460 |  |  |  | Priority : 2 Hour - Emergency
Description: Reports for TVP that columns 30/31 have been involved in RTA - 2 hour emergency attendance required. reported this on 31.10.22 - JB called MD on 31.10.22 @11.20 2 x streetlamp posts. Number 30 and 31. Completely taken out! 5/6 plastic bollards (black and white reflective) Col 30 rta, new 6m ali column required Col 31 rta, new col and new Vmax lantern required. 31/10/2022
|  | Defect Number : D2231367 |  |  |  | Source:
|  | Date Raised:07/12/2022 10:40:00 |  |  |  | Date Completed:03/04/2023 09:15:00
|  | Location: Binfield Rd junction with Barrett Crescent, Wokingham. |  |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. Please carry out permanent reinstatement to cway marked. 2 0 x 1.5 HRA. Will need 3 way temp lights on Junction. Will need Bus stop suspension. Off peak or School holiday working. Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: medium, high at peak times. Approx HGV / Bus Traffic Flow: medium. Approx pedestrian volume along Footways: low, higher at school times. Near Bend: no Near Pedestrian Crossing: yes Near Traffic Signals: no Near Junction: yes Near School: yes Near Roundabout: no Other hazard: Avoid peak hours TM recommended yes
|  | Defect Number : D2231435 |  |  |  | Source:
|  | Date Raised:12/12/2022 14:03:00 |  |  |  | Date Completed:03/04/2023 09:45:00
|  | Location: Outside Bean Oak Barn, Binfield Rd. Near Junction with Plough Lane. |  |  |  | Priority : 2 Hour - Emergency
Description: L2 S2 CAT2A. Please carry out permanent reinstatement to cway marked. 4.5 x 1.0 10mm SMA. Will require minimum of 2 way temp lights, possibly 3 way as next Junction is 25m from site. Edge of cway. 3.8M Road space left. Road Speed: believe to be National Speed Limit. Approx Road Width: 5M Approx Traffic Flow: medium, high at peak times. Approx HGV / Bus Traffic Flow: medium. Approx pedestrian volume along Footways: no fway. Near Bend: yes. Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: Avoid peak hours. Overhead cables. TM recommended yes
|  | Defect Number : D2231759 |  |  |  | Source:
|  | Date Raised:05/01/2023 08:59:01 |  |  |  | Date Completed:06/01/2023 09:09:59
|  | Location: North of Keep Hatch Meadows. 7 Potholes Marked. please fix with Via-Fix. 5 potholes are along the centre line 2 are in the centre of the lane. |  |  |  | Priority : 24 Hours - Urgent
Description: Raised on behalf of MG (HA) by VH
|  | Defect Number : D2232022 |  |  |  | Source: Inspection Area 3
|  | Date Raised:13/01/2023 10:15:00 |  |  |  | Date Completed:16/01/2023 12:46:53
|  | Location: Next to Bean Oak Farm. Approx 20M from JN with Plough Lane. |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe where marked in CW. Road Speed: 30MPH Approx Road Width: 5.0M. Approx Traffic Flow: Med, depending on time of day. Approx HGV / Bus Traffic Flow: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: No
|  | Defect Number : D2233016 |  |  |  | Source:
|  | Date Raised:16/02/2023 09:47:00 |  |  |  | Date Completed:17/02/2023 08:29:43
|  | Location: Binfield Road, from workingham towards bracknell. On the bridge over the A329 |  |  |  | Priority : 24 Hours - Urgent
Description: Please place a temporary Road sign for UNEVEN ROAD to be placed on Binfield Road, from workingham towards bracknell. On the bridge over the A329
|  | Defect Number : D2233172 |  |  |  | Source:
|  | Date Raised:24/02/2023 08:00:00 |  |  |  | Date Completed:06/03/2023 07:30:00
|  | Location: Binfield Road from Carina Drive to Oak Avenue and Diamond Jubilee Way roundabout. In the past Binfield Road driving towards Stokes Farm is also missed regularly. |  |  |  | Priority : Planned Maintenance
Description: Binfield Road from Carina Drive to Oak Avenue and Diamond Jubilee Way roundabout. In the past Binfield Road driving towards Stokes Farm is also missed regularly.
|  | Defect Number : D2233408 |  |  |  | Source:
|  | Date Raised:06/03/2023 11:41:00 |  |  |  | Date Completed:07/03/2023 11:00:00
|  | Location: ? |  |  |  | Priority : Planned Maintenance
Description: Please sweep Binfield Road on next scheduled date
|  | Defect Number : D2233409 |  |  |  | Source: Inspection Area 3
|  | Date Raised:06/03/2023 12:48:00 |  |  |  | Date Completed:07/03/2023 09:10:35
|  | Location: Outside 2 / 2a Binfield Rd. Wokingham. |  |  |  | Priority : 24 Hours - Urgent
Description: L3 S3 cat 1b. Please make safe cway pothole, marked. 50m from junction with London Rd. May require Stop Go, off peak. Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: medium Approx pedestrian volume along Footways: medium Near Bend: no Near Pedestrian Crossing: yes Near Traffic Signals: yes Near Junction: yes Near School: yes Near Roundabout: no Other hazard: Avoid peak hours. VXOs both sides. TM recommended yes.
|  | Defect Number : D2233659 |  |  |  | Source:
|  | Date Raised:15/03/2023 11:23:00 |  |  |  | Date Completed:22/03/2023 09:25:39
|  | Location: On Carina drive with Binfield Road. |  |  |  | Priority : 24 Hours - Urgent
Description: Please remove obstruction on Highway. On the grass verge. On Carina drive with Binfield Road. Road Speed: 30MPH Approx Road Width: 6.0M. Approx Traffic Flow: low, depending on time of day. Approx HGV / Bus Traffic Flow: low Footways: yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: yes Near School: No Near Roundabout: yes
|  | Defect Number : D2233974 |  |  |  | Source:
|  | Date Raised:24/03/2023 11:21:00 |  |  |  | Date Completed:01/01/9999 00:00:00
|  | Location: On Roundabout joining Binfield Road/ Oak Avenue |  |  |  | Priority : 28 Days - Standard Response
Description: 24/3/23 - CANCEL THIS JOB? This sign hasn't been adopted yet and is still the developers responsibility to maintan. Details passed to Highway Agreements Team to pass to the developer. - DH S2 L2 Please fit post onto verge area and refit 1 x chevron ( enquiry sent to Streetlighting (W2349044) may require new brackets? Road Speed: 40MPH Approx Road Width: 6M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: Yes Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: Yes Other hazard: Main route for industrial area TM recommended: Signing & Guarding ( parking limited due to location)
|  | Defect Number : D2233977 |  |  |  | Source: Inspection Area 3
|  | Date Raised:24/03/2023 11:59:00 |  |  |  | Date Completed:03/04/2023 10:15:00
|  | Location: Approx 100yrds from Carina Drive at start of Anti Skid surface |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required HRA approx 1sq mtr ( 3mth inspection) Road Speed: 40MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume along Low Footways: partial Near Bend: Yes Near Pedestrian Crossing: Yes Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: Yes Other hazard: PROW TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2233984 |  |  |  | Source:
|  | Date Raised:24/03/2023 12:49:00 |  |  |  | Date Completed:03/04/2023 10:45:00
|  | Location: Junction with Keephatch Road |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required mixed material less than 1sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: Yes Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: Yes Other hazard: PROW TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2233999 |  |  |  | Source:
|  | Date Raised:24/03/2023 13:59:00 |  |  |  | Date Completed:16/04/2023 11:00:00
|  | Location: Outside number 2B |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM less than 1sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Bus stop ( Reading) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2234000 |  |  |  | Source:
|  | Date Raised:24/03/2023 14:06:00 |  |  |  | Date Completed:03/04/2023 11:15:00
|  | Location: Outside number 2B |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx 1sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Bus stop ( Reading) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2234002 |  |  |  | Source:
|  | Date Raised:24/03/2023 14:08:00 |  |  |  | Date Completed:03/04/2023 11:30:00
|  | Location: Outside number 2B |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx 1.5sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Bus stop ( Reading) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2234003 |  |  |  | Source:
|  | Date Raised:24/03/2023 14:12:00 |  |  |  | Date Completed:03/04/2023 11:45:00
|  | Location: Outside number 2b/ 2c |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx less than 1sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Bus stop ( Reading) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2234004 |  |  |  | Source:
|  | Date Raised:24/03/2023 14:14:00 |  |  |  | Date Completed:03/04/2023 12:15:00
|  | Location: Outside number 2b/2c |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx less than 1sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Bus stop ( Reading) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2234005 |  |  |  | Source:
|  | Date Raised:24/03/2023 14:16:00 |  |  |  | Date Completed:03/04/2023 12:30:00
|  | Location: Outside number 2B/2C |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx 1sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Bus stop ( Reading) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2234006 |  |  |  | Source:
|  | Date Raised:24/03/2023 14:17:00 |  |  |  | Date Completed:03/04/2023 12:45:00
|  | Location: Outside number 2c |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx 1sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Bus stop ( Reading) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2234007 |  |  |  | Source:
|  | Date Raised:24/03/2023 14:20:00 |  |  |  | Date Completed:03/04/2023 13:00:00
|  | Location: Opposite house name # Maret# |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx 2sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Bus stop ( Reading) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2234008 |  |  |  | Source:
|  | Date Raised:24/03/2023 14:22:00 |  |  |  | Date Completed:03/04/2023 13:30:00
|  | Location: Outside house name # Maret # |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx 2sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Bus stop ( Reading) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2234009 |  |  |  | Source:
|  | Date Raised:24/03/2023 14:24:00 |  |  |  | Date Completed:01/01/9999 00:00:00
|  | Location: Outside number 6 |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx 2sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Bus stop ( Reading) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2234010 |  |  |  | Source:
|  | Date Raised:24/03/2023 14:27:00 |  |  |  | Date Completed:03/04/2023 09:30:00
|  | Location: Outside number 49 |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx 2 sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Bus stop ( Reading) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2234011 |  |  |  | Source:
|  | Date Raised:24/03/2023 14:30:00 |  |  |  | Date Completed:03/04/2023 11:00:00
|  | Location: Outside number 49 |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx 1sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Bus stop ( Reading) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2234012 |  |  |  | Source:
|  | Date Raised:24/03/2023 14:31:00 |  |  |  | Date Completed:03/04/2023 12:15:00
|  | Location: Opposite number 51 |  |  |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required 10mm DBM approx less than 1sq mtr ( 3mth inspection) Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: High depending on time of day Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Bus stop ( Reading) TM recommended: May require 2 way temp traffic lights
|  | Defect Number : D2234016 |  |  |  | Source:
|  | Date Raised:24/03/2023 16:13:02 |  |  |  | Date Completed:24/03/2023 17:00:00
|  | Location: Illuminated "Go Left"/"Chevron" sign no. DEVS449 Binfield Road, Wokingham (On Oak Ave/Diamond Jubilee Way r'bout facing north) - unique ID 028805. Knocked down (see W2349044) - as per phone call to 24/3/23 @ 15:55. This sign hasn't yet been adopted so is till the developers responsibility however still needs to be made safe. Volkers Highway Inspector attended 24/3/23 but didn't call this through as an emergency instead they raised D2233974 to replace the chevron and added a note to W2349044 to pass the illumination and large base post replacement to street lighting! DH e-mailed to advise that this is still the developers and also asked Highway Agreements to pass the developer for repair/replacement. |  |  |  | Priority : 2 Hour - Emergency
Description: Signpost knocked down. I stood the signpost upright and secured it. I removed the signlight to tip and refitted the go left signplate to the post and ive then removed the chevron plate and 1x straight post to stores. Needs a new signlight, also needs the w/b post and the straight post concreting back in place and th3n the chevron plate needs refitting to the straight posts.
|  | Defect Number : Unsaved |  |  |  | Source: ?
|  | Date Raised:31/10/2022 11:19:58 |  |  |  | Date Completed:01/01/9999 00:00:00
|  | Location: Lamp Column 030 R/o 25 De-Vitre Grn 65m west of Plough L Asset Id:25460 |  |  |  | Priority : N/A
Description: ?
Enquiries In Date Order - Latest First
| Road Name: |  |  | 44700154 - Binfield Road - Wokingham, 44700154
|  | Enquiry Number: W2232652 |  |  |  | Assigned CSO: Inspection Area 3
|  | Date Raised: 07/02/2022 13:19:00 |  |  |  | Date Completed: 07/02/2022 14:15:00
Location: This a test so that I am able to see the steps taken to report a problem on this system.
Description: This a test so that I am able to see the steps taken to report a problem on this system.
Recomended Action:
|  | Enquiry Number: W2232987 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 15/02/2022 16:29:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Binfield Road
Description: Lots of them
Recomended Action:
|  | Enquiry Number: W2233029 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 16/02/2022 14:14:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Binfield road, from Barrett Crescent to London Road
Description: Potholes in centre of the road most of the way from Barrett Crescent to the traffic lights with London road.
Recomended Action:
|  | Enquiry Number: W2235049 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 01/04/2022 10:47:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Near junction with Carina Drive
Description: Please forward for the attention of Highways Assets Noted as part of driven 3mth inspection 01.04.2022 - SN Zebra crossing and zig zag carriageway markings on approach and exit have worn and require refreshing Speed 30mph Traffic count medium
Recomended Action:
|  | Enquiry Number: W2235068 |  |  |  | Assigned CSO:
|  | Date Raised: 01/04/2022 16:28:00 |  |  |  | Date Completed: 06/04/2022 08:22:53
Location: It is laying in the ditch to the left had side of the cattle grid
Description: The item is under a blanket of weeds that have grown over the bed springs over the past few years.
Recomended Action:
|  | Enquiry Number: W2235688 |  |  |  | Assigned CSO:
|  | Date Raised: 18/04/2022 11:36:00 |  |  |  | Date Completed: 17/02/2023 09:50:00
Location: Near no. 57 Binfield road
Description: Vegetation overgrowing the path, difficult for people with mobility aids to pass through.
Recomended Action:
|  | Enquiry Number: W2235855 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 21/04/2022 14:22:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Crossing from Carina Drive to Keep Hatch woods entrance the crossing markings are very badly worn
Description: Worn markings on crossing
Recomended Action:
|  | Enquiry Number: W2236213 |  |  |  | Assigned CSO:
|  | Date Raised: 01/05/2022 14:36:00 |  |  |  | Date Completed: 03/05/2022 12:15:00
Location: Pothole on Keep Hatch Woods side of Binfield Road
Description: ?
Recomended Action:
|  | Enquiry Number: W2236215 |  |  |  | Assigned CSO:
|  | Date Raised: 01/05/2022 14:51:00 |  |  |  | Date Completed: 03/05/2022 12:15:00
Location: On Carina drive side of Binfield road
Description: Many areas of erosion. Water runs down road due to no kerbing/guttering to help the water flow down the road to Carina drive. Has been gradually getting more and more cracked and have reported this on a previous occasion in the last few years but no action taken.
Recomended Action:
|  | Enquiry Number: W2236588 |  |  |  | Assigned CSO: Tree Management
|  | Date Raised: 11/05/2022 16:52:00 |  |  |  | Date Completed: 03/08/2022 10:10:00
Location: Footpath alongside the Binfield Road&#10;Dead trees visible from closed end of Laud Way
Description: There are two clearly dead trees amongst others beside the footpath at the closed end of Laud Way
Recomended Action:
|  | Enquiry Number: W2237086 |  |  |  | Assigned CSO:
|  | Date Raised: 24/05/2022 15:16:00 |  |  |  | Date Completed: 25/05/2022 10:13:00
Location: By the side of Binfield Road as marked on the map.
Description: This footpath has been blocked for many months. I reported this on Incident Number W2232056 4 months ago, but the footpath is still blocked, which forces pedestrians to walk along the narrow and busy Binfield Road with no footpath. I appreciate that some work has ben done on the site, but this footpath needs to be unblocked.
Recomended Action:
|  | Enquiry Number: W2237136 |  |  |  | Assigned CSO:
|  | Date Raised: 25/05/2022 21:28:00 |  |  |  | Date Completed: 21/11/2022 10:00:00
Location: On LHS of Binfield Road as you go up hill towards new roundabout
Description: Pothole
Recomended Action:
|  | Enquiry Number: W2237315 |  |  |  | Assigned CSO:
|  | Date Raised: 30/05/2022 16:35:00 |  |  |  | Date Completed: 14/06/2022 17:33:00
Location: ?
Description: arm chair and other waste
Recomended Action:
|  | Enquiry Number: W2237913 |  |  |  | Assigned CSO: Flooding
|  | Date Raised: 16/06/2022 07:46:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Outside electricity sub station
Description: Water flowing down the side of the road past 3 houses
Recomended Action:
|  | Enquiry Number: W2238112 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 21/06/2022 11:46:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Binfield Rd from Barrett Crescent to London Road
Description: Please forward to Highways Assets. As part Highways inspection found sections of cway degradation. Multiple areas, sizes would need to he assessed.
Recomended Action:
|  | Enquiry Number: W2238830 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 10/07/2022 17:45:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Binfield Road RG40 1SL. Stretch of road from A329 to the roundabout.
Description: Terrible road condition with many collapsed old pothole repairs. Road looks to need resurfacing.
Recomended Action:
|  | Enquiry Number: W2239425 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 27/07/2022 17:52:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Footpath on the section of Binfield Road between Carina Drive and Oak Avenue.
Description: The footpath here is blocked and has been for at least a year. This means that pedestrians have to walk along Binfield Road, which has no footpaths and is therefore very dangerous. This will become even more dangerous as Autumn approaches and pedestrians have to walk along the road in the dark. This path has been blocked for so long, it is becoming overgrown and may need relaying.
Recomended Action:
|  | Enquiry Number: W2239768 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 04/08/2022 16:32:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Between Binfield Road and Oak Drive
Description: The new footpath leading from Carina Drive to the Binfield Road has a new fence at the end which obviously blocks access to the road. Maybe it would have been more sensible to ensure the pathway around the pond area leading to Oak Drive was opened up first! Someone needs to give Bellway a poke (if it's them that is holding up things) and get them to finish off the pond and open it all up, it's been like this for years now and meanwhile pedestrians have to walk along the road trying to avoid traffic.....
Recomended Action:
|  | Enquiry Number: W2239800 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 05/08/2022 13:44:00 |  |  |  | Date Completed: 28/11/2022 10:12:00
Location: Half way along the Binfield Road section which joins Carina Drive to Diamond Jubilee Way.
Description: I have complained previously about the fact that the footpath here is blocked by steel fences which have been in place for about a year! The lack of a footpath means that pedestrians have to walk along a 200m stretch of Binfield Road, which has no footpaths and inadequate lighting. Although it is a 30 mph zone, many cars travel much faster. This is very dangerous. About 3 months ago, WBC or the developers installed a footpath that at least allowed pedestrians to have a footpath for part of the way. In the last 2 weeks someone has installed a new wooden barrier which blocks access to the new path!! This now means that once again pedestrians have to walk the full 200m without footpaths on a dangerous road.
Recomended Action:
|  | Enquiry Number: W2239972 |  |  |  | Assigned CSO: Flooding
|  | Date Raised: 12/08/2022 06:23:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Binfield road between London road and barrett crescent
Description: Water leak covering most of lane away from london road
Recomended Action:
|  | Enquiry Number: W2240165 |  |  |  | Assigned CSO:
|  | Date Raised: 17/08/2022 18:15:00 |  |  |  | Date Completed: 18/08/2022 12:42:00
Location: Behind the seat and bin between Barrett crescent and binfield road
Description: A flatscreen tv
Recomended Action:
|  | Enquiry Number: W2240346 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 23/08/2022 16:57:00 |  |  |  | Date Completed: 29/11/2022 14:17:00
Location: Corner of Plough Lane and London Road (on side next to Loch Fyne
Description: At least 4 sections of kerbing is damaged
Recomended Action:
|  | Enquiry Number: W2240892 |  |  |  | Assigned CSO:
|  | Date Raised: 08/09/2022 09:27:00 |  |  |  | Date Completed: 12/09/2022 07:45:00
Location: On Binfield Road
Description: Reported this weeks ago , it was marked with paint but hasn't been filled in yet
Recomended Action:
|  | Enquiry Number: W2241223 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 16/09/2022 10:23:00 |  |  |  | Date Completed: 09/03/2023 13:32:00
Location: Binfield Rd just before Road Bridge over A329m, heading North towards Forest Road.
Description: Please forward to Highways Assets. As part of Highways inspection found section of cway degradation. Possibly located at change point in road where Road Bridge starts, over A329m. SB
Recomended Action:
|  | Enquiry Number: W2242405 |  |  |  | Assigned CSO: Flooding
|  | Date Raised: 21/10/2022 09:10:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: bean oak/ barrett crescent end of binfield road
Description: manhole cover/gully pouring water out and down road, road is one huge puddle
Recomended Action:
|  | Enquiry Number: W2242658 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 27/10/2022 17:53:00 |  |  |  | Date Completed: 09/03/2023 13:34:00
Location: Binfield Road bridge over the A329M. And… the same on the Straight Mile Road bridge on the way from the WarrenHouse roundabout to Twyford.
Description: The road surface is breaking up either side of the bridge. The road surface is lower than the bridge surface. The Straight Mile Road bridge surface Is dreadfully wobbly, sunk in places!
Recomended Action:
|  | Enquiry Number: W2242734 |  |  |  | Assigned CSO:
|  | Date Raised: 30/10/2022 17:31:00 |  |  |  | Date Completed: 01/11/2022 13:07:00
Location: ?
Description: This lamppost and the one next to it plus bollards have been completely upended after a car has ploughed into them, unsure if the council is aware but they could be dangerous and electrical wires exposed?
Recomended Action:
|  | Enquiry Number: W2242823 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 01/11/2022 13:49:00 |  |  |  | Date Completed: 01/11/2022 14:13:00
Location: outside property 73
Description: W2242734-This lamppost and the one next to it plus bollards have been completely upended after a car has ploughed into them, unsure if the council is aware but they could be dangerous and electrical wires exposed original enquiry said it couldn't be found but he has rung back in to say it has happened outside number 73
Recomended Action:
|  | Enquiry Number: W2243315 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 11/11/2022 18:47:00 |  |  |  | Date Completed: 09/03/2023 13:35:00
Location: Travelling north, as the Binfield road joins the bridge that goes over the A329, in the direction of Stokes Farm.
Description: Crack across road that appears to be getting worse. There’s a significant bump, change in road height as you drive over it.
Recomended Action:
|  | Enquiry Number: W2244304 |  |  |  | Assigned CSO:
|  | Date Raised: 06/12/2022 09:16:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Junction with Keephatch Road
Description: Please send to Highways Assets as part of Highways Inspection SH Please consider for resurfacing program Road degradation at Roundabout
Recomended Action:
|  | Enquiry Number: W2244305 |  |  |  | Assigned CSO:
|  | Date Raised: 06/12/2022 09:45:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Left hand side as going over bridge
Description: Please send to Highways Assets as part of Highways Inspection SH For further investigation, Road surface cracked from kerbside to centre line of carrigeway
Recomended Action:
|  | Enquiry Number: W2244338 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 07/12/2022 10:22:00 |  |  |  | Date Completed: 14/03/2023 09:57:00
Location: Barrett Crescent Junction with Binfield Rd, Wokingham.
Description: Please forward to Highways Assets. As part of Highways inspection found cway markings faded at junction. Give Way, centre line, Stop line and 'SLOW'. SB
Recomended Action:
|  | Enquiry Number: W2244339 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 07/12/2022 10:28:00 |  |  |  | Date Completed: 07/12/2022 10:28:25
Location: Binfield Rd at Zebra Crossing Near Bean Oak Rd, Wokingham.
Description: Please forward to Cleaner and Greener. As part of Highways inspection found dead vegetation in kerbline and covering tactile paving at ped crossing. &#10;SB
Recomended Action:
|  | Enquiry Number: W2244340 |  |  |  | Assigned CSO: Streetworks
|  | Date Raised: 07/12/2022 10:34:00 |  |  |  | Date Completed: 12/12/2022 16:59:00
Location: Binfield Rd junction with Barrett Crescent, Wokingham.
Description: Please forward to Streetworks. As part of Highways inspection found 2 x inspection covers in cway, polished smooth. SB.
Recomended Action:
|  | Enquiry Number: W2244341 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 07/12/2022 10:58:00 |  |  |  | Date Completed: 20/03/2023 08:51:00
Location: Binfield Rd junction with Barrett Crescent, Wokingham.
Description: Please forward to Highways Assets. As part of Highways inspection found cway degradation. Surface cracking, worn, centre seam open. Consideration for resurfacing. SB.
Recomended Action:
|  | Enquiry Number: W2244342 |  |  |  | Assigned CSO: Streetworks
|  | Date Raised: 07/12/2022 11:07:00 |  |  |  | Date Completed: 13/12/2022 10:08:00
Location: Binfield Rd, outside property "Mandalay", 50m from London Rd. Wokingham.
Description: Please forward to Streetworks. As part of Highways inspection found double lid concrete cover in fway. One section has concrete broken out, exposing reinforcing. Slip / trip hazard. Not clear if this is CATV or BT?. SB
Recomended Action:
|  | Enquiry Number: W2244683 |  |  |  | Assigned CSO: Tree Management
|  | Date Raised: 20/12/2022 16:38:00 |  |  |  | Date Completed: 06/01/2023 11:21:00
Location: Along the road travelling east from keep hatch road. exact location not sure
Description: ?
Recomended Action:
|  | Enquiry Number: W2244822 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 24/12/2022 14:44:00 |  |  |  | Date Completed: 14/03/2023 09:56:00
Location: Crossing on Binfield Road at junction with Carina Drive
Description: White markings on crossing on side nearest Carina Drive are virtually non-existent. Also flashing light on Carina Drive is not working and there has been black tape on the lights for months. There is also no warnings signs about a crossing on either side of crossing. I have reported faint lines and no warning signs in the last two years but nothing has ever been done.
Recomended Action:
|  | Enquiry Number: W2345301 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 07/01/2023 11:47:00 |  |  |  | Date Completed: 09/01/2023 12:31:00
Location: Zebra crossing at the end of Carina drive /Binfield road.
Description: The beacon and column have been inoperative for about a year. There is a real danger that someone will be seriously hurt as traffic is speeding towards the crossing and drivers do not see the crossing. It is common for several vehicles to speed past people waiting to cross. The whole area needs detailed inspection followed by being upgraded. Please confirm that you have received this important message by replying to marilynpayler@gmail.com. Many thanks for your attention to this dangerous matter. Marilyn Payler. 07943888102.
Recomended Action:
|  | Enquiry Number: W2345537 |  |  |  | Assigned CSO: Inspection Area 3
|  | Date Raised: 12/01/2023 07:40:00 |  |  |  | Date Completed: 16/01/2023 12:46:53
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2345654 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 13/01/2023 10:24:00 |  |  |  | Date Completed: 20/03/2023 08:49:00
Location: Binfield Road. Near property Bean Oak Farm. Approx 20M from JN of Plough Lane
Description: Please send to Highway Asset. Noted by JU. I have ordered a make safe of the pothole at this location. But it needs a patch larger then 5m². It may also be worth including the other areas nearby that are being to crack and show signs of breaking up. Please can you order the repair work required
Recomended Action:
|  | Enquiry Number: W2345716 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 14/01/2023 09:06:00 |  |  |  | Date Completed: 16/01/2023 11:22:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2345718 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 14/01/2023 09:12:00 |  |  |  | Date Completed: 14/03/2023 09:54:00
Location: Junction of Carina Drive and Binfield Road
Description: Zebra crossing needs repainting
Recomended Action:
|  | Enquiry Number: W2346014 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 17/01/2023 22:58:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: The bridge over the A329 Binfield Road, approx 150 metres from the roundabout where Oak avenue and Diamond Jubilee Way meet.
Description: There is a large amount of damage to the road where it meets the bridge. It looks like the road is falling below the level of the bridge causing significant discomfort when travelling over it.
Recomended Action:
|  | Enquiry Number: W2347108 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 09/02/2023 10:55:00 |  |  |  | Date Completed: 12/04/2023 15:57:00
Location: Binfield Road, where it crosses the A329M, Keephatch area
Description: There is a dangerous section of raised road on the bridge that crosses the A329M on the Binfield Road. This is not easy to see but causes a horrendous jolt and crunch on wheels and tyres (especially low profile) when crossing it. It goes across the road so you cant avoid it.
Recomended Action:
|  | Enquiry Number: W2347741 |  |  |  | Assigned CSO:
|  | Date Raised: 23/02/2023 15:42:00 |  |  |  | Date Completed: 06/03/2023 07:30:00
Location: Binfield Road from Carina Drive to Oak Avenue and Diamond Jubilee Way roundabout. In the past Binfield Road driving towards Stokes Farm is also missed regularly.
Description: This part of road is continually not being cleaned.
Recomended Action:
|  | Enquiry Number: ENQ2347822 |  |  |  | Assigned CSO: Traffic Signals
|  | Date Raised: 27/02/2023 09:16:11 |  |  |  | Date Completed: 21/06/2023 17:46:00
Location: A329 London Rd, Wokingham, jct with Binfield Rd
Description: Traffic lights turning from right from London Road (A329) into Binfield Road: the sensor in the road that should detect bikes does not work to change the lights and activate the green filter - I have had to sit there through a few changes of lights until a car triggers the detector on the road to change the lights.
Recomended Action:
|  | Enquiry Number: W2347891 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 28/02/2023 10:52:00 |  |  |  | Date Completed: 20/03/2023 08:45:00
Location: Binfield Road from its junction of London Road all the way up to Bean Oak Road.
Description: Potholes are evident along the crown of the road for the length of Binfield Road. These have been poorly repaired before and now reopened up. This forces road traffic to take a tighter line towards the kerb and is bringing traffic closer to a busy pathway at school times. The size of potholes vary between fist size up to the size of a large dinner plate and have a depth of about 2 inches.
Recomended Action:
|  | Enquiry Number: W2348014 |  |  |  | Assigned CSO: Inspection Area 3
|  | Date Raised: 02/03/2023 19:34:00 |  |  |  | Date Completed: 06/03/2023 13:08:00
Location: ?
Description: Several v deep potholes from junction with London Rd to Bean Oak Rd.
Recomended Action:
|  | Enquiry Number: W2348021 |  |  |  | Assigned CSO: Inspection Area 3
|  | Date Raised: 02/03/2023 20:30:00 |  |  |  | Date Completed: 07/03/2023 09:10:35
Location: ?
Description: There are lots of deep pot holes one after the other in this slip of road.
Recomended Action:
|  | Enquiry Number: W2348188 |  |  |  | Assigned CSO:
|  | Date Raised: 06/03/2023 18:24:00 |  |  |  | Date Completed: 14/03/2023 14:19:00
Location: At the entrance of The Carillons development / roundabout of Carina Drive and Binfield Road.
Description: These trees need to be pruned as they are dangerously close to the houses, have overhanging branches, the branches drop off which is a danger to passers by on the path. They also block out a significant amount of natural light and need to be pruned.
Recomended Action:
|  | Enquiry Number: W2348189 |  |  |  | Assigned CSO:
|  | Date Raised: 06/03/2023 18:29:00 |  |  |  | Date Completed: 22/03/2023 09:25:39
Location: In front of 11 Carina Drive, on the other side of the knee high guard rail.
Description: A replacement plastic composite knee high rail guard was recently installed replacing the old rotten rail guard...Thats great....but can you please remove the residual rubbish (old wooden posts and concrete foundations) that have been left. I spoke to the contractor and he said it would be taken away as part 2 of the job....2 weeks have gone by and this is still lying in piles on the grass. It is very unsightly and a potential danger to pedestrians. Please arrange to have this removed as soon as possible.
Recomended Action:
|  | Enquiry Number: W2348244 |  |  |  | Assigned CSO:
|  | Date Raised: 07/03/2023 09:57:00 |  |  |  | Date Completed: 09/03/2023 07:53:00
Location: ?
Description: city fibre left in state
Recomended Action:
|  | Enquiry Number: W2348819 |  |  |  | Assigned CSO: Inspection Area 3
|  | Date Raised: 16/03/2023 18:07:00 |  |  |  | Date Completed: 24/03/2023 12:40:00
Location: There are a number all along this stretch up to the roundabout.
Description: There are lots of potholes all next to each other, they look quite deep & there are some on the left & then a few running in the middle by the white line. You can’t avoid them!
Recomended Action:
|  | Enquiry Number: W2348891 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 17/03/2023 14:39:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: From Motorway Bridge to Forest Road. More extreme towards ForestRoad
Description: Virtually the length of the road from the motorway bridge up to Forest road has deep rutting both sides of the road. Some are extremely deep and could cause a major accident If vehicle strayed into them. Easily done at night.
Recomended Action:
|  | Enquiry Number: W2349044 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 21/03/2023 11:46:00 |  |  |  | Date Completed: 24/03/2023 16:28:00
Location: New Road - near Oakingham Bell First roundabout coming from Oakingham Bell
Description: Sign is down and a part of it is hanging over the road Looks like something has taken sign out
Recomended Action:
|  | Enquiry Number: W2349150 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 22/03/2023 20:11:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Between Carina Drive and balancing pond on corner of Oak Avenue and Binfield Road
Description: Cracks on Road surface for several metres. Reported this area around 2 years ago and is getting worse. Binfield Road is not a quiet road and, whilst not as busy as London Road, is used by a lot of traffic including articulated lorries that travel up to Stokes Farm and further along Binfield Road.
Recomended Action:
|  | Enquiry Number: W2349152 |  |  |  | Assigned CSO: Inspection Area 3
|  | Date Raised: 22/03/2023 20:15:00 |  |  |  | Date Completed: 03/04/2023 10:15:00
Location: Between Carina Drive and balancing pond at corner of Oak Avenue and Binfield Road
Description: Pothole near cracks
Recomended Action:
|  | Enquiry Number: W2349164 |  |  |  | Assigned CSO: Inspection Area 3
|  | Date Raised: 23/03/2023 08:38:00 |  |  |  | Date Completed: 24/03/2023 12:41:00
Location: Binfield Road, between London Road and Keephatch Road.
Description: There are multiple pot holes on both sides of the road near the kerb, as well as along the central line of Binfield Road, between London Road and Keephatch Road.
Recomended Action:
|  | Enquiry Number: W2349265 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 24/03/2023 12:24:00 |  |  |  | Date Completed: 24/03/2023 12:24:33
Location: By Carina Drive
Description: Please send to Highways Assets as part of 3mth Highways Inspection SH &#10;&#10;Please consider for repainting the faded white road markings at the zebra Crossing
Recomended Action:
|  | Enquiry Number: W2349269 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 24/03/2023 12:37:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: From plough Lane to number 71/72 Binfield Road
Description: Please send to Highways Assets as part of 3mth Highways Inspection SH Please can you take a look at the verged area that has several reflective bollards some of which are broken - perhaps consideration for something more substantial as there is a ditch 1 side
Recomended Action:
|  | Enquiry Number: W2349579 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 29/03/2023 16:36:00 |  |  |  | Date Completed: 31/03/2023 08:57:00
Location: ?
Description: Light not working since 27th October as whole light pole demolished in a traffic accident. Cllr Burgess reported it on 28th October. I was told years ago when new housing estates were built near here told that lighting behind us were needed for safety reasons yet it is now over 5 months with two lights missing. Will report the other one too.
Recomended Action:
|  | Enquiry Number: W2349581 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 29/03/2023 16:38:00 |  |  |  | Date Completed: 31/03/2023 08:58:00
Location: ?
Description: Please see W2349579 for same comments
Recomended Action:
|  | Enquiry Number: W2349582 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 29/03/2023 16:48:00 |  |  |  | Date Completed: 31/03/2023 08:58:00
Location: ?
Description: Unknown number of roadside safety bollards been missing since road accident on 27th October. Cllr Burgess reported this plus the 2 street lights which were completely destroyed. These bollards are between the road and a ditch so this road has been unsafe for 5 months. I have reported the 2 missing street lights today. Reference W2349579 and W2349581
Recomended Action:
|  | Enquiry Number: W2349584 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 29/03/2023 16:53:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Binfield Road at junction of Carina Drive.
Description: White lines on crossing virtually non-existent on half the crossing.
Recomended Action:
|  | Enquiry Number: W2349686 |  |  |  | Assigned CSO:
|  | Date Raised: 31/03/2023 15:09:00 |  |  |  | Date Completed: 20/04/2023 09:19:00
Location: Binfield Road between its junction with Keephatch Road and London Road.
Description: Poor Road surface.
Recomended Action:
|  | Enquiry Number: W2349792 |  |  |  | Assigned CSO: Flooding
|  | Date Raised: 01/04/2023 16:10:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Binfield Road - At the back of 15-17 De Vitre Green. Also along to back of 31 De Vitre Green,
Description: On Friday large amounts of water on road which was flowing down from past crossing on Binfield Road and flooding from Bean Oak Barn side into ditch on 17 De Vitre Green side. Cars were driving through so much water that it was being sprayed over the ditch onto ground at back of 17 De Vitre Green. Water was also being sprayed over brick fence at Bean Oak Barn. This ditch has had no vegetation removed since 2021. Rest of ditch behind 19 through to 31 has not been cleared for years and has dead branches, car parts from an accident last October, bits of safety bollards plus litter. I will send photos separately via the Customer Services email as my photos will not download.
Recomended Action:
|  | Enquiry Number: W2349814 |  |  |  | Assigned CSO:
|  | Date Raised: 01/04/2023 20:51:00 |  |  |  | Date Completed: 20/04/2023 09:34:00
Location: All Plough Lane
Description: Several potholes and very uneven road damage
Recomended Action:
Orders In Date Order - Latest First
| Road Name: |  |  | 44700154 - Binfield Road - Wokingham, 44700154
|  | Order Number: ORD2200339 |  |  |  | Originator:
|  | Date Raised: 04/03/2022 07:47:41 |  |  |  | Date Completed: 27/06/2022 10:23:00
|  | Location: 44700154 - BINFIELD ROAD - WOKINGHAM |  |  |  | Date Instructed: 04/03/2022 07:57:05
|  | Description: Illum. Bollard B028 (id:19676) On traffic island opposite lamp col 24 Not applicable Unknown illuminated bollard, 11w compact fluorscnt PL 4-pin, Unknown control - CHECK Remove all existing bollard kit to tip, supply and install 1no Non-illuminated reflective rebound keep left bollard complete new number (BO28) with new underground cage system, unit will require disconnection of DNO underground service. Tm may be required here - please add ass required. |  |  |  | Priority: 361 Days
|  | Order Number: ORD2200340 |  |  |  | Originator:
|  | Date Raised: 04/03/2022 08:01:29 |  |  |  | Date Completed: 22/03/2022 08:58:00
|  | Location: 44700154 - BINFIELD ROAD - WOKINGHAM |  |  |  | Date Instructed: 04/03/2022 08:03:16
|  | Description: Illum. Bollard B013 (id:22647) At Keephatch Rd r'ndabout (facing north) Not applicable Glasdon Rebound Signmaster LED, LED Glasdon Rebnd Bld Mains 7w, Glasdon Infra-Red PEC Mains Vt Bollard shell is missing. Please install new plain aspect bollard shell complete with new number (BO13) |  |  |  | Priority: 41 Days
|  | Order Number: ORD2200440 |  |  |  | Originator:
|  | Date Raised: 21/03/2022 15:34:28 |  |  |  | Date Completed: 08/04/2022 13:42:00
|  | Location: 44700154 - BINFIELD ROAD - WOKINGHAM |  |  |  | Date Instructed: 21/03/2022 15:39:16
|  | Description: Reflect Bollard B021(NON) (id:19988) Opp col 18 on island at Twycross Rd rnbt Please replace non - illuminated bollard complete. Remove all existing equipment to tip. Install 1no new Pudsey Diamond ground cage system C/W Pudsey Diamond Visabol reflective non-illuminated keep left shell C/W new numbering on rear (BO21) |  |  |  | Priority: 39 Days
|  | Order Number: ORD2201537 |  |  |  | Originator:
|  | Date Raised: 23/08/2022 10:52:15 |  |  |  | Date Completed: 06/10/2022 12:46:10
|  | Location: 44700154 - BINFIELD ROAD - WOKINGHAM |  |  |  | Date Instructed: 23/08/2022 10:58:50
|  | Description: As per attached spreadsheet clear surface water grille from all debris Location: Location number 48 TM may be required. Any problems call |  |  |  | Priority: 31 Days
|  | Order Number: ORD2201538 |  |  |  | Originator:
|  | Date Raised: 23/08/2022 11:06:22 |  |  |  | Date Completed: 06/10/2022 12:59:15
|  | Location: 44700154 - BINFIELD ROAD - WOKINGHAM |  |  |  | Date Instructed: 23/08/2022 11:10:23
|  | Description: As per attached spreadsheet clear surface water grille from all debris - mentions garden waste Location: Location number 50 TM may be required. Any problems call |  |  |  | Priority: 31 Days
|  | Order Number: ORD2201851 |  |  |  | Originator:
|  | Date Raised: 02/11/2022 11:47:37 |  |  |  | Date Completed: 01/01/9999 00:00:00
|  | Location: 44700154 - BINFIELD ROAD - WOKINGHAM |  |  |  | Date Instructed: 02/11/2022 11:51:07
|  | Description: Lamp Column 030 (id:25460) R/o 25 De-Vitre Grn 65m west of Plough L Alumin 5m ALC Promenade 380 pl Philips "Iridium" 45w CPO SE P, LED Holophane VMX.V1x16 3920lm, Telensa Telecell NEMA+In Dim M (000362467900) This order is for columns 30 & 31. Install 2no Alumin 5m ALC Promenade 380 pl with 0.5 outreach brackets complete with new numbering, please fit 2no LED Holophane VMX.V1x16 3920lm lanterns (I think one was retained in stores) complete with Telensa nodes. Both units will require transfers of underground service (DNO) Carry out 2no electrical tests once energised. Please add TM as required (assume 2-way lights for 8 hours) |  |  |  | Priority: 40 Days
|  | Order Number: ORD2202062 |  |  |  | Originator:
|  | Date Raised: 02/12/2022 16:30:14 |  |  |  | Date Completed: 19/12/2022 09:45:00
|  | Location: 44700154 - BINFIELD ROAD - WOKINGHAM |  |  |  | Date Instructed: 02/12/2022 16:31:14
|  | Description: Lamp column no. 040 Binfield Road, Wokingham (Approx. 70m east of Carina Drive r'about) - unique ID 025470. Light out - Telecell I reporting lamp failure (light may work when first switched on but system will shut it down soon after to protect the LED driver). Alumin 5m ALC Promenade 380 pl column with Holophane V-MAXv1 3920lm LED S/E lantern and Telensa Telecell NEMA+In Dim M (0002105487-83). |  |  |  | Priority: 31 Days
|  | Order Number: ORD2202234 |  |  |  | Originator:
|  | Date Raised: 19/12/2022 17:14:02 |  |  |  | Date Completed: 07/02/2023 18:20:00
|  | Location: 44700154 - BINFIELD ROAD - WOKINGHAM |  |  |  | Date Instructed: 19/12/2022 17:15:30
|  | Description: remove roots by digging gully pot and remove any visible roots in outlet pipe. Then clear gully and jet outlet pipe. Gully located opposite bean oak road Location: FMC ID number: FMC_26506 FMC_21917 TM may be required. Any problems call Notes: Near a junction Near a roundabout Approx road width - 7.4m Footway- yes |  |  |  | Priority: 31 Days
|  | Order Number: ORD2300441 |  |  |  | Originator:
|  | Date Raised: 07/03/2023 17:25:04 |  |  |  | Date Completed: 29/03/2023 10:31:16
|  | Location: 44700154 - BINFIELD ROAD - WOKINGHAM |  |  |  | Date Instructed: 28/03/2023 14:48:28
|  | Description: Defect Size: x9 Small potholes Photos attached: Yes Mapping attached: No Road Speed: 30 MPH Approx Road Width: 6 Approx Traffic Flow: Medium Footways: Both Sides Near Bend: No Near a Hill: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: No Additional TM: No |  |  |  | Priority: 1 Days
|  | Order Number: ORD2300549 |  |  |  | Originator:
|  | Date Raised: 22/03/2023 14:35:04 |  |  |  | Date Completed: 01/01/9999 00:00:00
|  | Location: 44700154 - BINFIELD ROAD - WOKINGHAM |  |  |  | Date Instructed: 28/03/2023 14:23:16
|  | Description: Defect: Replace x10 Bollards (see photo) Location: Binfield Road - Between Plough Ln & No73 (x7 West side,x3 East Side) Carriageway or Footway: Verge Photos attached: Yes Mapping attached: No Road Speed: 40 MPH Approx Road Width: 6 Approx Traffic Flow: Medium Footways: Neither side Near Bend: Yes Near a Hill: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: No Additional TM: N two way traffic control maybe required |  |  |  | Priority: 31 Days
|  | V18 | 28/06/2023 08:49:50
Page 48 of 48