## 44701916
Inspections In Date Order - Latest First
| Road Name: |  |  | 44701916 - Swallowfield Bypass - Swallowfield, 44701916
|  | Date Due: 28/02/2024 00:00:00 |  |  | Date Completed: 21/02/2024 15:58:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: WET
|  | Defects Found: Yes |  |  | Inspection Comments: Observed outstanding defect D2229549 and D2335105 for galvanised guardrail repairs.
|  | Date Due: 28/01/2024 00:00:00 |  |  | Date Completed: 22/01/2024 13:41:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DAMP
|  | Defects Found: Yes |  |  | Inspection Comments: ?
|  | Date Due: 28/12/2023 00:00:00 |  |  | Date Completed: 21/12/2023 11:35:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DAMP
|  | Defects Found: Yes |  |  | Inspection Comments: ?
|  | Date Due: 28/11/2023 00:00:00 |  |  | Date Completed: 22/11/2023 12:46:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DAMP
|  | Defects Found: Yes |  |  | Inspection Comments: ?
|  | Date Due: 28/10/2023 00:00:00 |  |  | Date Completed: 25/10/2023 11:46:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DAMP
|  | Defects Found: Yes |  |  | Inspection Comments: ?
|  | Date Due: 28/09/2023 00:00:00 |  |  | Date Completed: 21/09/2023 14:36:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: Yes |  |  | Inspection Comments: ?
|  | Date Due: 28/08/2023 00:00:00 |  |  | Date Completed: 22/08/2023 07:52:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: No |  |  | Inspection Comments: Inspected 21/08/2023
|  | Date Due: 28/07/2023 00:00:00 |  |  | Date Completed: 21/07/2023 09:54:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: No |  |  | Inspection Comments: ?
|  | Date Due: 28/06/2023 00:00:00 |  |  | Date Completed: 21/06/2023 09:11:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: No |  |  | Inspection Comments: ?
|  | Date Due: 28/05/2023 00:00:00 |  |  | Date Completed: 24/05/2023 17:31:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: No |  |  | Inspection Comments: ?
|  | Date Due: 28/04/2023 00:00:00 |  |  | Date Completed: 27/04/2023 11:34:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: Yes |  |  | Inspection Comments: ?
|  | Date Due: 28/03/2023 00:00:00 |  |  | Date Completed: 21/03/2023 14:30:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DAMP
|  | Defects Found: Yes |  |  | Inspection Comments: ?
|  | Date Due: 28/02/2023 00:00:00 |  |  | Date Completed: 27/02/2023 10:07:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: Yes |  |  | Inspection Comments: ?
Defects In Date Order - Latest First
| Road Name: |  |  | 44701916 - Swallowfield Bypass - Swallowfield, 44701916
|  | Defect Number : D2232908 |  |  |  | Source:
|  | Date Raised:13/02/2023 09:11:00 |  |  |  | Date Completed:13/02/2023 09:33:24
|  | Location: ? |  |  |  | Priority : 3 Days
Description: General rubbish/litter strewn all along A33 and in lay bys
|  | Defect Number : D2233548 |  |  |  | Source:
|  | Date Raised:12/03/2023 18:22:00 |  |  |  | Date Completed:15/03/2023 12:52:00
|  | Location: A33 junction at traffic lights into spencers wood |  |  |  | Priority : 3 Days
Description: Cars wanted for cash stickers on bollards and poles. We tried to remove but needed special tools.
|  | Defect Number : D2233610 |  |  |  | Source: Inspection Area 1
|  | Date Raised:14/03/2023 10:34:00 |  |  |  | Date Completed:14/03/2023 11:14:27
|  | Location: A33 dual carriageway south of 3 Mile Cross junction |  |  |  | Priority : 28 Days - Standard Response
Description: Huge amount of litter alongside the A33 dual carriageway south of 3 Mile Cross junction
|  | Defect Number : D2233687 |  |  |  | Source:
|  | Date Raised:16/03/2023 09:49:00 |  |  |  | Date Completed:16/03/2023 22:30:00
|  | Location: Going north near 14A marker post. |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe pothole, NOT marked on A33 swallowfield bypass. Going north near 14A marker post. Not marked nor pictures due to the location and speed of the road. Permanent repair if possible, but please let me know. RB Road Speed: national speed 60mph Approx Road Width: 6.0M. Approx Traffic Flow: high, depending on time of day. Approx HGV / Bus Traffic Flow: high Footways: no Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No
|  | Defect Number : D2334668 |  |  |  | Source:
|  | Date Raised:13/04/2023 13:41:00 |  |  |  | Date Completed:13/04/2023 14:15:00
|  | Location: Swallowfield By pass marker 14 alpha |  |  |  | Priority : 2 Hour - Emergency
Description: S4 L4 Not on scheduled inspection- call centre request Please make safe potholes Road Speed: National speed limit Approx Road Width: 8M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume: NA Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction:No Near School: No Near Roundabout: No Other hazard: No TM recommended: Signing & Guarding
|  | Defect Number : D2334907 |  |  |  | Source:
|  | Date Raised:19/04/2023 14:49:36 |  |  |  | Date Completed:21/04/2023 10:15:00
|  | Location: Along A33 (spotted by Steve) to heavy for one man to lift |  |  |  | Priority : 3 Days
Description: Please collect x2 tyres from side of the road along A33
|  | Defect Number : D2335094 |  |  |  | Source:
|  | Date Raised:27/04/2023 09:00:00 |  |  |  | Date Completed:28/04/2023 18:44:38
|  | Location: A33 centre Crossing point, at slip road, turn for Basingstoke Rd. Opposite the bus lanes. |  |  |  | Priority : 24 Hours - Urgent
Description: From enquiry. **A33** L3 S3 CAT 1B. Please sweep up loose aggregate from concrete spill on tactile paving at pedestrian controlled lights. May need to park works vehicle remotely. May require Traffic management. Road Speed: 40MPH Approx Road Width: 12M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: yes Near Traffic Signals: yes Near Junction: yes Near School: no Near Roundabout: no Other hazard: Avoid peak hours TM recommended yes
|  | Defect Number : D2335100 |  |  |  | Source:
|  | Date Raised:27/04/2023 10:39:00 |  |  |  | Date Completed:28/04/2023 18:59:20
|  | Location: A33 Bravo between marker 0/7 and 0/8 in Lane 1 of 2. In Offside wheel line. |  |  |  | Priority : 24 Hours - Urgent
Description: L3 S3 CAT 1B **A33** Please make safe cway pothole, not marked. Will require lane 1 of 2 closure. Road Speed: 70MPH Approx Road Width: 10M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: no Other hazard: TM recommended yes
|  | Defect Number : D2335105 |  |  |  | Source:
|  | Date Raised:27/04/2023 11:22:00 |  |  |  | Date Completed:01/01/9999 00:00:00
|  | Location: A33 Northbound. At centre island, right turning for Basingstoke Rd. |  |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. **A33**. Please replace missing galvanised railing on centre island. May need assessment for Traffic management. Blue barrier already in situ. Road Speed: 40MPH Approx Road Width: 12M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: medium Near Bend: no Near Pedestrian Crossing: yes Near Traffic Signals: yes Near Junction: yes Near School: no Near Roundabout: no Other hazard: off peak working. TM recommended yes
|  | Defect Number : D2335866 |  |  |  | Source:
|  | Date Raised:24/05/2023 09:39:00 |  |  |  | Date Completed:26/07/2023 10:47:07
|  | Location: Along centre reservation, Lane 3 of 3. Near to opposite Lamp 505. It is the 3rd gully up from inline with Lamp 505. |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe the pothole around gully. Not marked due to location. Will need Lane 3 closure. Road Speed: 40MPH Approx Road Width: 12.0M, 3 lanes. Approx Traffic Flow: High, depending on time of day. Approx HGV / Bus Traffic Flow: High Footways: No Near Bend: No Near Pedestrian Crossing: Yes Near Traffic Signals: Yes Near Junction: Yes, approx 300m away Near School: No Near Roundabout: No
|  | Defect Number : D2337239 |  |  |  | Source:
|  | Date Raised:11/07/2023 15:07:00 |  |  |  | Date Completed:12/07/2023 12:55:00
|  | Location: A33 lay-by Swallowfield ///plots.places.stress |  |  |  | Priority : 3 Days
Description: Wood piled up next to bin///plots.places.stress
|  | Defect Number : D2337278 |  |  |  | Source:
|  | Date Raised:13/07/2023 08:36:00 |  |  |  | Date Completed:18/07/2023 13:19:31
|  | Location: A33 - second lay-by if coming from Wellington Park towards M4 Junction (Bollard 25A) |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe debris in adopted verge off national speed limit dual carriageway. Road Speed: 70MPH Approx Road Width: 10.0M, there is a lay by next to issue. Approx Traffic Flow: V. High, depending on time of day. Approx HGV / Bus Traffic Flow: V. High Footways: Yes Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No
|  | Defect Number : D2337518 |  |  |  | Source:
|  | Date Raised:25/07/2023 09:53:00 |  |  |  | Date Completed:25/07/2023 12:22:00
|  | Location: A33 Northbound Wellington End - swallowfield |  |  |  | Priority : 3 Days
Description: Dumped tires
|  | Defect Number : D2337655 |  |  |  | Source:
|  | Date Raised:31/07/2023 08:59:00 |  |  |  | Date Completed:08/08/2023 10:20:40
|  | Location: A33/Basingstoke Road, on ventral verge, after lights at Mereoak. |  |  |  | Priority : 3 Days
Description: Mattress URBASER - We do not attend the central reservation of the A33 without TM - this needs TM to be installed by Volker Highways
|  | Defect Number : D2338667 |  |  |  | Source:
|  | Date Raised:21/09/2023 14:15:00 |  |  |  | Date Completed:27/09/2023 11:36:53
|  | Location: Lane 3 - centre verge between Basingstoke Rd traffic lights & Mereoak traffic lights |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L3 ( no photos due to vasalia not loading at time of defect raised) Please make safe pothole around gully Road Speed: 40MPH Approx Road Width: 18M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: Yes Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Traffic Volume TM recommended: Signing & Guarding
|  | Defect Number : D2338668 |  |  |  | Source:
|  | Date Raised:21/09/2023 14:23:00 |  |  |  | Date Completed:28/09/2023 06:49:57
|  | Location: Lane 2 after Mereoak Traffic lights |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L3 ( no photos due to vasalia not loading at time of defect raised) Please make safe pothole Road Speed: 40MPH/ National speed limit Approx Road Width: 18M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: Yes Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Traffic Volume TM recommended: Signing & Guarding
|  | Defect Number : D2338669 |  |  |  | Source:
|  | Date Raised:21/09/2023 14:26:00 |  |  |  | Date Completed:27/09/2023 11:14:38
|  | Location: Lane 1 just past Berkshire border |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L3 ( no photos due to vasalia not loading at time of defect raised) Please make safe pothole Road Speed: National speed limit Approx Road Width: 12M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: Yes Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: Yes Other hazard: Traffic Volume TM recommended: Signing & Guarding
|  | Defect Number : D2338670 |  |  |  | Source:
|  | Date Raised:21/09/2023 14:29:00 |  |  |  | Date Completed:27/09/2023 11:27:15
|  | Location: Lane 1 by layby |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L3 ( no photos due to vasalia not loading at time of defect raised) Please make safe pothole by layby Road Speed: National speed limit Approx Road Width: 12M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No Other hazard: Traffic Volume/ layby TM recommended: Signing & Guarding
|  | Defect Number : D2339760 |  |  |  | Source: Inspection Area 1
|  | Date Raised:16/11/2023 08:56:00 |  |  |  | Date Completed:16/11/2023 11:01:00
|  | Location: SWALLOWFIELD BYPASS - SWALLOWFIELD Outside the electric Sub-station |  |  |  | Priority : 24 Hours - Urgent
Description: Dead badger.
|  | Defect Number : D2339865 |  |  |  | Source:
|  | Date Raised:22/11/2023 10:50:00 |  |  |  | Date Completed:01/01/9999 00:00:00
|  | Location: A33 Alpha, off slip to Mereoak Lane. |  |  |  | Priority : 24 Hours - Urgent
Description: L3 S3 CAT 1B. .A33. Please replace damaged post on grassed island and reattach Traffic information signs (left on verge). Second post is intact. May require Traffic management set up. Road Speed: 40MPH Approx Road Width: 6M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: yes Near Junction: yes Near School: no Near Roundabout: yes Other hazard: off peak working. TM recommended yes
|  | Defect Number : D2340127 |  |  |  | Source:
|  | Date Raised:05/12/2023 13:54:00 |  |  |  | Date Completed:06/12/2023 11:20:00
|  | Location: North bound A33 lay-by ///giving.solar.feed Sofa and furniture |  |  |  | Priority : 3 Days
Description: North bound A33 lay-by ///giving.solar.feed Sofa and furniture
|  | Defect Number : D2340406 |  |  |  | Source:
|  | Date Raised:21/12/2023 09:22:00 |  |  |  | Date Completed:22/12/2023 01:15:00
|  | Location: A33 opp lamp column 505. Between Basingstoke Road lights and Mereoak lights. |  |  |  | Priority : 24 Hours - Urgent
Description: L3 S3 CAT 1B. Please make safe cway pothole at gully, not marked. Lane 3 of 3. Opposite lamp column 505. May require (outside) lane closure. Road Speed: 40MPH Approx Road Width: 12M Approx Traffic Flow: HIGH Approx HGV / Bus Traffic Flow: HIGH Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: yes Near Traffic Signals: yes Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended YES.
|  | Defect Number : D2340704 |  |  |  | Source: Inspection Area 1
|  | Date Raised:08/01/2024 09:23:00 |  |  |  | Date Completed:08/01/2024 13:23:00
|  | Location: Swallowfield Bypass - Swallowfield Parallel to Roe Gardens |  |  |  | Priority : 2 Hour - Emergency
Description: Dead Dog
|  | Defect Number : D2340753 |  |  |  | Source:
|  | Date Raised:09/01/2024 09:18:00 |  |  |  | Date Completed:10/01/2024 10:42:00
|  | Location: North bound carriageway - in layby and also along carriageway - swallowfield/riseley |  |  |  | Priority : 3 Days
Description: North bound carriageway - in layby and also along carriageway - swallowfield/riseley
|  | Defect Number : D2341035 |  |  |  | Source:
|  | Date Raised:22/01/2024 09:31:00 |  |  |  | Date Completed:23/01/2024 14:09:00
|  | Location: Single panel and garden gate metal, W3W swing.supply.edge, Basingstoke Road - Shinfield. |  |  |  | Priority : 3 Days
Description: Single panel and garden gate metal, W3W swing.supply.edge, Basingstoke Road - Shinfield.
|  | Defect Number : D2341053 |  |  |  | Source:
|  | Date Raised:22/01/2024 12:52:00 |  |  |  | Date Completed:29/02/2024 19:04:00
|  | Location: Centre carrigeway By marker 04B |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L3 Please make safe pothole Road Speed: National speed limit Approx Road Width: 6M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: Yes Other hazard: Lay By TM recommended: Signing & Guarding, may require temp lane closure due to location
|  | Defect Number : D2341055 |  |  |  | Source:
|  | Date Raised:22/01/2024 13:00:00 |  |  |  | Date Completed:23/01/2024 14:25:00
|  | Location: Opposite lay by -marker 26A lane 1 near to centre line |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L3 Please make safe pothole Road Speed: National speed limit Approx Road Width: 6M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: Yes Other hazard: Lay By TM recommended: Signing & Guarding, may require temp lane closure due to location
|  | Defect Number : D2341056 |  |  |  | Source:
|  | Date Raised:22/01/2024 13:09:00 |  |  |  | Date Completed:23/01/2024 14:26:00
|  | Location: Opposite lay by -marker 26A lane 1 |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L3 Please make safe pothole Road Speed: National speed limit Approx Road Width: 6M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: Yes Other hazard: Lay By TM recommended: Signing & Guarding, may require temp lane closure due to location
|  | Defect Number : D2341248 |  |  |  | Source:
|  | Date Raised:30/01/2024 12:22:00 |  |  |  | Date Completed:30/01/2024 13:47:00
|  | Location: On the right lane going up towards M4 just after the set of traffic lights with meteoak. Note no photos due to location and no footpath to take pictures safely. |  |  |  | Priority : 2 Hour - Emergency
Description: Please sweep stones which has fallen onto the carriageway just after the junction with Mereoak after the set if lights from Basingstoke towards M4 Road Speed: 40MPH Approx Traffic Flow: high depending on time of day. Approx HGV / Bus Traffic Flow: high Footways: no Near Bend: yes Near Pedestrian Crossing: no Near Traffic Signals: yes Near Junction: yes Near School: no Near Roundabout: no
|  | Defect Number : D2341463 |  |  |  | Source:
|  | Date Raised:11/02/2024 10:33:00 |  |  |  | Date Completed:12/02/2024 14:00:00
|  | Location: A33 - Wellington Country Park to the Petrol Station - heading into Reading. Construction waste - Transit Van Load - its all along that stretch of road |  |  |  | Priority : 3 Days
Description: A33 - Wellington Country Park to the Petrol Station - heading into Reading. Construction waste - Transit Van Load - its all along that stretch of road This is not a flytip - it's strewn all the way down a long section of A33, requires a litter pick - VH may do scheduled litter picks down there, please enquire with them otherwise we will have to price it which will include buffer truck/TM
|  | Defect Number : D2341820 |  |  |  | Source:
|  | Date Raised:21/02/2024 15:17:00 |  |  |  | Date Completed:29/02/2024 19:18:00
|  | Location: A33 Swallowfield by pass, Alpha. 10meters into WBC boundary from Welsh Lane Roundabout |  |  |  | Priority : 24 Hours - Urgent
Description: L3 S3 CAT 1B. Please make safe cway pothole, not marked due to location. See photo. Traffic management required. If possible first time permanent 1m2 HRA. Lane 1 closure, patch is 1m off nearside of Lane. Road Speed: National Speed Limit Approx Road Width: 10M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: yes Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: yes Other hazard: off peak working TM recommended yes
|  | Defect Number : D2341821 |  |  |  | Source:
|  | Date Raised:21/02/2024 15:35:00 |  |  |  | Date Completed:29/02/2024 19:20:00
|  | Location: A33 Swallowfield by pass, 18meters into WBC boundary from Welsh Lane Roundabout |  |  |  | Priority : 24 Hours - Urgent
Description: L3 S3 CAT 1B. Please make safe cway pothole, not marked due to location. See photo. Traffic management required. If possible first time permanent 1m2 HRA. Lane 1 closure, patch is 1m off centre line to Lane 2. Road Speed: National Speed Limit Approx Road Width: 10M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: yes Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: yes Other hazard: off peak working TM recommended yes
|  | Defect Number : D2341822 |  |  |  | Source:
|  | Date Raised:21/02/2024 15:39:00 |  |  |  | Date Completed:29/02/2024 19:27:00
|  | Location: A33 Swallowfield by pass. At mile marker 2/3 Alpha. |  |  |  | Priority : 24 Hours - Urgent
Description: L3 S3 CAT 1B. Please make safe cway pothole, not marked due to location. See photo. Traffic management required. If possible first time permanent 1m2 HRA. Lane 1 closure, patch is 1m off nearside of Lane. Road Speed: National Speed Limit Approx Road Width: 10M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: yes Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: yes Other hazard: off peak working TM recommended yes
|  | Defect Number : D2341823 |  |  |  | Source:
|  | Date Raised:21/02/2024 15:44:00 |  |  |  | Date Completed:29/02/2024 19:36:00
|  | Location: A33 Swallowfield by pass 20m before Mile marker 2/6 Alpha. |  |  |  | Priority : 24 Hours - Urgent
Description: L3 S3 CAT 1B. Please make safe cway pothole, not marked due to location. See photo. Traffic management required. If possible first time permanent 1m2 HRA. Lane 1 closure, patch is 1m off nearside of Lane. Road Speed: National Speed Limit Approx Road Width: 10M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: yes Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: yes Other hazard: off peak working. Located at end of rigid concrete lay by. TM recommended yes
|  | Defect Number : D2341845 |  |  |  | Source:
|  | Date Raised:22/02/2024 13:59:00 |  |  |  | Date Completed:23/02/2024 11:50:00
|  | Location: A33 North in verge on entrance to lay-by just past marker post 43A |  |  |  | Priority : 24 Hours - Urgent
Description: Please barrier off damaged manhole cover in verge of lay-by. Sandbags will be required to hold the barriers in place due to dual carriageway. Road Speed: 70MPH Approx Road Width: 10.0M Approx Traffic Flow: High, depending on time of day. Approx HGV / Bus Traffic Flow: High Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No Other: Defect on entrance to lay-by
|  | Defect Number : D2342054 |  |  |  | Source:
|  | Date Raised:29/02/2024 13:05:00 |  |  |  | Date Completed:29/02/2024 19:43:00
|  | Location: Before marker 26A |  |  |  | Priority : 2 Hour - Emergency
Description: S4 L4 Please make safe pothole- lane 1 Carrigeway Depth: 100mm Road Speed: National speed limit Approx Road Width: 10M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No Other hazard: No TM recommended: Signing & Guarding/ lane closure
|  | Defect Number : D2342055 |  |  |  | Source:
|  | Date Raised:29/02/2024 13:13:00 |  |  |  | Date Completed:29/02/2024 19:38:00
|  | Location: Before marker 26A |  |  |  | Priority : 2 Hour - Emergency
Description: S4 L4 Please make safe pothole- lane 1 Carrigeway Depth: 100mm Road Speed: National speed limit Approx Road Width: 10M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No Other hazard: No TM recommended: Signing & Guarding/ lane closure
Enquiries In Date Order - Latest First
| Road Name: |  |  | 44701916 - Swallowfield Bypass - Swallowfield, 44701916
|  | Enquiry Number: W2347086 |  |  |  | Assigned CSO:
|  | Date Raised: 08/02/2023 22:28:00 |  |  |  | Date Completed: 09/02/2023 09:00:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2347087 |  |  |  | Assigned CSO:
|  | Date Raised: 08/02/2023 22:38:00 |  |  |  | Date Completed: 13/02/2023 09:33:24
Location: ?
Description: The whole a33 needs to be tidied up it’s an eyesore on both sides of the road with tyres and general rubbish from lorries and cars. Regular clearance is required urgently
Recomended Action:
|  | Enquiry Number: W2347283 |  |  |  | Assigned CSO: Inspection Area 3
|  | Date Raised: 14/02/2023 08:24:00 |  |  |  | Date Completed: 24/02/2023 11:32:00
Location: ?
Description: A33 Northbound N of Barge Lane 2x potholes in left hand lane either side of the bridge over the stream
Recomended Action:
|  | Enquiry Number: W2347304 |  |  |  | Assigned CSO: Jane Hopkins
|  | Date Raised: 14/02/2023 11:29:00 |  |  |  | Date Completed: 14/02/2023 15:22:00
Location: ?
Description: Rubbish (refuse and recycling) As above, rubbish is strewn all along both verges.
Recomended Action:
|  | Enquiry Number: W2347307 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 14/02/2023 12:16:00 |  |  |  | Date Completed: 15/02/2023 08:04:00
Location: See above
Description: On North bound slip lane from A33 onto Basingstoke Road heading east. Bollard is on its side in centre island
Recomended Action:
|  | Enquiry Number: W2347554 |  |  |  | Assigned CSO:
|  | Date Raised: 20/02/2023 11:28:00 |  |  |  | Date Completed: 20/02/2023 12:36:00
Location: Swallowfield By-pass
Description: I reported this information under reference 2347087, A reply was received that it had been dealt with. The whole Swallowfield bypass needs a litter pick, some of the plastic can cause danger to drivers if it blows across the windscreen. The whole bypass looks a mess and requires urgent attention please
Recomended Action:
|  | Enquiry Number: W2347612 |  |  |  | Assigned CSO:
|  | Date Raised: 21/02/2023 09:00:00 |  |  |  | Date Completed: 22/02/2023 08:03:00
Location: ?
Description: The verges on the Swallowfield Bypass are covered in litter. I cannot remember ever having seen litter being cleared in our area. The fly tipping along the layby going towards Reading is awful. Its been there for 20 plus years so please don't tell me it's a new problem. It is wrong to only concentrate on Towns The area looks horrendous.
Recomended Action:
|  | Enquiry Number: W2347966 |  |  |  | Assigned CSO:
|  | Date Raised: 02/03/2023 08:53:00 |  |  |  | Date Completed: 02/03/2023 12:27:00
Location: ?
Description: Rubbish both sides of carriageway - tyres, mattresses, a sofa, and general waste. It is attracting fly tipping due to the shear volume of rubbish. Can this please be cleared?
Recomended Action:
|  | Enquiry Number: W2347977 |  |  |  | Assigned CSO:
|  | Date Raised: 02/03/2023 12:02:00 |  |  |  | Date Completed: 02/03/2023 12:25:00
Location: ?
Description: Location: A33 dual carriageway from Mereoak crossroads to Wellington roundabout (Hampshire boarder). Both Southbound & northbound. Litter on grass verges , particularly near lay-bye, including Sofas, tyres to general rubbish and bags of rubbish. Very dangerous and unsightly
Recomended Action:
|  | Enquiry Number: W2348303 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 08/03/2023 14:49:00 |  |  |  | Date Completed: 18/04/2023 09:56:00
Location: ?
Description: Westbound two potholes on left carridge
Recomended Action:
|  | Enquiry Number: W2348384 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 10/03/2023 08:11:00 |  |  |  | Date Completed: 18/04/2023 09:58:00
Location: After the roundabout on the north bound land towards Reading
Description: A very large dip with a diameter about 1 meter
Recomended Action:
|  | Enquiry Number: W2348406 |  |  |  | Assigned CSO:
|  | Date Raised: 10/03/2023 11:26:00 |  |  |  | Date Completed: 15/03/2023 12:52:00
Location: ?
Description: We As shinfield parish Council have noticed a high number of flyposting again on the junction at A33 Basingstoke road into three mile cross. the adverts are for Wanted cars and vans and the number is 0747 020 7162
Recomended Action:
|  | Enquiry Number: W2348555 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 13/03/2023 11:01:00 |  |  |  | Date Completed: 03/05/2023 13:10:15
Location: A33 Northbound marker posts 22A to 27A, opposite BP Garage.
Description: Police TA 3 report sever pothole and road damage to the A33 likely to cause a danger to road users. 2nd report, initially reported 15/12/2022 police reference 43220486875.
Recomended Action:
|  | Enquiry Number: W2348586 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 13/03/2023 16:13:00 |  |  |  | Date Completed: 14/03/2023 11:14:27
Location: A33 south of M4
Description: Huge amount of litter alongside the A33 dual carriageway south of 3 Mile Cross junction
Recomended Action:
|  | Enquiry Number: W2349430 |  |  |  | Assigned CSO:
|  | Date Raised: 27/03/2023 13:12:00 |  |  |  | Date Completed: 18/04/2023 11:14:00
Location: Swallowfield bypass A33 northbound inside lane
Description: Nearside lane of the northbound carriageway is subsiding for about half a mile causing traffic to drive in the middle of the road.
Recomended Action:
|  | Enquiry Number: W2350007 |  |  |  | Assigned CSO:
|  | Date Raised: 04/04/2023 16:15:00 |  |  |  | Date Completed: 18/04/2023 11:14:00
Location: A33
Description: Big hole very dangerous my tyre exploded
Recomended Action:
|  | Enquiry Number: W2350019 |  |  |  | Assigned CSO:
|  | Date Raised: 04/04/2023 18:56:00 |  |  |  | Date Completed: 18/04/2023 11:13:00
Location: Between Spring lane bridge and turn off for barge lane Photo shows grid references
Description: Thats one big hole !
Recomended Action:
|  | Enquiry Number: W2350058 |  |  |  | Assigned CSO:
|  | Date Raised: 05/04/2023 12:57:00 |  |  |  | Date Completed: 18/04/2023 11:12:00
Location: Northbound carriageway
Description: Road damage which is starting to turn into pothole due to significant wear on the road surface on inside lane
Recomended Action:
|  | Enquiry Number: W2350224 |  |  |  | Assigned CSO:
|  | Date Raised: 10/04/2023 20:47:00 |  |  |  | Date Completed: 18/04/2023 11:12:00
Location: A33 north bound towards Reading shortly after the roundabout at the junction with B3349
Description: These potholes caused my brand new tyre fitted on 4th April to burst and damaged my alloy wheel. I can&rsquo;t get a new tyre until the alloy wheel has been repaired. This will cost me approximately &pound;160+ Vat in addition to a new tyre costing approx &pound;80.00. This happened on 8th April. I had to call out the AA to change the wheel. This is extremely inconvenient as I cannot do my work so in addition am losing money.
Recomended Action:
|  | Enquiry Number: W2350421 |  |  |  | Assigned CSO:
|  | Date Raised: 13/04/2023 11:43:00 |  |  |  | Date Completed: 13/04/2023 12:55:00
Location: ?
Description: I travel this road frequently and have done so for a few years. Never have I seen any of the litter being removed. For a royal county it is a disgrace. The bins get empty but that is it. May be someone should actually drive along and view it. I see other people have raised this issue too.
Recomended Action:
|  | Enquiry Number: W2350478 |  |  |  | Assigned CSO:
|  | Date Raised: 13/04/2023 22:49:00 |  |  |  | Date Completed: 14/04/2023 13:15:18
Location: A33/Mereoak Lane Junction
Description: Originally posted on Fix My Street 7 months ago but still not rectified. https://www.fixmystreet.com/report/3902466 Several large dangerous lumps of solid concrete in road On the junction of Mereoak Lane and the A33. These lumps of concrete have obviously fallen from the nearby concrete company’s tipper lorries at some point in the past years. They’ve been there so long that they’re visible on Google Maps street view (see photo attached). Having to dodge them on a daily basis to commute to and from work, they are highly raised and unavoidable. Trying to drive over them in the rain as I’ve had to today, makes it even more difficult and dangerous. They need to be removed urgently, will cause tyres to blow or cause a serious accident on a very busy road.
Recomended Action:
|  | Enquiry Number: W2350565 |  |  |  | Assigned CSO:
|  | Date Raised: 15/04/2023 16:52:00 |  |  |  | Date Completed: 18/04/2023 11:13:00
Location: A33 heading to Reading.
Description: Pothole causing damage to tyres and alloys. Popped tyres and dented alloys.
Recomended Action:
|  | Enquiry Number: W2350717 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 18/04/2023 08:59:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: At the junction of Mereoak Land and Swallowfield bypass
Description: Debris and loose stones on the road
Recomended Action:
|  | Enquiry Number: W2351137 |  |  |  | Assigned CSO: Traffic Signals
|  | Date Raised: 26/04/2023 13:56:00 |  |  |  | Date Completed: 15/11/2023 17:35:00
Location: Northbound to Reading A33 junction with Basingstoke Road at Three Mile Cross.
Description: Right filter lane to Basingstoke Road is twisted so that cars waiting on the Basingstoke Road to drive onto the A33 can see the colour of the traffic light. Someone not concentrating properly could look up, see a green light then drive forward. The unit needs to be twisted back into the correct position.
Recomended Action:
|  | Enquiry Number: W2351177 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 27/04/2023 11:06:00 |  |  |  | Date Completed: 14/12/2023 12:58:00
Location: A33 Bravo between marker 4/4 & 4/3
Description: Please forward to Highways Assets. As part of Highways inspection found cway degradation. Lane 1 of 2 at nearside wheel line. Cway surface split, uneven, pulling down towards verge.
Recomended Action:
|  | Enquiry Number: W2351178 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 27/04/2023 11:12:00 |  |  |  | Date Completed: 14/12/2023 12:59:00
Location: A33 Alpha at marker 4/3
Description: Please forward to Highways Assets. As part of Highways inspection found cway degradation. Lane 1 of 2 at nearside wheel line. Cway surface split, uneven, pulling down towards verge.
Recomended Action:
|  | Enquiry Number: W2351179 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 27/04/2023 11:20:00 |  |  |  | Date Completed: 27/04/2023 11:29:00
Location: A33 North bound, at Traffic lights, Junction with Basingstoke Road. Bollard 431n.
Description: Please forward to steet lighting. As part of Highways inspection found bollard on island broken off at bolts. Bollard 431n.
Recomended Action:
|  | Enquiry Number: W2352360 |  |  |  | Assigned CSO: Traffic Signals
|  | Date Raised: 22/05/2023 22:54:00 |  |  |  | Date Completed: 15/08/2023 12:05:00
Location: ?
Description: From Thames Valley Police - have received a phone call from a member of the public stating the traffic lights at this location are not working. Thank you
Recomended Action:
|  | Enquiry Number: W2352374 |  |  |  | Assigned CSO: Traffic Signals
|  | Date Raised: 23/05/2023 09:19:00 |  |  |  | Date Completed: 22/08/2023 16:00:00
Location: ?
Description: 3 way permanent traffic lights reported as not working in any direction. Just as traffic is coming off the M4, the 3 way lights on the junction with Mereoak Lane are not working in any direction.
Recomended Action:
|  | Enquiry Number: W2353008 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 08/06/2023 11:01:00 |  |  |  | Date Completed: 09/06/2023 14:17:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2353727 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 24/06/2023 07:41:00 |  |  |  | Date Completed: 06/07/2023 11:28:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2354041 |  |  |  | Assigned CSO:
|  | Date Raised: 03/07/2023 13:14:00 |  |  |  | Date Completed: 07/07/2023 19:22:00
Location: At the A33 in front Tabby Drive, Mereoak Park, Shinfield, Three Mile Cross, Wokingham, , RG7 1WR
Description: The A33 is being used as a race track. I live nearby and sometimes, late at night, there is very loud vehicle noise. You hear engines revving, breaks squealing and engines backfiring. This goes on for some time before it stops. I am concerned that this is dangerous and someone could be seriously injured or killed in these escapades.
Recomended Action:
|  | Enquiry Number: W2354261 |  |  |  | Assigned CSO:
|  | Date Raised: 06/07/2023 13:08:00 |  |  |  | Date Completed: 18/07/2023 13:19:31
Location: 12 July 2023 - issue is with hazard from loose wire on adopted highway verge next to A33 northbound layby, south of Beech Hill Road overbridge. Bridleway running between the underpass from Lambs Lane Spencers Wood towards Wood Lane, Beech Hill. Issue near the lay-by.
Description: Fencing still not fixed even though I reported it over a year ago. Broken tangled wire is a hazard for horse riders. Loads of rubbish by the lay-by. Without the fencing animals can get on the A33 and cause an accident. People parking in the lay-by climb down to the bridlepath to urinate.
Recomended Action:
|  | Enquiry Number: W2354265 |  |  |  | Assigned CSO:
|  | Date Raised: 06/07/2023 13:24:00 |  |  |  | Date Completed: 11/07/2023 09:33:00
Location: A33, Shinfield, Three Mile Cross before Lamb's La
Description: The wire fencing separating the bridle path from the dual carriageway is broken in various places and missing completely from a long stretch along the lay-by. This is a serious health and safety concern for horses, their riders and motorists on the A33 alike. Horses are flight animals weighing half a ton or more. If one found its way onto the dual carriageway, the consequences could easily be fatal for those involved. There are long stretches of bridle path running along both sides of the A33 which are all fenced securely. This section needs urgent attention to return the path to a safe amenity. It has already been left in this sorry state for at least three years!
Recomended Action:
|  | Enquiry Number: W2354602 |  |  |  | Assigned CSO:
|  | Date Raised: 12/07/2023 16:51:00 |  |  |  | Date Completed: 13/07/2023 10:14:00
Location: What3words location format.loose.less
Description: Manhole cover is slightly open with water visible underneath. Partially covered with dead grass. Manhole occurs adjacent to footpath between road and VRS
Recomended Action:
|  | Enquiry Number: W2355037 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 21/07/2023 08:38:00 |  |  |  | Date Completed: 21/07/2023 09:03:00
Location: At junction with Basingstoke Road
Description: Please forward for the attention of Street Lighting Noted as part of monthly driven inspection 21.07.2023 - SN Bollard 431 N has been displaced from its current, correct positioning on the island dividing turn right Traffic from north bound A33 traffic. Consideration for remedy required.
Recomended Action:
|  | Enquiry Number: W2355040 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 21/07/2023 09:37:00 |  |  |  | Date Completed: 21/07/2023 12:23:00
Location: A33 alpga on centre island. At junction with Basingstoke Road.
Description: Please forward to Street lighting. As part of Highways inspection found plastic Traffic island bollard has come unbolt from mounting. Many thanks SB
Recomended Action:
|  | Enquiry Number: W2355042 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 21/07/2023 09:47:00 |  |  |  | Date Completed: 19/12/2023 14:14:00
Location: A33 Bravo Mile marker 24B.
Description: Please forward to Highways Assets. As part of Highways inspection found Mile Marker 24B damaged, laying on verge. No photo taken due to location. Many thanks SB
Recomended Action:
|  | Enquiry Number: W2355173 |  |  |  | Assigned CSO:
|  | Date Raised: 24/07/2023 14:51:00 |  |  |  | Date Completed: 25/07/2023 12:22:00
Location: A33 stanford end - Swallofield
Description: Car tyres dumped here on side of northbound carriageway.
Recomended Action:
|  | Enquiry Number: W2355260 |  |  |  | Assigned CSO:
|  | Date Raised: 25/07/2023 16:24:00 |  |  |  | Date Completed: 27/07/2023 10:29:00
Location: mereoak park - three mile cross behind No 42
Description: a lot of brambles are damaging the fence of the property, they are so dry and the customer is requesting to cut it back
Recomended Action:
|  | Enquiry Number: W2355461 |  |  |  | Assigned CSO: Traffic Signals
|  | Date Raised: 30/07/2023 09:15:00 |  |  |  | Date Completed: 15/11/2023 17:34:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2355476 |  |  |  | Assigned CSO:
|  | Date Raised: 31/07/2023 08:54:00 |  |  |  | Date Completed: 08/08/2023 10:20:40
Location: ?
Description: Mattress on central verge, after lights at Mereoak, reported via Love Clean Streets.
Recomended Action:
|  | Enquiry Number: W2356364 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 22/08/2023 07:40:00 |  |  |  | Date Completed: 19/12/2023 19:54:00
Location: lane 1 of 2. Just before the last layby, north bound, A33.
Description: Please send to HA, noted by JU during inspection. Significant depression in the CW. the area is too large for me to order the patch to repair. please arrange the repair.
Recomended Action:
|  | Enquiry Number: W2357336 |  |  |  | Assigned CSO:
|  | Date Raised: 20/09/2023 12:05:00 |  |  |  | Date Completed: 20/09/2023 15:20:00
Location: basingstoke road - Swallofield in left side of the carriageway towards to reading, before Mereoak Lane
Description: The road is subsiding and cracking
Recomended Action:
|  | Enquiry Number: W2358176 |  |  |  | Assigned CSO: Traffic Signals
|  | Date Raised: 12/10/2023 09:23:00 |  |  |  | Date Completed: 16/11/2023 14:45:00
Location: A33 by Three Mile Cross
Description: The pedestrian crossing on the Reading bound side is not working. V dangerous for pedestrians!
Recomended Action:
|  | Enquiry Number: W2358477 |  |  |  | Assigned CSO: Tree Management
|  | Date Raised: 20/10/2023 16:13:00 |  |  |  | Date Completed: 25/10/2023 11:49:00
Location: 48 Mereoak Park, RG7 1NR. -The oak tree is located over the back fence on the raised portion bordering the A33.
Description: Oak tree that needs trimming and pruning thats dangerously hanging over the fence.
Recomended Action:
|  | Enquiry Number: W2359579 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 16/11/2023 08:39:00 |  |  |  | Date Completed: 16/11/2023 11:01:00
Location: Outside the electric Sub-station
Description: Dead badger
Recomended Action:
|  | Enquiry Number: W2359683 |  |  |  | Assigned CSO:
|  | Date Raised: 20/11/2023 09:08:00 |  |  |  | Date Completed: 24/11/2023 11:20:00
Location: Access road from Grazaley road to the A33 - Three Mile cross
Description: Deep drop at the edge of the road affecting stability.
Recomended Action:
|  | Enquiry Number: W2359998 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 28/11/2023 15:02:00 |  |  |  | Date Completed: 09/01/2024 10:29:00
Location: Please forward onto HA on behalf of RB reference to W2359683. There is an section of carriageway which is uneven causing vehicles to dip. Next to 43B/44B
Description: Please forward onto HA on behalf of RB reference to W2359683. There is an section of carriageway which is uneven causing vehicles to dip. Next to 43B/44B
Recomended Action:
|  | Enquiry Number: W2360023 |  |  |  | Assigned CSO:
|  | Date Raised: 29/11/2023 08:34:00 |  |  |  | Date Completed: 29/11/2023 09:23:00
Location: A33, Shinfield, Three Mile Cross Before the junction with Mereoak Lane
Description: Subsidence is causing northbound and southbound carriageways to collapse (the inner lane on either side). The location on the map is approximate. The issue has been present for at least one year.
Recomended Action:
|  | Enquiry Number: W2360923 |  |  |  | Assigned CSO: Traffic Signals
|  | Date Raised: 28/12/2023 17:35:00 |  |  |  | Date Completed: 29/12/2023 09:06:00
Location: If the bus goes to these lights, the driver will have to reverse the whole way back to drive towards Mereoak P&R.
Description: The Bus Gate traffic lights are no longer working to enable buses to cross the A33 towards Three Mile Cross. Thank you
Recomended Action:
|  | Enquiry Number: W2461028 |  |  |  | Assigned CSO:
|  | Date Raised: 02/01/2024 09:57:00 |  |  |  | Date Completed: 10/01/2024 10:24:00
Location: A33 - Shinfield Three Mile Cross RG71LZ
Description: Multiple potholes northbound on A33 from roundabout at B3499 and M4 junction.
Recomended Action:
|  | Enquiry Number: W2461481 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 07/01/2024 10:39:00 |  |  |  | Date Completed: 08/01/2024 13:23:00
Location: Swallowfield Bypass - Swallowfield Parallel to Roe Gardens
Description: Dead Dog
Recomended Action:
|  | Enquiry Number: W2461540 |  |  |  | Assigned CSO:
|  | Date Raised: 08/01/2024 11:58:00 |  |  |  | Date Completed: 10/01/2024 10:42:00
Location: ?
Description: Appeared to be a small sofa and various bags of rubbish, litter etc. Seen at the A33 lay-by whilst driving by towards M4 & Reading. This stretch of the A33 has an issue with fly tipping, litter, debris etc.
Recomended Action:
|  | Enquiry Number: W2461880 |  |  |  | Assigned CSO:
|  | Date Raised: 13/01/2024 17:25:00 |  |  |  | Date Completed: 23/01/2024 12:04:00
Location: Bridleway on West Side of underpass next to A33 heading towards Wood Lane
Description: Fallen tree
Recomended Action:
|  | Enquiry Number: W2462117 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 18/01/2024 12:23:00 |  |  |  | Date Completed: 29/01/2024 14:31:00
Location: Three Mile Cross notice on Basingstoke Road A33 junction
Description: Three Mile Cross notice on Basingstoke Road A33 junction is defaced with red spray paint.
Recomended Action:
|  | Enquiry Number: W2462229 |  |  |  | Assigned CSO:
|  | Date Raised: 22/01/2024 08:47:00 |  |  |  | Date Completed: 23/01/2024 14:09:00
Location: ?
Description: Some form of a panel and some garden gate metal. What3Words location was swing.supply.edge
Recomended Action:
|  | Enquiry Number: W2462376 |  |  |  | Assigned CSO: Traffic Signals
|  | Date Raised: 24/01/2024 09:19:00 |  |  |  | Date Completed: 24/01/2024 10:30:00
Location: Traffic lights 3 mile cross - Just after junction headig towards basingstoke Heading towards basingstoke and millets farm A33.
Description: 2 sets of traffic lights not working in three mile cross as you go into basingstoke. Traffic lights 3 mile cross - Just after junction headig towards basingstoke Heading towards basingstoke and millets farm A33.
Recomended Action:
|  | Enquiry Number: W2462408 |  |  |  | Assigned CSO: Traffic Signals
|  | Date Raised: 24/01/2024 14:43:00 |  |  |  | Date Completed: 09/02/2024 16:20:00
Location: Right hand turn into Grazley from the A33
Description: ?
Recomended Action:
|  | Enquiry Number: W2462595 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 28/01/2024 17:12:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: ?
Description: Swastika blazoned on the tarmac, amongst a series of what was clearly a graffiti rampage! Also something about ‘Allah’ on the overbridge.
Recomended Action:
|  | Enquiry Number: W2462693 |  |  |  | Assigned CSO:
|  | Date Raised: 30/01/2024 13:10:00 |  |  |  | Date Completed: 30/01/2024 14:32:00
Location: ?
Description: Looked like part of the front fog light cover. This was just by the crossing. Picture attached
Recomended Action:
|  | Enquiry Number: W2462906 |  |  |  | Assigned CSO:
|  | Date Raised: 04/02/2024 09:50:00 |  |  |  | Date Completed: 06/02/2024 10:01:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2463196 |  |  |  | Assigned CSO: Traffic Signals
|  | Date Raised: 09/02/2024 07:41:00 |  |  |  | Date Completed: 09/02/2024 09:28:00
Location: A33 towards basingstoke and Spencer’s wood
Description: Lights not working.
Recomended Action:
|  | Enquiry Number: W2463322 |  |  |  | Assigned CSO:
|  | Date Raised: 11/02/2024 09:20:00 |  |  |  | Date Completed: 12/02/2024 14:00:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2463366 |  |  |  | Assigned CSO:
|  | Date Raised: 12/02/2024 11:41:00 |  |  |  | Date Completed: 22/02/2024 07:43:00
Location: A33- Riseley
Description: Pothole in road causing traffic to swerve
Recomended Action:
|  | Enquiry Number: W2463415 |  |  |  | Assigned CSO:
|  | Date Raised: 13/02/2024 08:56:00 |  |  |  | Date Completed: 13/02/2024 14:31:00
Location: ?
Description: This is some type of a canister Blue I have attached an image. This is located On A33 crossing point at Three Mile Cross the refuge area between the two carriage ways. From truning left to three mile corss, cross the A33 Basingstoke bound carriage way and when you are waiting in the middle of the road to cross A33 towards Reading side you will see this canister in that refuge area for pedestrians. I tried to pick it with litter picker but it is metal too heavy and out of reach. Hence reporting here
Recomended Action:
|  | Enquiry Number: W2463507 |  |  |  | Assigned CSO:
|  | Date Raised: 14/02/2024 10:18:00 |  |  |  | Date Completed: 22/02/2024 07:45:00
Location: Just past Layby
Description: Very Deep pothole
Recomended Action:
|  | Enquiry Number: W2463548 |  |  |  | Assigned CSO: Flooding
|  | Date Raised: 14/02/2024 16:14:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: ?
Description: The gully is flooded with water flooding the road. This has previously been reported with reference No W2360743
Recomended Action:
|  | Enquiry Number: W2464053 |  |  |  | Assigned CSO:
|  | Date Raised: 22/02/2024 10:49:00 |  |  |  | Date Completed: 22/02/2024 12:33:00
Location: A33
Description: Pavement slab come loos, expose a 6ft deep hole. The location is circled in black pen, another photo attached to show it is near the BP petrol station. The resident have also submitted a Highway claim too-
Recomended Action:
|  | Enquiry Number: W2464071 |  |  |  | Assigned CSO:
|  | Date Raised: 22/02/2024 13:18:00 |  |  |  | Date Completed: 23/02/2024 11:50:00
Location: Swallowfield Bypass - Swallowfield Opp petrol station RG71LZ Contact number:
Description: Loose and crack Manhole cover, The customer fell because of this First enquire but wrong location W2464053
Recomended Action:
|  | Enquiry Number: W2464080 |  |  |  | Assigned CSO: Streetworks
|  | Date Raised: 22/02/2024 15:31:00 |  |  |  | Date Completed: 29/02/2024 11:14:00
Location: A33 in grass verge on approach to lay-by just past marker post 43A.
Description: Please forward to SW noted by WE. Concrete manhole cover has become completely dislodged where vehicle has come off the carriageway and driven over it. This is in the grass verge on entrance to lay-by past marker post 43a. Was unable to determine who owns this manhole due to the cover being caked in wet mud. This issue is subject to a claim. Please raise urgent S81 with relevant utility company for permanent repair to concrete manhole cover.
Recomended Action:
|  | Enquiry Number: W2464130 |  |  |  | Assigned CSO:
|  | Date Raised: 23/02/2024 11:51:00 |  |  |  | Date Completed: 25/02/2024 15:38:00
Location: ?
Description: There is a huge amount of build waste all along the verge northbound on this section of road. Looks like its come out of a skip.
Recomended Action:
|  | Enquiry Number: W2464264 |  |  |  | Assigned CSO:
|  | Date Raised: 26/02/2024 16:44:00 |  |  |  | Date Completed: 29/02/2024 19:38:00
Location: Near lay-by, North bound A33 between barge lane and Beech Hill Road over bridge
Description: 3 potholes near the lay-by on the A33 bypass, north bound. One is quite deep. Size of dinner plate at least.
Recomended Action:
|  | Enquiry Number: W2464266 |  |  |  | Assigned CSO: Jane Hopkins
|  | Date Raised: 26/02/2024 17:41:00 |  |  |  | Date Completed: 28/02/2024 08:14:00
Location: The whole stretch of the A33 going into Reading.
Description: Soo much litter at the side of the road that needs picking up. Mattresses/sofas - everything has been dropped here and needs to be picked up. It’s both an eyesore and a disgrace, it’s been like this for 3 months now.
Recomended Action:
|  | Enquiry Number: W2464267 |  |  |  | Assigned CSO:
|  | Date Raised: 26/02/2024 17:45:00 |  |  |  | Date Completed: 28/02/2024 08:15:00
Location: The whole stretch of the A33 between Risely and Reading.
Description: Someone has been flytipping all down this road. There’s mattresses, sofas and everything just scattered on the side of the road. Absolute disgrace. Someone needs to come and pick this up immediately. It’s such an eyesore and the fact it’s been like this for 3 months is totally unacceptable.
Recomended Action:
|  | Enquiry Number: W2464273 |  |  |  | Assigned CSO:
|  | Date Raised: 26/02/2024 21:41:00 |  |  |  | Date Completed: 29/02/2024 13:17:00
Location: Carriageway travelling from Basingstoke to Reading on the inside lane, a series of 3 or 4 potholes along a short stretch of a few hundred metres
Description: There are a series of 3 or 4 potholes on this road travelling from Basingstoke towards Reading. One is particularly large and dangerous that cars swerve to avoid it
Recomended Action:
|  | Enquiry Number: W2464325 |  |  |  | Assigned CSO:
|  | Date Raised: 27/02/2024 15:59:00 |  |  |  | Date Completed: 28/02/2024 08:19:00
Location: Mereoak Park - Three Mile Cross
Description: Huge pothole on the inner lane, passenger side. It's very sharpe and deep. Would be lethal if a motorcyclist hit it or if a driver had to swerve to miss. This will cause severe damage to a car it hit.
Recomended Action:
Orders In Date Order - Latest First
| Road Name: |  |  | 44701916 - Swallowfield Bypass - Swallowfield, 44701916
|  | Order Number: ORD2300544 |  |  |  | Originator:
|  | Date Raised: 21/03/2023 13:37:44 |  |  |  | Date Completed: 05/11/2023 12:07:00
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 28/03/2023 13:39:27
|  | Description: Carryout 2023 (JUNE/JULY 2023) BI-ANNUAL as specified within the term maintenance contract. DATE TO BE AGREED WITH VH. Method statement and risk assessments required 1 MONTH PRIOR TO WORKS A33 SWALLOWFIELD BYPASS and associated slips Bi-annual activities as per contract Pre Bi-annual meeting to take place 2 weeks prior to start. Live lanes 70mph Mobile Lane closure, Lane closures, full closure required at various locations. AT LEAST 1 MONTH WE WILL REQUIRE FOR REVIEW - METHOD STATEMENT, RAMS. Site Induction required for Assets Team prior to start to allow site visits. Vegetation to be recorded of what's is to be cut, photos of before, after and ongoing works required. Advise when areas have been completed so these can be inspected i.e. Alpha verge side, Centre, Slip roads etc.., and also a daily report as to what has been carried out that day start and finish times, location of works undertaken and type of works undertake, any issues identified). Reports for all activities supplied within 2 weeks of completion of works, showing what has been checked and what has been carried out/cleaned/cut, not cleaned/not cut/is satisfactory or not satisfactory. Any issues report to Assets team . Meeting to be arranged 2 weeks prior to start, Assets team may be out on site on daily basis as required by Assets team, so site induction will be required. |  |  |  | Priority: 121 Days
|  | Order Number: ORD2301044 |  |  |  | Originator:
|  | Date Raised: 24/05/2023 11:53:35 |  |  |  | Date Completed: 23/06/2023 06:00:00
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 20/07/2023 12:00:54
|  | Description: Structural Maintenance 2023/24 Plane Inlay. Swallowfield Bypass (9382) BOQ ATTACHED. Provisional Sum code utilised to represent codes which aren't on the HIMs system (Series 8000 and 9000, and STAR items) |  |  |  | Priority: 255 Days
|  | Order Number: ORD2301045 |  |  |  | Originator:
|  | Date Raised: 24/05/2023 12:06:15 |  |  |  | Date Completed: 17/07/2023 15:19:53
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 05/06/2023 10:27:55
|  | Description: Structural Maintenance 2023/24 Plane Inlay. Swallowfield Bypass (9384) BOQ ATTACHED. Provisional Sum code utilised to represent codes which aren't on the HIMs system (Series 8000 and 9000, and STAR items) |  |  |  | Priority: 300 Days
|  | Order Number: ORD2301149 |  |  |  | Originator:
|  | Date Raised: 06/06/2023 09:21:29 |  |  |  | Date Completed: 22/06/2023 11:46:47
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 06/06/2023 10:33:06
|  | Description: To provide scaffold tower & support inspector in his duties. Max. Headroom Clearance: 3.7m Works are scheduled to be undertaken on 22 June @ 9.00 - one shift only. |  |  |  | Priority: 16 Days
|  | Order Number: ORD2301313 |  |  |  | Originator:
|  | Date Raised: 05/07/2023 16:14:49 |  |  |  | Date Completed: 13/07/2023 15:00:00
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 05/07/2023 16:19:32
|  | Description: Lamp column no. 442[1-2] Swallowfield Bypass (A33), Swallowfield (On island at Mereoak Ln x-rds (nrst jct)) - unique ID 025605. Check lights - Neither Telecell ID 0003711634-?? or ID 0003711550-?? has communicated since 14/5/2023. Both Telecells have good signal strength. Was last checked for similar issue 27/7/22 (see ORD2201332) but no fault was found and both lanterns appeared to be working and started communicating again that night. Telecells are however reporting intermittent "power up" events which suggests that there may be an intermittent power supply fault or cable connection fault in the base of the column or back at the feeder pillar? Supply fed from feeder pillar in the bus lane opposite lamp column no. 7 Mereoak Lane. May require traffic management as located on dual carriageway at traffic light junction but suspect fault is with fuses or supply so possibly just needs checking at ground level? Steel 12m unk tubular plant gv column with 2 no. LED Philips Luma 24000lm 4000k lanterns and Telensa Telecells NEMA+In Dim M (0003711634-?? and 0003711550-??). |  |  |  | Priority: 28 Days
|  | Order Number: ORD2301719 |  |  |  | Originator:
|  | Date Raised: 04/09/2023 16:52:45 |  |  |  | Date Completed: 01/01/9999 00:00:00
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 04/09/2023 16:54:47
|  | Description: This work to tie in with Bi - annual to liase Replace 1 broken gully lid. If spare lid is available in yard then just replace gully lid. it is not clear form report- FMC iD: FMC_27397 or take gully lid from less sensative area and replace at different location. Please laise with assets team- Location: FMC iD: FMC_27397 -SWALLOWFIELD BYPASS A33 SWALLOWFIELD BYPASS - right next to layby TM may be required - to discussif spare lid is available or can wait till bi-annual -TM not yet added to BOQ as dependant on method of carrying out works. Any problems call Notes: on A33 bypass High speed road extra traffic management |  |  |  | Priority: 149 Days
|  | Order Number: ORD2302319 |  |  |  | Originator:
|  | Date Raised: 16/11/2023 23:02:10 |  |  |  | Date Completed: 23/11/2023 15:00:00
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 16/11/2023 23:12:23
|  | Description: to put out lane 1 closures between Beech Hill and Mearoak Lane on northbound Alpha carriageway and between Mereoak Lane and Beech Hill on Southbound Bravo carriageway. This is to allow WBC officers to look at the carriageway and verges. To be carried out on 23.11.2023 after rush hour nd taken off before afternoon rush hour. Width of carriagewy in excess of 8m speed limit is national speed limit (max 70mph) and also 50mph medium traffic after rushour ANy probelems contact |  |  |  | Priority: 8 Days
|  | Order Number: ORD2302459 |  |  |  | Originator:
|  | Date Raised: 08/12/2023 15:04:12 |  |  |  | Date Completed: 01/01/9999 00:00:00
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 08/12/2023 15:05:21
|  | Description: Location: There is an section of carriageway which is uneven causing vehicles to dip. Next to 43B/44B Works: Put out UNEVEN ROAD signs. Suggested Traffic Management: Give & Take Please supply pictures of completed works. Road Speed: National. Approx Road Width: 6.5m. Approx Traffic Flow: Low/Medium/High, depending on time of day. Approx HGV Traffic Flow: Low. Footways: No. Near Bend: No. Near a Hill: No. Near Pedestrian Crossing: No. Near Traffic Signals: No. Near Junction: No. Near School: No. Near Roundabout: No. |  |  |  | Priority: 1 Days
|  | Order Number: ORD2400063 |  |  |  | Originator:
|  | Date Raised: 09/01/2024 12:45:52 |  |  |  | Date Completed: 08/02/2024 14:48:00
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 09/01/2024 12:52:13
|  | Description: Undertake & supply C2 results for this location. Grid Reference SU 71157 64575 Address (near) : A33, Swallowfield, Riseley, Borough of Wokingham, England, RG7 1JE, United Kingdom Postcode (nearest) : RG7 1JE |  |  |  | Priority: 31 Days
|  | Order Number: ORD2400064 |  |  |  | Originator:
|  | Date Raised: 09/01/2024 12:45:59 |  |  |  | Date Completed: 08/02/2024 14:48:00
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 09/01/2024 12:52:20
|  | Description: Undertake & supply C2 results for this location. Grid Reference SU 71107 64628 Address (near) : A33, Swallowfield, Three Mile Cross, Borough of Wokingham, England, RG7 1LZ, United Kingdom Postcode (nearest) : RG7 1LZ |  |  |  | Priority: 31 Days
|  | Order Number: ORD2400068 |  |  |  | Originator:
|  | Date Raised: 09/01/2024 13:12:55 |  |  |  | Date Completed: 01/01/9999 00:00:00
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 09/01/2024 13:25:33
|  | Description: Remedy damage to the carriageway surfacing. See attached (east end of the structure). Sawcut affected area (approx.1m) max. depth of the sawcut 80mm. Avoid damage to the kerb. Any affected units should be replaced. Break out & remove the existing tarmac. Remove all debris & water from the sawcut area. Ensure all faces are free of contamination, loose material, or dust. Apply coat of ‘seal & tuck’ edge sealant & reinstate tarmac using BBA/HAPAS approved repair products. Adhere to the manufacturer’s instructions when using proprietary products. Check integrity of the existing patch repair along the west end of the bridge. In case of any damage (i.e. pothole or cracking) undertake the repair using above steps. Please provide images for the depth of the sawcut & each stage of the work. |  |  |  | Priority: 21 Days
|  | Order Number: ORD2400376 |  |  |  | Originator:
|  | Date Raised: 26/01/2024 16:47:28 |  |  |  | Date Completed: 01/01/9999 00:00:00
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 13/02/2024 17:16:11
|  | Description: 1. All structures. Cut down vegetation to enable clear perimeter (approx.2m) around a structure i.e. bridge & adjacent embankments, access around culverts & or subways. 2. Remove all debris, litter & vegetation from the deck, foot/cycleway & parapets & sweep clean. 3. Remove all debris from bearing shelves/abutments, rod out drainage outlets to ensure functionality of the system. 4. Steel bearings (accessible from ground level) old grease to be removed, bearings wiped clean, new grease to be applied to all steel elements i.e. top & bottom plates, sliding surfaces & fixings (use non-flowing at 40º C grease). 5. Check & ensure sturdiness of parapets & road restraint system, adjust/replace any missing fixings to achieve sturdy fit (for torque guidance adequate to the system refer to BS 6579). 6. Timber structures. Any soil deposits & vegetation encroaching structure i.e. ends of the beams or deck to be removed (expose timber). Any moss/algae growth along deck & parapets to be brushed off. 7. Culverts & bridges with pier supports. Any obstructions to the water flow i.e. branches within the invert or debris trapped against pier supports to be removed, cut down (timber can be left along the riverbank away from the invert). 8. Any encountered on site defects that require further action i.e. potholes, parapet impact damage to be reported via email for further action. Please provide required date stamped photo evidence of: -VH Job Data Sheet - Photos showing any TM used, condition of a structure before & after RM |  |  |  | Priority: 412 Days
|  | Order Number: ORD2400529 |  |  |  | Originator:
|  | Date Raised: 13/02/2024 12:37:59 |  |  |  | Date Completed: 01/01/9999 00:00:00
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 01/01/1900 00:00:00
|  | Description: SM 2024-25 SWALLOWFIELD BYPASS SOUTH 7914. Provisional sum code used to represent Series 8000/9000 valuation, plus FY uplift provisional sum. BoQ attached for full value. |  |  |  | Priority: 45745 Days
|  | Order Number: ORD2400571 |  |  |  | Originator:
|  | Date Raised: 15/02/2024 14:32:47 |  |  |  | Date Completed: 01/01/9999 00:00:00
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 01/01/1900 00:00:00
|  | Description: SM 2024-25 SWALLOWFIELD BYPASS NORTH 7915. Provisional sum code used to represent Series 8000/9000 valuation, plus FY uplift provisional sum. BoQ attached for full value. |  |  |  | Priority: 45745 Days
|  | V18 | 07/03/2024 15:07:40
Page 37 of 37