## A3290
Defects In Date Order - Latest First
| Road Name: |  | 44706335 - A3290 Bravo - Earley, 44706335
|  | Defect Number : D2340813 |  | Source:
|  | Date Raised:10/01/2024 12:55:00 |  | Date Completed:14/02/2024 14:34:00
|  | Location: Between Mile markers 3/3 Bravo and 3/2 Bravo - prior to Suttons roundabout off slip |  | Priority : 28 Days - Standard Response
Description: L2 S2 Repair unmarked 2.0m x 1.0m HRA carriageway defect Damaged and uneven Located in Lane 1 of 2 towards nearside of carriageway Duel carriageway + marked but unused bus lane Width of carriageway 8.0m+ Live lanes National speed limit 70mph Traffic count high Defect located approx 0.50m from solid white bus lane demarcation line BRAVO lane closure may be required
|  | Defect Number : D2340882 |  | Source: Inspection Area 1
|  | Date Raised:12/01/2024 10:58:00 |  | Date Completed:12/01/2024 12:08:00
|  | Location: A3290 Bravo going to Suttons Park Business Park |  | Priority : 2 Hour - Emergency
Description: A car was in fire, now there is debris on the road and road damaged Call from Police
|  | Defect Number : D2341348 |  | Source:
|  | Date Raised:05/02/2024 12:54:00 |  | Date Completed:29/02/2024 20:18:00
|  | Location: A329 Bravo between 3/3 & 3/2. |  | Priority : 24 Hours - Urgent
Description: A329. L3 S3 CAT 1B. Please make safe cway pothole, not marked. 0.5m off bold white line at Bus Lane. Lane 1 closure. Outstanding perm ticket on D2340813. Road Speed: 70MPH Approx Road Width: 8M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: no Other hazard: TM recommended Yes
|  | Defect Number : D2342128 |  | Source:
|  | Date Raised:05/03/2024 13:24:00 |  | Date Completed:06/03/2024 14:34:00
|  | Location: Bus lane prior to Reading Slip road |  | Priority : 24 Hours - Urgent
Description: S3 L3 Please make safe pothole within bus lane - marker 29 Carrigeway Depth: 100mm Road Speed: National speed limit Approx Road Width: 8M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: Yes Other hazard: Bus Lane TM recommended: Signing & Guarding
|  | Defect Number : D2342132 |  | Source:
|  | Date Raised:05/03/2024 14:09:00 |  | Date Completed:01/01/9999 00:00:00
|  | Location: Hatch area - hard shoulder marker 43 |  | Priority : 28 Days - Standard Response
Description: S2 L2 Permanent repair required approx 4sq mtr - red material Carrigeway Depth: 100mm Road Speed: National speed limit Approx Road Width: 8M Approx Traffic Flow: High Approx HGV / Bus Traffic Flow: High Approx pedestrian volume: Low Footways: No Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No Other hazard: Hard shoulder TM recommended: Signing & Guarding, Lane closure
|  | Defect Number : D2342737 |  | Source:
|  | Date Raised:19/03/2024 12:53:00 |  | Date Completed:01/01/9999 00:00:00
|  | Location: A3290 Bravo between 3/3 & 3/2. |  | Priority : 24 Hours - Urgent
Description: L3 S3 CAT 1B. Please make safe cway pothole, not marked, see photos. 0.5m off nearside bold white line, adjacent to old Bus lane. Lane 1 closure. Road Speed: National Speed Limit Approx Road Width: 8M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: no Other hazard: TM recommended yes
|  | Defect Number : D2342738 |  | Source:
|  | Date Raised:19/03/2024 13:02:00 |  | Date Completed:01/01/9999 00:00:00
|  | Location: A3290 Bravo between 3/3 & 3/2 |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. Please carry out permanent reinstatement to cway. Not marked, see photos. 1.8 x 0.6 HRA & PCC. 0.5m off nearside bold white line, adjacent to old Bus lane. Lane 1 closure. Road Speed: National Speed Limit Approx Road Width: 8M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: no Other hazard: TM recommended yes