## Sheet1
Inspections In Date Order - Latest First
| Road Name: |  |  | 44700510 - Emmbrook Road - Wokingham, 44700510
|  | Date Due: 07/06/2023 00:00:00 |  |  | Date Completed: 05/06/2023 12:43:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Walked Route 22 (6 Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: Yes |  |  | Inspection Comments: ?
Defects In Date Order - Latest First
|  | Defect Number : D2336170 |  |  |  | Source:
|  | Date Raised:05/06/2023 11:59:00 |  |  |  | Date Completed:01/01/9999 00:00:00
|  | Location: Outside number 21/ 25 |  |  |  | Priority : 28 Days - Standard Response
Description: Permanent repair required 10mm DBM Approx 5sq - 6mth inspection Road Speed: 20MPH Approx Road Width: 6M Approx Traffic Flow: Med Approx HGV / Bus Traffic Flow: Med Approx pedestrian volume: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: Yes Near Junction: Yes Near School: No Near Roundabout: No Other hazard: Residents crossover/ railway bridge/ one way Traffic at lights TM recommended: Signing & Guarding, may require temp traffic lights due to location
Orders In Date Order - Latest First
| Road Name: |  |  | 44700510 - Emmbrook Road - Wokingham, 44700510
|  | Order Number: ORD2300855 |  |  |  | Originator:
|  | Date Raised: 26/04/2023 14:48:56 |  |  |  | Date Completed: 02/05/2023 13:15:00
|  | Location: 44700510 - EMMBROOK ROAD - WOKINGHAM |  |  |  | Date Instructed: 26/04/2023 14:51:16
|  | Description: Meet with jetter at 10:30 on Tuesday 02/05/23 at Emmbrook Juniour School , Emmbrook Road |  |  |  | Priority: 6 Days
|  | Order Number: ORD2300888 |  |  |  | Originator:
|  | Date Raised: 05/05/2023 08:02:25 |  |  |  | Date Completed: 01/01/9999 00:00:00
|  | Location: 44700510 - EMMBROOK ROAD - WOKINGHAM |  |  |  | Date Instructed: 01/01/1900 00:00:00
|  | Description: Dig Trial pit to expose buried manhole and raise existing cover. If no manhole cover install one |  |  |  | Priority: 45084 Days
|  | Order Number: ORD2301130 |  |  |  | Originator:
|  | Date Raised: 01/06/2023 10:32:11 |  |  |  | Date Completed: 02/06/2023 12:11:36
|  | Location: 44700510 - EMMBROOK ROAD - WOKINGHAM |  |  |  | Date Instructed: 01/06/2023 10:35:31
|  | Description: Meet at 08:30 on 02/06/23 outside Emmbrook Junior School to replace manhole cover and frame in wooded area |  |  |  | Priority: 1 Days
|  | Order Number: ORD2301142 |  |  |  | Originator:
|  | Date Raised: 02/06/2023 12:16:01 |  |  |  | Date Completed: 08/06/2023 11:30:00
|  | Location: 44700510 - EMMBROOK ROAD - WOKINGHAM |  |  |  | Date Instructed: 02/06/2023 12:17:32
|  | Description: Meet with jetter at Emmbrook Junior School, Emmbrook Road at 10:30 on Thursday 08/08/23 |  |  |  | Priority: 6 Days
|  | Order Number: ORD2301182 |  |  |  | Originator:
|  | Date Raised: 12/06/2023 07:13:24 |  |  |  | Date Completed: 01/01/9999 00:00:00
|  | Location: 44700510 - EMMBROOK ROAD - WOKINGHAM |  |  |  | Date Instructed: 12/06/2023 07:15:48
|  | Description: Meet at Emmbrook Junior School, Emmbrook Road with Combi Jetter/Vactor unit on 25/07/23 at 10:30 |  |  |  | Priority: 43 Days
|  | Order Number: ORD2301448 |  |  |  | Originator:
|  | Date Raised: 26/07/2023 09:02:03 |  |  |  | Date Completed: 21/08/2023 12:06:17
|  | Location: 44700510 - EMMBROOK ROAD - WOKINGHAM |  |  |  | Date Instructed: 26/07/2023 09:03:59
|  | Description: Dig trial hole in wooded area to the rear of Emmbrook Junior School Meet on site on 07/08/23 at 09:00 for exact location |  |  |  | Priority: 12 Days
|  | Order Number: ORD2301572 |  |  |  | Originator:
|  | Date Raised: 11/08/2023 13:41:19 |  |  |  | Date Completed: 21/08/2023 12:30:00
|  | Location: 44700510 - EMMBROOK ROAD - WOKINGHAM |  |  |  | Date Instructed: 22/08/2023 07:50:41
|  | Description: Meet on site with combi jetter at Emmbrook Junior School at 09:00 on 21/08/23 |  |  |  | Priority: (1) Days
|  | V18 | 17/05/2024 15:09:36