## 44701916
Inspections In Date Order - Latest First
| Road Name: |  |  | 44701916 - Swallowfield Bypass - Swallowfield, 44701916
|  | Date Due: 28/03/2023 00:00:00 |  |  | Date Completed: 21/03/2023 14:22:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DAMP
|  | Defects Found: Yes |  |  | Inspection Comments: ?
|  | Date Due: 28/02/2023 00:00:00 |  |  | Date Completed: 27/02/2023 10:12:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 5b(1Monthly) |  |  | Surface Condition: DRY
|  | Defects Found: Yes |  |  | Inspection Comments: ?
Defects In Date Order - Latest First
| Road Name: |  |  | 44701916 - Swallowfield Bypass - Swallowfield, 44701916
|  | Defect Number : D2232908 |  |  |  | Source:
|  | Date Raised:13/02/2023 09:11:00 |  |  |  | Date Completed:13/02/2023 09:33:24
|  | Location: ? |  |  |  | Priority : 3 Days
Description: General rubbish/litter strewn all along A33 and in lay bys
|  | Defect Number : D2233610 |  |  |  | Source: Inspection Area 1
|  | Date Raised:14/03/2023 10:34:00 |  |  |  | Date Completed:14/03/2023 11:14:27
|  | Location: A33 dual carriageway south of 3 Mile Cross junction |  |  |  | Priority : 28 Days - Standard Response
Description: Huge amount of litter alongside the A33 dual carriageway south of 3 Mile Cross junction
|  | Defect Number : D2233687 |  |  |  | Source:
|  | Date Raised:16/03/2023 09:49:00 |  |  |  | Date Completed:16/03/2023 22:30:00
|  | Location: Going north near 14A marker post. |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe pothole, NOT marked on A33 swallowfield bypass. Going north near 14A marker post. Not marked nor pictures due to the location and speed of the road. Permanent repair if possible, but please let me know. RB Road Speed: national speed 60mph Approx Road Width: 6.0M. Approx Traffic Flow: high, depending on time of day. Approx HGV / Bus Traffic Flow: high Footways: no Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No
Enquiries In Date Order - Latest First
| Road Name: |  |  | 44701916 - Swallowfield Bypass - Swallowfield, 44701916
|  | Enquiry Number: W2347087 |  |  |  | Assigned CSO:
|  | Date Raised: 08/02/2023 22:38:00 |  |  |  | Date Completed: 13/02/2023 09:33:24
Location: ?
Description: The whole a33 needs to be tidied up it’s an eyesore on both sides of the road with tyres and general rubbish from lorries and cars. Regular clearance is required urgently
Recomended Action:
|  | Enquiry Number: W2347283 |  |  |  | Assigned CSO: Inspection Area 3
|  | Date Raised: 14/02/2023 08:24:00 |  |  |  | Date Completed: 24/02/2023 11:32:00
Location: ?
Description: A33 Northbound N of Barge Lane 2x potholes in left hand lane either side of the bridge over the stream
Recomended Action:
|  | Enquiry Number: W2347304 |  |  |  | Assigned CSO:
|  | Date Raised: 14/02/2023 11:29:00 |  |  |  | Date Completed: 14/02/2023 15:22:00
Location: ?
Description: Rubbish (refuse and recycling) As above, rubbish is strewn all along both verges.
Recomended Action:
|  | Enquiry Number: W2347307 |  |  |  | Assigned CSO: Street Lighting
|  | Date Raised: 14/02/2023 12:16:00 |  |  |  | Date Completed: 15/02/2023 08:04:00
Location: See above
Description: On North bound slip lane from A33 onto Basingstoke Road heading east. Bollard is on its side in centre island
Recomended Action:
|  | Enquiry Number: W2347554 |  |  |  | Assigned CSO:
|  | Date Raised: 20/02/2023 11:28:00 |  |  |  | Date Completed: 20/02/2023 12:36:00
Location: Swallowfield By-pass
Description: I reported this information under reference 2347087, A reply was received that it had been dealt with. The whole Swallowfield bypass needs a litter pick, some of the plastic can cause danger to drivers if it blows across the windscreen. The whole bypass looks a mess and requires urgent attention please
Recomended Action:
|  | Enquiry Number: W2347612 |  |  |  | Assigned CSO:
|  | Date Raised: 21/02/2023 09:00:00 |  |  |  | Date Completed: 22/02/2023 08:03:00
Location: ?
Description: The verges on the Swallowfield Bypass are covered in litter. I cannot remember ever having seen litter being cleared in our area. The fly tipping along the layby going towards Reading is awful. Its been there for 20 plus years so please don't tell me it's a new problem. It is wrong to only concentrate on Towns The area looks horrendous.
Recomended Action:
|  | Enquiry Number: W2347966 |  |  |  | Assigned CSO:
|  | Date Raised: 02/03/2023 08:53:00 |  |  |  | Date Completed: 02/03/2023 12:27:00
Location: ?
Description: Rubbish both sides of carriageway - tyres, mattresses, a sofa, and general waste. It is attracting fly tipping due to the shear volume of rubbish. Can this please be cleared?
Recomended Action:
|  | Enquiry Number: W2347977 |  |  |  | Assigned CSO:
|  | Date Raised: 02/03/2023 12:02:00 |  |  |  | Date Completed: 02/03/2023 12:25:00
Location: ?
Description: Location: A33 dual carriageway from Mereoak crossroads to Wellington roundabout (Hampshire boarder). Both Southbound & northbound. Litter on grass verges , particularly near lay-bye, including Sofas, tyres to general rubbish and bags of rubbish. Very dangerous and unsightly
Recomended Action:
|  | Enquiry Number: W2348303 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 08/03/2023 14:49:00 |  |  |  | Date Completed: 18/04/2023 09:56:00
Location: ?
Description: Westbound two potholes on left carridge
Recomended Action:
|  | Enquiry Number: W2348384 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 10/03/2023 08:11:00 |  |  |  | Date Completed: 18/04/2023 09:58:00
Location: After the roundabout on the north bound land towards Reading
Description: A very large dip with a diameter about 1 meter
Recomended Action:
|  | Enquiry Number: W2348555 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 13/03/2023 11:01:00 |  |  |  | Date Completed: 03/05/2023 13:10:15
Location: A33 Northbound marker posts 22A to 27A, opposite BP Garage.
Description: Police TA 3 report sever pothole and road damage to the A33 likely to cause a danger to road users. 2nd report, initially reported 15/12/2022 police reference 43220486875.
Recomended Action:
|  | Enquiry Number: W2348586 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 13/03/2023 16:13:00 |  |  |  | Date Completed: 14/03/2023 11:14:27
Location: A33 south of M4
Description: Huge amount of litter alongside the A33 dual carriageway south of 3 Mile Cross junction
Recomended Action:
|  | Enquiry Number: W2349430 |  |  |  | Assigned CSO:
|  | Date Raised: 27/03/2023 13:12:00 |  |  |  | Date Completed: 18/04/2023 11:14:00
Location: Swallowfield bypass A33 northbound inside lane
Description: Nearside lane of the northbound carriageway is subsiding for about half a mile causing traffic to drive in the middle of the road.
Recomended Action:
|  | Enquiry Number: W2350007 |  |  |  | Assigned CSO:
|  | Date Raised: 04/04/2023 16:15:00 |  |  |  | Date Completed: 18/04/2023 11:14:00
Location: A33
Description: Big hole very dangerous my tyre exploded
Recomended Action:
|  | Enquiry Number: W2350019 |  |  |  | Assigned CSO:
|  | Date Raised: 04/04/2023 18:56:00 |  |  |  | Date Completed: 18/04/2023 11:13:00
Location: Between Spring lane bridge and turn off for barge lane Photo shows grid references
Description: Thats one big hole !
Recomended Action:
|  | Enquiry Number: W2350058 |  |  |  | Assigned CSO:
|  | Date Raised: 05/04/2023 12:57:00 |  |  |  | Date Completed: 18/04/2023 11:12:00
Location: Northbound carriageway
Description: Road damage which is starting to turn into pothole due to significant wear on the road surface on inside lane
Recomended Action:
Orders In Date Order - Latest First
| Road Name: |  |  | 44701916 - Swallowfield Bypass - Swallowfield, 44701916
|  | Order Number: ORD2300544 |  |  |  | Originator:
|  | Date Raised: 21/03/2023 13:37:44 |  |  |  | Date Completed: 05/11/2023 12:07:00
|  | Location: 44701916 - SWALLOWFIELD BYPASS - SWALLOWFIELD |  |  |  | Date Instructed: 28/03/2023 13:39:27
|  | Description: Carryout 2023 (JUNE/JULY 2023) BI-ANNUAL as specified within the term maintenance contract. DATE TO BE AGREED WITH VH. Method statement and risk assessments required 1 MONTH PRIOR TO WORKS A33 SWALLOWFIELD BYPASS and associated slips Bi-annual activities as per contract Pre Bi-annual meeting to take place 2 weeks prior to start. Live lanes 70mph Mobile Lane closure, Lane closures, full closure required at various locations. AT LEAST 1 MONTH WE WILL REQUIRE FOR REVIEW - METHOD STATEMENT, RAMS. Site Induction required for Assets Team prior to start to allow site visits. Vegetation to be recorded of what's is to be cut, photos of before, after and ongoing works required. Advise when areas have been completed so these can be inspected i.e. Alpha verge side, Centre, Slip roads etc.., and also a daily report as to what has been carried out that day start and finish times, location of works undertaken and type of works undertake, any issues identified). Reports for all activities supplied within 2 weeks of completion of works, showing what has been checked and what has been carried out/cleaned/cut, not cleaned/not cut/is satisfactory or not satisfactory. Any issues report Meeting to be arranged 2 weeks prior to start, Assets team may be out on site on daily basis as required by Assets team, so site induction will be required. |  |  |  | Priority: 121 Days
|  | V18 | 12/06/2024 15:38:16
Page 7 of 7