## B3348 The Ridges
Inspections In Date Order - Latest First
| Road Name: |  |  | 44706383 - The Ridges - Finchampstead, 44706383
|  | Date Due: 08/01/2023 00:00:00 |  |  | Date Completed: 03/01/2023 16:07:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 9 (3 Monthly) |  |  | Surface Condition: WET
Defects Found: Yes
Inspection Comments:
|  | Date Due: 08/10/2022 00:00:00 |  |  | Date Completed: 22/09/2022 13:19:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 9 (3 Monthly) |  |  | Surface Condition: DRY
Defects Found: Yes
Inspection Comments: Section under Road closure for cway subsidence repairs
|  | Date Due: 08/07/2022 00:00:00 |  |  | Date Completed: 05/07/2022 15:04:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 9 (3 Monthly) |  |  | Surface Condition: DRY
Defects Found: Yes
Inspection Comments: Part Road closure due to subsidence
|  | Date Due: 19/06/2022 00:00:00 |  |  | Date Completed: 17/06/2022 13:30:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Walked Route 53 (12 Monthly) |  |  | Surface Condition: DRY
Defects Found: Yes
Inspection Comments: Very little footway apparent. Cars parked in layby's for Finchampstead Ridges Road currently closed from junction with Jubilee Road Highways Assets advised of spun sign opposite entrance to North Court
|  | Date Due: 08/04/2022 00:00:00 |  |  | Date Completed: 28/03/2022 14:54:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 9 (3 Monthly) |  |  | Surface Condition: DRY
Defects Found: Yes
Inspection Comments: This section includes part cway fenced off for subsidence investigation.
|  | Date Due: 08/01/2022 00:00:00 |  |  | Date Completed: 05/01/2022 13:31:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 9 (3 Monthly) |  |  | Surface Condition: DRY
Defects Found: Yes
Inspection Comments: Road closed from Dell Road to Jubilee Ave
|  | Date Due: 08/10/2021 00:00:00 |  |  | Date Completed: 04/10/2021 09:23:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 9 (3 Monthly) |  |  | Surface Condition: DAMP
Defects Found: Yes
Inspection Comments:
|  | Date Due: 08/07/2021 00:00:00 |  |  | Date Completed: 05/07/2021 06:24:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 9 (3 Monthly) |  |  | Surface Condition: DRY
Defects Found: Yes
Inspection Comments: Road closures
|  | Date Due: 19/06/2021 00:00:00 |  |  | Date Completed: 10/06/2021 08:29:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Walked Route 53 (12 Monthly) |  |  | Surface Condition: DRY
Defects Found: Yes
Inspection Comments: Partial footpath No footpath No footpath
|  | Date Due: 08/04/2021 00:00:00 |  |  | Date Completed: 08/04/2021 13:48:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 9 (3 Monthly) |  |  | Surface Condition: DRY
Defects Found: No
Inspection Comments: Small area closed D2115844 D2115844
Defects In Date Order - Latest First
| Road Name: |  |  | 44706383 - The Ridges - Finchampstead, 44706383
|  | Defect Number : D2015077 |  |  |  | Source: Inspection Area 2
|  | Date Raised:11/03/2021 11:25:00 |  |  |  | Date Completed:11/03/2021 14:32:56
|  | Location: At the junction of the jubilee next to war memorial |  |  |  | Priority : 2 Hour - Emergency
Description: Please close road at the junction of jubilee road for emergency repair
|  | Defect Number : D2115710 |  |  |  | Source:
|  | Date Raised:06/04/2021 08:49:00 |  |  |  | Date Completed:07/04/2021 10:02:00
|  | Location: The Ridges as per map |  |  |  | Priority : 3 Days
Description: black Bags
|  | Defect Number : D2115844 |  |  |  | Source:
|  | Date Raised:08/04/2021 13:34:00 |  |  |  | Date Completed:09/04/2021 12:29:44
|  | Location: Opposite Windsmoor House heading towards Dell Road Left hand carriageway near to Layby Road Speed: 50MPH Approx Road Width: 8M Approx Traffic Flow: High, depending on time of day. Approx HGV / Bus Traffic Flow: High Approx pedestrian volume along FW:Med Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No Other hazard: Layby for woodland area |  |  |  | Priority : 28 Days - Standard Response
Description: Permanent repair required 1sq mtr 10mm DBM
|  | Defect Number : D2117345 |  |  |  | Source:
|  | Date Raised:20/05/2021 09:51:00 |  |  |  | Date Completed:20/05/2021 12:00:00
|  | Location: Junction The Ridges/Dell Road |  |  |  | Priority : 2 Hour - Emergency
Description: Decking and garden wste
|  | Defect Number : D2118756 |  |  |  | Source:
|  | Date Raised:22/07/2021 17:42:00 |  |  |  | Date Completed:26/07/2021 11:45:00
|  | Location: Near map pin By the road works next to the Memorial at the end of The Ridges, Finchampstead RG40 3SJ |  |  |  | Priority : 3 Days
Description: Typewriter, several black bags and a large container with astroturf Please investigate and remove
|  | Defect Number : D2118795 |  |  |  | Source:
|  | Date Raised:23/07/2021 13:36:00 |  |  |  | Date Completed:27/07/2021 10:57:50
|  | Location: As pinned B3348 The Ridges near the memorial |  |  |  | Priority : 3 Days
Description: Tipper load of wood/rubble - image attached
|  | Defect Number : D2118932 |  |  |  | Source:
|  | Date Raised:02/08/2021 15:43:00 |  |  |  | Date Completed:06/08/2021 11:45:00
|  | Location: As pinned The Ridges, in the long layby |  |  |  | Priority : 3 Days
Description: Chair and child car seats
|  | Defect Number : D2122577 |  |  |  | Source:
|  | Date Raised:12/08/2021 06:41:00 |  |  |  | Date Completed:12/08/2021 08:37:47
|  | Location: as per map |  |  |  | Priority : 3 Days
Description: car seats
|  | Defect Number : D2122578 |  |  |  | Source:
|  | Date Raised:12/08/2021 06:45:00 |  |  |  | Date Completed:12/08/2021 10:49:20
|  | Location: as per map |  |  |  | Priority : 3 Days
Description: construction
|  | Defect Number : D2122589 |  |  |  | Source:
|  | Date Raised:12/08/2021 11:11:00 |  |  |  | Date Completed:12/08/2021 11:45:18
|  | Location: The ridges as per map |  |  |  | Priority : 2 Hour - Emergency
Description: Green waste
|  | Defect Number : D2122613 |  |  |  | Source:
|  | Date Raised:12/08/2021 11:11:00 |  |  |  | Date Completed:12/08/2021 12:15:00
|  | Location: The ridges as per map |  |  |  | Priority : 2 Hour - Emergency
Description: Green waste
|  | Defect Number : D2122915 |  |  |  | Source:
|  | Date Raised:02/09/2021 09:57:00 |  |  |  | Date Completed:02/09/2021 11:25:46
|  | Location: The Ridges |  |  |  | Priority : 3 Days
Description: Fly tipping and including furniture and rubbish was spotted here on 31st August (2021).
|  | Defect Number : D2123184 |  |  |  | Source:
|  | Date Raised:17/09/2021 07:21:00 |  |  |  | Date Completed:17/09/2021 11:58:00
|  | Location: Junction of Jubilee Road and The Ridges |  |  |  | Priority : 3 Days
Description: Construction, Bricks and Soild
|  | Defect Number : D2123490 |  |  |  | Source: Traffic Management
|  | Date Raised:06/10/2021 18:09:00 |  |  |  | Date Completed:12/01/2022 10:33:47
|  | Location: Rosedene, The Ridges, Finchampstead |  |  |  | Priority : 28 Days - Standard Response
Description: Re-align deer warning sign
|  | Defect Number : D2123712 |  |  |  | Source:
|  | Date Raised:21/10/2021 11:57:00 |  |  |  | Date Completed:26/10/2021 07:11:34
|  | Location: As pinned B3348 The Ridges, by the road closure at the memorial |  |  |  | Priority : 3 Days
Description: Large fly tip of builder's waste (bricks, stones, buckets, packaging) - images attached
|  | Defect Number : D2228692 |  |  |  | Source:
|  | Date Raised:26/06/2022 20:06:00 |  |  |  | Date Completed:30/06/2022 13:30:00
|  | Location: Finchampstead, the Ridges, end of road by road closed sign |  |  |  | Priority : 3 Days
Description: Soil, bricks, straw
|  | Defect Number : D2229166 |  |  |  | Source:
|  | Date Raised:27/07/2022 14:53:00 |  |  |  | Date Completed:04/08/2022 13:45:00
|  | Location: The Ridges, heading towards Wellingtonia Avenue, Finchampstead |  |  |  | Priority : 3 Days
Description: Building materials
|  | Defect Number : D2229233 |  |  |  | Source:
|  | Date Raised:29/07/2022 14:49:00 |  |  |  | Date Completed:04/08/2022 10:54:00
|  | Location: ///anode.duet.tallest the ridges |  |  |  | Priority : 3 Days
Description: Fence panels and bricks
|  | Defect Number : D2229234 |  |  |  | Source:
|  | Date Raised:29/07/2022 15:04:00 |  |  |  | Date Completed:04/08/2022 00:00:00
|  | Location: ///foal.chapters.scaffold the ridges |  |  |  | Priority : 3 Days
Description: This is a large tip of bricks and wood, but small quantities of fibrous material in the waste - spread over 3 piles in the lay-by
|  | Defect Number : D2229237 |  |  |  | Source:
|  | Date Raised:30/07/2022 16:24:00 |  |  |  | Date Completed:01/08/2022 14:12:00
|  | Location: Opposite Pine Cottage, The Ridges, Finchampstead - 3 locations on South side of the road. |  |  |  | Priority : 3 Days
Description: Three separate loads of fencing, bricks, timber and general rubbish.
|  | Defect Number : D2229291 |  |  |  | Source:
|  | Date Raised:03/08/2022 08:28:00 |  |  |  | Date Completed:04/08/2022 11:49:02
|  | Location: All located opposite four winds. All Marked |  |  |  | Priority : 24 Hours - Urgent
Description: Please make replace 4 sections are missing and approx 7 grante setts are loose. All located opposite Four Winds along the layby Road Speed: 50MPH Approx Road Width: 6.0M. Approx Traffic Flow: low, depending on time of day. Approx HGV / Bus Traffic Flow: low Footways: no but there is a layby Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No
|  | Defect Number : D2229421 |  |  |  | Source:
|  | Date Raised:12/08/2022 10:41:57 |  |  |  | Date Completed:12/08/2022 12:15:00
|  | Location: Grass Verge outside the property Birchenholt |  |  |  | Priority : 24 Hours - Urgent
Description: Please clear glass from the verge
|  | Defect Number : D2229658 |  |  |  | Source:
|  | Date Raised:29/08/2022 11:25:00 |  |  |  | Date Completed:07/09/2022 10:08:00
|  | Location: The Ridges, Finchampstead. W3w:///hiker.softest.economics |  |  |  | Priority : 3 Days
Description: Bags of bricks and builders waste
|  | Defect Number : D2230395 |  |  |  | Source:
|  | Date Raised:10/10/2022 15:24:00 |  |  |  | Date Completed:24/10/2022 10:30:00
|  | Location: B3348 Wellingtonia Avenue, The Ridges, Finchampstead |  |  |  | Priority : 48 Hours
Description: Construction waste. ROOF tiling, wooden beans, food containers, nails, metal pieces
|  | Defect Number : D2231947 |  |  |  | Source:
|  | Date Raised:10/01/2023 14:30:00 |  |  |  | Date Completed:12/01/2023 11:42:00
|  | Location: The Ridges, finch ///fonts.offer.thumb |  |  |  | Priority : 3 Days
Description: Approx.40 black bags of garden waste and unidentified brown pellets
Enquiries In Date Order - Latest First
| Road Name: |  |  | 44706383 - The Ridges - Finchampstead, 44706383
|  | Enquiry Number: W2120337 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 09/03/2021 14:16:00 |  |  |  | Date Completed: 30/05/2022 13:19:22
Location: Four Winds, The Ridges, Finchampstead B3348
Description: Granite sets along road edge are loose or missing, over about 50m of the highway edge, opposite the property Four Winds. Risk that an HGV could throw these loose sets up into the path of other traffic of that a vehicle tyre could be damaged. WBC have had to undertake these repairs every couple of years and remedial work is now needed please.
Recomended Action:
|  | Enquiry Number: W2123059 |  |  |  | Assigned CSO:
|  | Date Raised: 19/05/2021 18:06:00 |  |  |  | Date Completed: 20/05/2021 12:00:00
Location: Junction The Ridges/Dell Road
Description: ?
Recomended Action:
|  | Enquiry Number: W2127305 |  |  |  | Assigned CSO:
|  | Date Raised: 01/09/2021 09:00:00 |  |  |  | Date Completed: 01/09/2021 09:12:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2127317 |  |  |  | Assigned CSO:
|  | Date Raised: 01/09/2021 11:23:00 |  |  |  | Date Completed: 02/09/2021 11:25:46
Location: ?
Description: Fly tipping and including furniture and rubbish was spotted here on 31st August (2021).
Recomended Action:
|  | Enquiry Number: W2129490 |  |  |  | Assigned CSO:
|  | Date Raised: 21/10/2021 16:13:00 |  |  |  | Date Completed: 21/10/2021 16:45:00
Location: Start of Ridges by Finch War Memorial
Description: ?
Recomended Action:
|  | Enquiry Number: W2237979 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 17/06/2022 10:33:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Opposite junction leading to 'North Court'
Description: Please forward for the attention of Highways Assets Noted as part of walked annual inspection 17.06.2022 - SN Not dangerous at time of observation - road is currently closed. Three part sign - junction to the right ahead and right left bend has been spun. Further consideration for remedy required Affixed to pole located in grass verge to back of footway Footway only available on one side Width of carriageway 5.50m Speed 50mph
Recomended Action:
|  | Enquiry Number: W2239368 |  |  |  | Assigned CSO:
|  | Date Raised: 26/07/2022 22:28:00 |  |  |  | Date Completed: 04/08/2022 10:54:00
Location: ?
Description: Fly tipped in the road. Appears to be garden building waste including potential asbestos. Neighbours have cleared to the side of the road as blocking traffic on The Ridges
Recomended Action:
|  | Enquiry Number: W2239370 |  |  |  | Assigned CSO:
|  | Date Raised: 26/07/2022 22:50:00 |  |  |  | Date Completed: 04/08/2022 00:00:00
Location: What3Words: pleaser.invented.good
Description: What3Words: pleaser.invented.good Road is clear and debris has been moved to the lay-by. Police attended and further assisted to clear road.
Recomended Action:
|  | Enquiry Number: W2239406 |  |  |  | Assigned CSO:
|  | Date Raised: 27/07/2022 14:36:00 |  |  |  | Date Completed: 04/08/2022 13:45:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2239534 |  |  |  | Assigned CSO:
|  | Date Raised: 30/07/2022 12:23:00 |  |  |  | Date Completed: 01/08/2022 14:12:00
Location: Opposite Pine Cottage, The Ridges, Finchampstead - 3 locations on South side of the road.
Description: Three separate loads of fencing, bricks, timber and general rubbish.
Recomended Action:
|  | Enquiry Number: W2239535 |  |  |  | Assigned CSO:
|  | Date Raised: 30/07/2022 12:31:00 |  |  |  | Date Completed: 04/08/2022 11:49:02
Location: Opposite Four Winds, The Ridges, Finchampstead - south side of the road.
Description: Granite kerb sets missing and loose. Need resetting. Risk of damage to vehicle tryes/wheels, or loose granite sets being thrown up by passing HGVs endangering following traffic. These repairs have been done every couple of years over the last decade.
Recomended Action:
|  | Enquiry Number: W2239757 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 04/08/2022 14:14:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: What was the beautiful monument
Description: Why is the footpath blocked between Jubilee Road and The Ridges. No warning. No means of walking to Crowthorne easily
Recomended Action:
|  | Enquiry Number: W2242045 |  |  |  | Assigned CSO:
|  | Date Raised: 10/10/2022 12:46:00 |  |  |  | Date Completed: 10/10/2022 17:20:00
Location: ?
Description: The fly tipping is blocking one lane of the road and the verge - there's quite a lot of debri
Recomended Action:
|  | Enquiry Number: W2242046 |  |  |  | Assigned CSO:
|  | Date Raised: 10/10/2022 12:55:00 |  |  |  | Date Completed: 10/10/2022 14:06:00
Location: The Ridges - next to the parking for dog walking
Description: Large amount of roofing lying in the road
Recomended Action:
|  | Enquiry Number: W2242053 |  |  |  | Assigned CSO:
|  | Date Raised: 10/10/2022 14:18:00 |  |  |  | Date Completed: 10/10/2022 14:28:00
Location: ?
Description: This is over part of the road and will be dangerous once it’s nightfall as the road is unlit
Recomended Action:
|  | Enquiry Number: W2242639 |  |  |  | Assigned CSO:
|  | Date Raised: 27/10/2022 02:11:00 |  |  |  | Date Completed: 27/10/2022 11:36:00
Location: The Ridges. Road is closed on the westward end near the war memorial, providing perfect, quiet roads for the our regular flytippers who enjoy visiting so much. They must be smug as hell knowing the council and police can't be bothered to do any preventative action after 4 unloads in approximately 3 months. Also, people walk their puppies here as it's a National Trust area. Do it for the puppies. Save their paws.
Description: Flytippers returned at 0129hrs on 27/10/22. Not photographed as this has been happening every two weeks or so for the past few months, and after we local residents cleared up significant construction waste from previous incidents, I don't really have further plans to go out there and breathe in yet more asbestos dust. Tried calling police on 101 - they referred back to the council. Curious to know if the council can actually prosecute without police involvement, or if we just accept people damaging public roads, vandalising and causing health hazards as something other than a crime. Oh and the potential for drivers getting into accidents when they travel along this 50mph road only to suddenly crash into a pile of bricks.
Recomended Action:
|  | Enquiry Number: W2345397 |  |  |  | Assigned CSO:
|  | Date Raised: 09/01/2023 15:14:00 |  |  |  | Date Completed: 12/01/2023 11:42:00
Location: B3348 The Ridges, Finchampstead. Western end of The Ridges beside the informal road side parking area.
Description: About 40 heavy black sacks containing some kind of grey pellets - possibly residual waste after sorting process?
Recomended Action:
|  | Enquiry Number: W2345416 |  |  |  | Assigned CSO:
|  | Date Raised: 09/01/2023 18:05:00 |  |  |  | Date Completed: 10/01/2023 09:00:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2346824 |  |  |  | Assigned CSO: Capital Schemes
|  | Date Raised: 02/02/2023 17:07:00 |  |  |  | Date Completed: 05/07/2023 16:51:00
Location: There is a drain cover that has sunk in the road. If you drive over the drain it is like hitting a pot hole.. Suprised this was not addressed by the council considering the two year closure of the road.
Description: ?
Recomended Action:
Orders In Date Order - Latest First
| Road Name: |  |  | 44706383 - The Ridges - Finchampstead, 44706383
|  | Order Number: ORD2100426 |  |  |  | Originator:
|  | Date Raised: 12/03/2021 13:58:01 |  |  |  | Date Completed: 27/11/2022 22:00:00
|  | Location: 44706383 - THE RIDGES - FINCHAMPSTEAD |  |  |  | Date Instructed: 12/03/2021 14:03:47
|  | Description: CONFIRMATION ORDER As discussed on site with (VH)12/3/2021 14:30pm Close The Ridges and create alternative footway. Use substantial barriers to prevent being moved, Diversion to be forwarded. Reason - Road subsidence 50/40mph Medium traffic count Width of carriageway in excess of 5.5m Footway on one side only FULL CLOSURE REQUIRED asap |  |  |  | Priority: (1) Days
|  | Order Number: ORD2100513 |  |  |  | Originator:
|  | Date Raised: 25/03/2021 10:50:39 |  |  |  | Date Completed: 05/07/2021 16:03:18
|  | Location: 44706383 - THE RIDGES - FINCHAMPSTEAD |  |  |  | Date Instructed: 26/03/2021 17:40:55
|  | Description: SM 2021-22 Programme - SD Treatments [2995 - WELLINGTONIA AVENUE] '80.030.005 Materials - Provisional Sum' code used to represent the cost of Restricted Working charges and 'H&J Lockseal' item. For full clarification please see attached Excel BoQ File. |  |  |  | Priority: 280 Days
|  | Order Number: ORD2201983 |  |  |  | Originator:
|  | Date Raised: 22/11/2022 02:24:25 |  |  |  | Date Completed: 26/11/2022 12:00:00
|  | Location: 44706383 - THE RIDGES - FINCHAMPSTEAD |  |  |  | Date Instructed: 22/11/2022 03:01:27
|  | Description: As discussed on site with VH Clean all signs on thre ridges and Wellingtonia AVenue Adjust sign near Dell Road Cut back vegetation around sign near junction of Jubilee Road Replace GIVE WAY sign on triangle Island Cut vegetation encroaching causing hazard into carriageway as discussed neat Jubilee Road Removing fencing, blocks and continuing to maintain TM and final removal of TM as discussed - This is being charged on original TM works order Road is currently closed but access mainteaned for residents, through road tho Dell Road width of carriageway in excess of 6.5m speed limit 50mph low to medium traffic count depending if road is open |  |  |  | Priority: 2 Days
|  | Order Number: ORD2202134 |  |  |  | Originator:
|  | Date Raised: 12/12/2022 11:30:59 |  |  |  | Date Completed: 18/11/2024 13:20:00
|  | Location: 44706383 - THE RIDGES - FINCHAMPSTEAD |  |  |  | Date Instructed: 12/12/2022 11:35:56
|  | Description: Replace weir gully cover and frame location: FMC id: FMC_20946 – opposite ridge end TM may be required. C2's to be applied for. Any problems call Notes: Near a bend Footpath - no Road width 6.8m - varies traffic count- medium depending on time of day |  |  |  | Priority: 109 Days
|  | Order Number: ORD2202233 |  |  |  | Originator:
|  | Date Raised: 19/12/2022 17:08:36 |  |  |  | Date Completed: 15/02/2023 08:30:00
|  | Location: 44706383 - THE RIDGES - FINCHAMPSTEAD |  |  |  | Date Instructed: 19/12/2022 17:10:05
|  | Description: remove roots by digging gully pot and remove any visible roots in outlet pipe. Then clear gully and jet outlet pipe. Location: FMC ID number: FMC_20946 TM may be required. Any problems call. Notes: Near a bend Approx road width 7m varies Footway – no |  |  |  | Priority: 31 Days
|  | V1.9 | 04/08/2025 13:55:42
Page 14 of 14