## Mole Road Sindlesham
Inspections In Date Order - Latest First
| Road Name: |  |  | 44701060 - Mole Road - Sindlesham, 44701060
|  | Date Due: 08/07/2025 00:00:00 |  |  | Date Completed: 30/06/2025 10:42:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 8 (3 Monthly) |  |  | Surface Condition: DRY
Defects Found: No
Inspection Comments: Section of carriageway undulates- Highways Assets have marked for repair - Warning signs situated either side
|  | Date Due: 18/05/2025 00:00:00 |  |  | Date Completed: 01/05/2025 11:34:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Walked Route 37 (6 Monthly) |  |  | Surface Condition: DRY
Defects Found: No
Inspection Comments: Damaged direction sign near roundabout observed - previously reported Damaged direction sign near roundabout observed - previously reported
|  | Date Due: 08/04/2025 00:00:00 |  |  | Date Completed: 04/04/2025 11:09:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 8 (3 Monthly) |  |  | Surface Condition: DRY
Defects Found: Yes
Inspection Comments: Undulation apparent within the carriageway outside Kasvene BMW and Fairview. Uneven signs present. Highways Assets previously advised - awaiting assessment and follow up ad deemed necessary by them. Damaged Arborfield and Nirvana Spa directional sign at junction with New Road - previously reported by SH
|  | Date Due: 08/01/2025 00:00:00 |  |  | Date Completed: 03/01/2025 14:35:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 8 (3 Monthly) |  |  | Surface Condition: DRY
Defects Found: Yes
Inspection Comments: 24hr D2448195 - D2448198 - D2448199 - D2448120 28-day D2448202
|  | Date Due: 18/11/2024 00:00:00 |  |  | Date Completed: 05/11/2024 12:35:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Walked Route 37 (6 Monthly) |  |  | Surface Condition: DRY
Defects Found: Yes
Inspection Comments: 24hr D2447357 - ref W2474682 24hr D2447357 - ref W2474682
|  | Date Due: 08/10/2024 00:00:00 |  |  | Date Completed: 26/09/2024 11:13:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 8 (3 Monthly) |  |  | Surface Condition: DAMP
Defects Found: No
Inspection Comments:
Defects In Date Order - Latest First
| Road Name: |  |  | 44701060 - Mole Road - Sindlesham, 44701060
|  | Defect Number : D2445708 |  |  |  | Source:
|  | Date Raised:05/08/2024 13:48:00 |  |  |  | Date Completed:23/08/2024 10:25:00
|  | Location: outside toad cottage opposite LC22 |  |  |  | Priority : 28 Days - Standard Response
Description: Please patch carriageway marked outside toad cottage opposite LC22 next to gully Size: 0.7x1.2 Material: HRA 30/14 PCC Recommended TM: 2way lights Carriageway 100ml depth Footway 75ml depth Road Speed: 40MPH Approx Road Width: 6m Approx Traffic Flow: low/med depending on time of day. Approx HGV / Bus Traffic Flow: low/med Footways: yes Near Bend: yes Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: no Note vehicles park along the Road Note adjacent kerbs may need to be moved/lifted and reset.
|  | Defect Number : D2445925 |  |  |  | Source:
|  | Date Raised:19/08/2024 09:54:00 |  |  |  | Date Completed:20/08/2024 10:37:00
|  | Location: They are at the front of my property where I leave my household recycling/waste. Several gas canisters used for catering dumped at several locations along the B3030 Mole Road between Church Lane and my house, Mole Park Bungalow. I collected them, along with 3 "Adopt a street" green bags of general litter and a metal cooker part? |  |  |  | Priority : Planned Maintenance
Description: Several gas canisters used for catering dumped at several locations along the B3030 Mole Road between Church Lane and my house, Mole Park Bungalow. I collected them, along with 3 "Adopt a street" green bags of general litter and a metal cooker part?
|  | Defect Number : D2446010 |  |  |  | Source: Inspection Area 1
|  | Date Raised:23/08/2024 11:16:00 |  |  |  | Date Completed:23/08/2024 11:51:00
|  | Location: Mole Rd just before Nirvana Spa |  |  |  | Priority : 2 Hour - Emergency
Description: Tree/ Shrub in road
|  | Defect Number : D2446011 |  |  |  | Source:
|  | Date Raised:23/08/2024 11:28:00 |  |  |  | Date Completed:01/01/9999 00:00:00
|  | Location: Mole Road outside property named Silver Birches. |  |  |  | Priority : 2 Hour - Emergency
Description: Please cut and remove fallen tree blocking footway and carriageway. Road Speed: 40MPH Approx Road Width: 6.0M Approx Traffic Flow: High, depending on time of day. Approx HGV / Bus Traffic Flow: Medium/High Footways: Yes Near Bend: No Near Pedestrian Crossing: Yes Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: Approx 150m from defect location Other: No
|  | Defect Number : D2446456 |  |  |  | Source:
|  | Date Raised:17/09/2024 08:24:00 |  |  |  | Date Completed:17/09/2024 09:02:00
|  | Location: Mole Road Approx 50m past junction with Ellis's Hill |  |  |  | Priority : 2 Hour - Emergency
Description: Please make safe pothole marked in CW. Please remove loose debris from carriageway. Road Speed: 50MPH Approx Road Width: 6.0M Approx Traffic Flow: High, depending on time of day. Approx HGV / Bus Traffic Flow: Medium. Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Approx 100m from defect Near School: No Near Roundabout: No Other: None
|  | Defect Number : D2446666 |  |  |  | Source: Inspection Area 1
|  | Date Raised:30/09/2024 08:38:00 |  |  |  | Date Completed:30/09/2024 10:10:00
|  | Location: Mole road - Sindesham in between Mole bridge farm and Newlands Lodge |  |  |  | Priority : 24 Hours - Urgent
Description: Dead Badger
|  | Defect Number : D2447310 |  |  |  | Source:
|  | Date Raised:02/11/2024 14:11:00 |  |  |  | Date Completed:19/11/2024 13:00:00
|  | Location: Mole Road, Sindlesham in layby near Ellis's Hill |  |  |  | Priority : 3 Days
Description: Yellow builders sack of waste Mole Road, Sindlesham in layby near Ellis's Hill This is asbestos and will need specialist removal - will arrange for this
|  | Defect Number : D2447357 |  |  |  | Source:
|  | Date Raised:05/11/2024 12:29:00 |  |  |  | Date Completed:06/11/2024 11:43:00
|  | Location: Exit area of Sindlesham Court |  |  |  | Priority : 24 Hours - Urgent
Description: L3:S3:- Inspection route:- 6mth Walk Please make safe potholes x 2 - marked # on instruction from HA - W2474682 # Road Speed:- 30MPH Approx Road Width:- 6M Approx Traffic Flow:- High depend on time of day Approx HGV / Bus Traffic Flow:- High depend on time of day Approx pedestrian volume:- Med Footways:- Yes - alternative footpath available Near Bend:- Yes Near Pedestrian Crossing:- Yes Near Traffic Signals:-No Near Junction:-Yes Near School:- No Near Roundabout:- mini roundabout Other hazard:- Sindlesham Court/ Nursing home/ Park TM recommended:- Signing & Guarding
|  | Defect Number : D2447543 |  |  |  | Source:
|  | Date Raised:18/11/2024 09:32:00 |  |  |  | Date Completed:19/11/2024 13:30:00
|  | Location: https://w3w.co/flops.sourced.carbonate. Mole Road, Sindelsham. Black bags, guttering and a metal frame.(See pics) |  |  |  | Priority : 3 Days
Description: https://w3w.co/flops.sourced.carbonate. Mole Road, Sindelsham. Black bags, guttering and a metal frame.(See pics) This is asbestos and already raised on D2447310 - awaiting collection. Will arrange for collection of the other items.
|  | Defect Number : D2447757 |  |  |  | Source: Inspection Area 1
|  | Date Raised:02/12/2024 11:35:00 |  |  |  | Date Completed:02/12/2024 13:00:00
|  | Location: Opposite reading training ground outside property 'woodside' |  |  |  | Priority : 2 Hour - Emergency
Description: Dead deer - blanket covering by resident - close to primary school
|  | Defect Number : D2447782 |  |  |  | Source:
|  | Date Raised:03/12/2024 12:37:00 |  |  |  | Date Completed:04/12/2024 08:35:00
|  | Location: Mole Road - What.three.words ///upwardly.sailing.contracts |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe pothole marked in CW. Road Speed: 50MPH Approx Road Width: 6.0M Approx Traffic Flow: Medium, depending on time of day. Approx HGV / Bus Traffic Flow: Low Footways: No Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No Other: No
|  | Defect Number : D2448195 |  |  |  | Source:
|  | Date Raised:03/01/2025 13:54:00 |  |  |  | Date Completed:03/01/2025 15:04:00
|  | Location: What 3 words ///bedrooms.steepest.lush Left side of carriageway heading towards Church Lane |  |  |  | Priority : 24 Hours - Urgent
Description: L3:S3:- Inspection route:- 3mth Driven Please make safe pothole marked Road Speed:- 50MPH Approx Road Width:- 6M Approx Traffic Flow:- High depend on time of day Approx HGV / Bus Traffic Flow:- Med Approx pedestrian volume:- Low - Cyclists Footways:- No Near Bend:- Yes Near Pedestrian Crossing:- No Near Traffic Signals:- No Near Junction:- No Near School:- No Near Roundabout:- No Other hazard:- No TM recommended:- Signing & Guarding
|  | Defect Number : D2448198 |  |  |  | Source:
|  | Date Raised:03/01/2025 14:03:00 |  |  |  | Date Completed:03/01/2025 17:56:00
|  | Location: What 3 words ///quaking.strength.mostly |  |  |  | Priority : 24 Hours - Urgent
Description: L3:S3:- Inspection route:- 3mth Driven 1 of 3 Please make safe pothole marked Road Speed:- 50MPH Approx Road Width:- 6M Approx Traffic Flow:- High depend on time of day Approx HGV / Bus Traffic Flow:- Med Approx pedestrian volume:- Low - Cyclists Footways:- No Near Bend:- Yes Near Pedestrian Crossing:- No Near Traffic Signals:- No Near Junction:- No Near School:- No Near Roundabout:- No Other hazard:- decline from hill TM recommended:- Signing & Guarding
|  | Defect Number : D2448199 |  |  |  | Source:
|  | Date Raised:03/01/2025 14:05:00 |  |  |  | Date Completed:03/01/2025 17:55:00
|  | Location: What 3 words ///quaking.strength.mostly |  |  |  | Priority : 24 Hours - Urgent
Description: L3:S3:- Inspection route:- 3mth Driven 2 of 3 Please make safe pothole marked Road Speed:- 50MPH Approx Road Width:- 6M Approx Traffic Flow:- High depend on time of day Approx HGV / Bus Traffic Flow:- Med Approx pedestrian volume:- Low - Cyclists Footways:- No Near Bend:- Yes Near Pedestrian Crossing:- No Near Traffic Signals:- No Near Junction:- No Near School:- No Near Roundabout:- No Other hazard:- decline from hill TM recommended:- Signing & Guarding
|  | Defect Number : D2448200 |  |  |  | Source:
|  | Date Raised:03/01/2025 14:06:00 |  |  |  | Date Completed:03/01/2025 17:49:00
|  | Location: What 3 words ///quaking.strength.mostly |  |  |  | Priority : 24 Hours - Urgent
Description: L3:S3:- Inspection route:- 3mth Driven 3 of 3 Please make safe pothole marked Road Speed:- 50MPH Approx Road Width:- 6M Approx Traffic Flow:- High depend on time of day Approx HGV / Bus Traffic Flow:- Med Approx pedestrian volume:- Low - Cyclists Footways:- No Near Bend:- Yes Near Pedestrian Crossing:- No Near Traffic Signals:- No Near Junction:- No Near School:- No Near Roundabout:- No Other hazard:- decline from hill TM recommended:- Signing & Guarding
|  | Defect Number : D2448202 |  |  |  | Source:
|  | Date Raised:03/01/2025 14:28:00 |  |  |  | Date Completed:15/01/2025 10:58:00
|  | Location: What 3 words ///bedrooms.steepest.lush |  |  |  | Priority : 28 Days - Standard Response
Description: L2 S2:- Inspection route:- 3mth Driven Please make safe pothole marked Defect size:- 0.7 x 0.9 Road Speed:- 50MPH Approx Road Width:- 6M Approx Traffic Flow:- High depend on time of day Approx HGV / Bus Traffic Flow:- Med Approx pedestrian volume:- Low - Cyclists Footways:- No Near Bend:- Yes Near Pedestrian Crossing:- No Near Traffic Signals:- No Near Junction:- Yes - Church Lane Near School:- No Near Roundabout:- No Other hazard:- No TM recommended:- Signing & Guarding 2 way temp traffic lights
|  | Defect Number : D2448676 |  |  |  | Source: Inspection Area 1
|  | Date Raised:27/01/2025 11:21:00 |  |  |  | Date Completed:27/01/2025 12:47:00
|  | Location: Mole road - Sindlesham outside Nirvana spa |  |  |  | Priority : 2 Hour - Emergency
Description: Manhole cover totally exposed
|  | Defect Number : D2448746 |  |  |  | Source:
|  | Date Raised:29/01/2025 10:57:00 |  |  |  | Date Completed:17/02/2025 14:52:00
|  | Location: Mole Road, as you go south to the jct with Church Lane, after the first layby |  |  |  | Priority : 28 Days - Standard Response
Description: Please patch marked area in CW. A closure will not be required. Size: 2.9 x 1.2 = 3.48m² Material: 30/14 hra Recommended TM: possible 2 way traffic lights Road Speed: 50MPH Approx Road Width: 6m Approx Traffic Flow: low to medium, depending on time of day. Approx HGV / Bus Traffic Flow: low to medium Footways: no Near Bend: yes Near Pedestrian Crossing: no Near Traffic Signals:no Near Junction: yes, further up Near School: no Near Roundabout: no Other: There is a water leak coming out of the tarmac that has been reported to Thames Water.
|  | Defect Number : D2449626 |  |  |  | Source:
|  | Date Raised:06/03/2025 09:00:00 |  |  |  | Date Completed:06/03/2025 14:40:00
|  | Location: Between AVS and Fine Drive Motors |  |  |  | Priority : 24 Hours - Urgent
Description: Please place out uneven road signs for the carriageway. As requested by Highway Assets Road Speed: 40MPH Approx Road Width: 6.0M Approx Traffic Flow: Low/Med Approx Traffic Flow: Low/med Footways: yes Near Bend: no Near Pedestrian crossing: No Near Traffic Signals: No Near Junction: Yes Near School: No Near roundabout: No
|  | Defect Number : D2449656 |  |  |  | Source:
|  | Date Raised:06/03/2025 14:01:00 |  |  |  | Date Completed:07/03/2025 08:23:00
|  | Location: marked at the entrance to nivana spa |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe pothole marked at the entrance to nivana spa Road Speed: 40mph Approx Road Width: 6.0M Approx Traffic Flow: low/med Approx HGV / Bus Traffic Flow: low/med Footways: yes Near Bend: yes Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: No Near Roundabout: no Raised by RB
|  | Defect Number : D2449657 |  |  |  | Source:
|  | Date Raised:06/03/2025 14:03:00 |  |  |  | Date Completed:01/01/9999 00:00:00
|  | Location: marked at the entrance to nivana spa |  |  |  | Priority : 28 Days - Standard Response
Description: Please patch Carriageway marked at the entrance to nivana spa Size: 2x0.6 Material:10mm TM:Rd closure Road Speed: 40mph Approx Road Width: 6.0M Approx Traffic Flow: low/med Approx HGV / Bus Traffic Flow: low/med Footways: yes Near Bend: yes Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: No Near Roundabout: no Raised by RB
|  | Defect Number : D2449658 |  |  |  | Source:
|  | Date Raised:06/03/2025 14:08:00 |  |  |  | Date Completed:07/03/2025 08:28:00
|  | Location: marked on the left side of the Carriageway traveling south towards Arborfield from Winnersh. Before the junction with church lane. |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe pothole marked on the left side of the Carriageway traveling south towards Arborfield from Winnersh. Before the junction with church lane. Road Speed: national speed into a 30mph Approx Road Width: 6.0M Approx Traffic Flow: low/med Approx HGV / Bus Traffic Flow: low/med Footways: no Near Bend: yes Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: No Near Roundabout: no Raised by RB
|  | Defect Number : D2550637 |  |  |  | Source: Inspection Area 1
|  | Date Raised:03/04/2025 09:04:00 |  |  |  | Date Completed:04/04/2025 10:17:00
|  | Location: ? |  |  |  | Priority : 24 Hours - Urgent
Description: ?
|  | Defect Number : D2550722 |  |  |  | Source:
|  | Date Raised:04/04/2025 09:04:00 |  |  |  | Date Completed:20/05/2025 12:27:00
|  | Location: Opposite entrance to Newlands House and stables |  |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 Missing 'left bend ahead' - 'max speed 40' sign Dimensions unknown - see attached historic image Two (2) fixing posts, located in grass verge are still present Width of carriageway approx 5.50m Speed 50mph Traffic count medium No footway present Two way TM / Signing and guarding may be required
|  | Defect Number : D2550731 |  |  |  | Source:
|  | Date Raised:04/04/2025 10:35:00 |  |  |  | Date Completed:04/04/2025 18:37:00
|  | Location: South bound lane approximately 30.0m prior to junction (opposite) with Church Lane |  |  |  | Priority : 24 Hours - Urgent
Description: L3 S3 Make safe marked 1.0m x 0.50m x 40mm HRA carriageway defect Damaged and uneven area Located to nearside of carriageway Width of carriageway 6.0m Speed 50mph Traffic count medium Solid and broken white central lane markings No footway present Approx 20.0m prior to change in speed limit to 30mph
|  | Defect Number : D2550735 |  |  |  | Source:
|  | Date Raised:04/04/2025 10:47:00 |  |  |  | Date Completed:15/04/2025 14:58:00
|  | Location: South bound lane approximately 30.0m prior to (and opposite) junction with Church Lane |  |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 Repair marked 2.50m x 1.00m x 100mm HRA carriageway defect Damaged and uneven area Refresh 2.50m x 150mm solid white edge of carriageway markings Make safe previously requested Located to nearside of carriageway Width of carriageway 6.0m Speed 50mph Traffic count medium Solid and broken white central lane markings No footway present Approx 20.0m prior to change in speed limit to 30mph
|  | Defect Number : D2552430 |  |  |  | Source:
|  | Date Raised:25/06/2025 07:10:00 |  |  |  | Date Completed:25/06/2025 09:30:00
|  | Location: Mole Road just before Navana spa |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe uneven/ dip in the CW by placing "slow" signs close to the defect and already existing warning signs at the side of the CW. Road Speed: 40MPH Approx Road Width: 6 M Approx Traffic Flow: high depending on time of day. Approx HGV / Bus Traffic Flow: low Footways: yes Near Bend: yes Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: no Other: defect is close to business entrances
Enquiries In Date Order - Latest First
| Road Name: |  |  | 44701060 - Mole Road - Sindlesham, 44701060
|  | Enquiry Number: W2470998 |  |  |  | Assigned CSO:
|  | Date Raised: 05/08/2024 10:22:00 |  |  |  | Date Completed: 23/08/2024 10:25:00
Location: Mole road - Sindlesham RG415DJ
Description: Road Sinking. The road towards Sindlesham, with the football club training ground on the right near to lighting column 22 is sinking again. This is gradually getting worse especially over the last month or so.
Recomended Action:
|  | Enquiry Number: W2471515 |  |  |  | Assigned CSO:
|  | Date Raised: 19/08/2024 08:28:00 |  |  |  | Date Completed: 20/08/2024 10:37:00
Location: They are at the front of my property where I leave my household recycling/waste. Will they be collected by the household waste team, next visit due on 30/08/24 or given the nature of some of the waste should it be picked up by the flytipping team?
Description: Several gas canisters used for catering dumped at several locations along the B3030 Mole Road between Church Lane and my house, Mole Park Bungalow. I collected them, along with 3 "Adopt a street" green bags of general litter and a metal cooker part?
Recomended Action:
|  | Enquiry Number: W2471704 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 23/08/2024 11:14:00 |  |  |  | Date Completed: 23/08/2024 11:51:00
Location: Mole road just before Nirvana Spa
Description: Tree/ Shrub in road
Recomended Action:
|  | Enquiry Number: W2472628 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 17/09/2024 08:34:00 |  |  |  | Date Completed: 24/10/2024 09:52:00
Location: Mile Road Approx 50m past junction with Ellis's Hill
Description: Please forward to HA noted by WE. Make safe raised for pothole D2446456. Area to patch measured as 9.0m x 1.5m. Please raise order for large patch to reinstate carriageway.
Recomended Action:
|  | Enquiry Number: W2473104 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 26/09/2024 13:18:00 |  |  |  | Date Completed: 02/10/2024 11:24:00
Location: Outside the BMW service garage
Description: Please send to Highways Assets as part of 3mth Drivens inspection There is a section of carriageway that had been repaired some time ago however when driving over it has started to dip & will need to be monitored 2.9 x 4.8 mtr
Recomended Action:
|  | Enquiry Number: W2473272 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 29/09/2024 13:45:00 |  |  |  | Date Completed: 17/10/2024 08:51:00
Location: Same as W2473281 / D2446666
Description: Dead badger
Recomended Action:
|  | Enquiry Number: W2473281 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 29/09/2024 20:26:00 |  |  |  | Date Completed: 30/09/2024 10:10:00
Location: Mole road - Sindesham in between Mole bridge farm and Newlands Lodge
Description: Dead Badger
Recomended Action:
|  | Enquiry Number: W2474682 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 29/10/2024 12:55:00 |  |  |  | Date Completed: 05/11/2024 12:38:00
Location: Entrance to Sindlesham/ Lord Harris court
Description: Please send to Highways Assets as part of Highways Inspection Carriageway Degradation noted at entrance of Sindlesham/ Lord Harris Court Verify whether adopted or private? To be discussed at weekly Highways Assets meeting before closing inspection route.
Recomended Action:
|  | Enquiry Number: W2474854 |  |  |  | Assigned CSO:
|  | Date Raised: 02/11/2024 14:00:00 |  |  |  | Date Completed: 19/11/2024 13:00:00
Location: In layby
Description: Yellow 1 tunne bag quater full of something
Recomended Action:
|  | Enquiry Number: W2475424 |  |  |  | Assigned CSO:
|  | Date Raised: 18/11/2024 08:37:00 |  |  |  | Date Completed: 19/11/2024 13:30:00
Location: https://w3w.co/flops.sourced.carbonate
Description: A whole sack of guttering, plus black bags and some kind of metal frame. This is another hot spot that could do with a camera.
Recomended Action:
|  | Enquiry Number: W2475862 |  |  |  | Assigned CSO:
|  | Date Raised: 28/11/2024 08:43:00 |  |  |  | Date Completed: 03/12/2024 12:36:00
Location: After Jnc to Ellis's Hill
Description: Water from an overflowing drain cover has spread across the road and frozen. On a bend with a hill so could cause an accident.
Recomended Action:
|  | Enquiry Number: W2475863 |  |  |  | Assigned CSO:
|  | Date Raised: 28/11/2024 08:44:00 |  |  |  | Date Completed: 04/12/2024 08:35:00
Location: Just before jnc to Ellis's Hill
Description: This recurring pothole is getting worse again. Creates a loud bang in the car if you hit it so must be quite deep. Not a safe place to stop so can't comment on size but it's occurred here before and sees a lot of traffic.
Recomended Action:
|  | Enquiry Number: W2475867 |  |  |  | Assigned CSO:
|  | Date Raised: 28/11/2024 09:47:00 |  |  |  | Date Completed: 03/12/2024 12:17:00
Location: Mole road - Sindlesham
Description: The custumer spined with his car because the road was icy the last night, he is requesting to add salt grit to that road. There is a water leak, but i have adviced him to contact Thame Water
Recomended Action:
|  | Enquiry Number: W2475964 |  |  |  | Assigned CSO:
|  | Date Raised: 01/12/2024 23:43:00 |  |  |  | Date Completed: 03/12/2024 12:40:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2475980 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 02/12/2024 11:13:00 |  |  |  | Date Completed: 02/12/2024 13:00:00
Location: Opposite reading training ground outside property 'woodside'
Description: Dead deer - blanket covering by resident
Recomended Action:
|  | Enquiry Number: W2476050 |  |  |  | Assigned CSO:
|  | Date Raised: 03/12/2024 10:14:00 |  |  |  | Date Completed: 09/12/2024 08:56:00
Location: Just before the speed increases to 50 going into Sindlesham.
Description: Very deep pot hole
Recomended Action:
|  | Enquiry Number: W2476056 |  |  |  | Assigned CSO:
|  | Date Raised: 03/12/2024 12:10:00 |  |  |  | Date Completed: 09/12/2024 08:56:00
Location: Mole road - Sindlesham
Description: big and deep pothole on the road
Recomended Action:
|  | Enquiry Number: W2476075 |  |  |  | Assigned CSO: Flooding
|  | Date Raised: 03/12/2024 14:36:00 |  |  |  | Date Completed: 01/08/2025 13:47:00
Location: Mole Road on bend Near Ellis's Hill
Description: Please forward to Flooding team noted by WE. Report of previous Flooding on bend. Unsure if this is from a blocked gully or a water leak. Unable to provide closer pictures due to Road Speed and proximity to tight bend.
Recomended Action:
|  | Enquiry Number: W2476157 |  |  |  | Assigned CSO:
|  | Date Raised: 05/12/2024 21:22:00 |  |  |  | Date Completed: 09/12/2024 08:57:00
Location: It is on the side of the road that approaches Arborfield before Church lane and the 30 mph sign.
Description: It is hard to locate exact place as I notice it when I am driving in the dark - I think it might even be a deep one - it is certainly in a position that catches car wheels and makes one think it will cause damage to my wheel. Very difficult to avoid without driving on other carriageway. As it is on the 50mph section it could cause serious damage to a vehicle and could cause further accident if cars swerve to miss it or it causes a wheel/tyre issue
Recomended Action:
|  | Enquiry Number: W2577358 |  |  |  | Assigned CSO:
|  | Date Raised: 09/01/2025 13:14:00 |  |  |  | Date Completed: 17/01/2025 11:22:00
Location: By Elliss hill jnc
Description: Pothole in road
Recomended Action:
|  | Enquiry Number: W2577367 |  |  |  | Assigned CSO:
|  | Date Raised: 09/01/2025 14:58:00 |  |  |  | Date Completed: 17/01/2025 11:24:00
Location: ///positions.paper.briefing
Description: ?
Recomended Action:
|  | Enquiry Number: W2577420 |  |  |  | Assigned CSO:
|  | Date Raised: 10/01/2025 14:39:00 |  |  |  | Date Completed: 13/01/2025 15:06:00
Location: ?
Description: Road closed signs still here and need to be removed
Recomended Action:
|  | Enquiry Number: W2577586 |  |  |  | Assigned CSO:
|  | Date Raised: 14/01/2025 15:04:00 |  |  |  | Date Completed: 17/01/2025 11:25:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2577588 |  |  |  | Assigned CSO:
|  | Date Raised: 14/01/2025 15:05:00 |  |  |  | Date Completed: 22/01/2025 10:08:00
Location: Just as you come off the roundabout down Mole's Road
Description: Dropped drain hole cover - impossible to avoid, unless going on the wrong side of the road as there is a kerb on the left hand side
Recomended Action:
|  | Enquiry Number: W2577736 |  |  |  | Assigned CSO: Highway Assets
|  | Date Raised: 17/01/2025 11:47:00 |  |  |  | Date Completed: 27/02/2025 09:02:00
Location: Mole Road, before the first bend as you go towards Arborfield, before the junction with Church Lane
Description: Please forward this matter to Highway Assets, noted by DE. We've had an enquiry about a new pothole on this section of the road. We have raised a make safe order for it but there are extensive cracks around it and the patch would be about 6.5m x 1m. Please consider the matter and discuss it during the weekly meeting.
Recomended Action:
|  | Enquiry Number: W2577904 |  |  |  | Assigned CSO: Flooding
|  | Date Raised: 22/01/2025 10:07:00 |  |  |  | Date Completed: 30/06/2025 10:25:00
Location: Mole Road, as you go southbound from the jct with New Road and Mill Lane
Description: Please forward this matter to Flooding, noted by DE. The drainage cover lid is slightly sunken and makes a noise every time cars go over it. Please arrange for the repair of the drainage cover.
Recomended Action:
|  | Enquiry Number: W2578048 |  |  |  | Assigned CSO:
|  | Date Raised: 25/01/2025 23:23:00 |  |  |  | Date Completed: 29/01/2025 09:28:00
Location: ?
Description: There is a huge dip in the road.
Recomended Action:
|  | Enquiry Number: W2578110 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 27/01/2025 11:19:00 |  |  |  | Date Completed: 27/01/2025 12:47:00
Location: Mole road - Sindlesham outside Nirvana spa
Description: Manhole cover exposed
Recomended Action:
|  | Enquiry Number: W2578759 |  |  |  | Assigned CSO:
|  | Date Raised: 07/02/2025 12:16:00 |  |  |  | Date Completed: 13/02/2025 13:28:00
Location: RG41 5DJ
Description: Between AVS and Fine Drive Motors (where the Toyota sign is) the road is uneven which may cause damage to suspension when going at 40 mph
Recomended Action:
|  | Enquiry Number: W2579512 |  |  |  | Assigned CSO:
|  | Date Raised: 23/02/2025 14:14:00 |  |  |  | Date Completed: 24/02/2025 11:37:00
Location: ?
Description: Two estate agents signs on corner of Mole Road and Wheatsheaf Close.
Recomended Action:
|  | Enquiry Number: W2579592 |  |  |  | Assigned CSO:
|  | Date Raised: 24/02/2025 16:40:00 |  |  |  | Date Completed: 01/01/9999 00:00:00
Location: Mole Road opposite Nirvana entrance
Description: Approx 2m pothole along the centre of the road opposite Nirvana entrance. Getting worse as patrons drive over it to enter and exit.
Recomended Action:
|  | Enquiry Number: W2580000 |  |  |  | Assigned CSO:
|  | Date Raised: 03/03/2025 22:47:00 |  |  |  | Date Completed: 07/03/2025 08:28:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2581034 |  |  |  | Assigned CSO:
|  | Date Raised: 25/03/2025 12:52:00 |  |  |  | Date Completed: 26/03/2025 10:00:00
Location: ?
Description: On Mole Road towards Sindlesham, with the football club training ground on the right near to lighting column 22 is still sinking (Mole road - Sindlesham RG415DJ). This has previously been logged and closed on log W2470998 showing as completed. This is getting worse on a daily basis, signs showing uneven road have been erected recently.
Recomended Action:
|  | Enquiry Number: W2581132 |  |  |  | Assigned CSO:
|  | Date Raised: 27/03/2025 12:45:00 |  |  |  | Date Completed: 31/03/2025 08:19:00
Location: You'll take off when you spot it on Mole road heading towards Nirvana spa direction from Barkham!
Description: The road here is dipping, was repaired about a year ago. It seems to be an underground subsidence issue, as the dip is increasing in size
Recomended Action:
|  | Enquiry Number: W2581404 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 03/04/2025 07:23:00 |  |  |  | Date Completed: 04/04/2025 10:17:00
Location: ?
Description: ?
Recomended Action:
|  | Enquiry Number: W2581468 |  |  |  | Assigned CSO: Inspection Area 1
|  | Date Raised: 04/04/2025 11:02:00 |  |  |  | Date Completed: 04/04/2025 13:46:00
Location: Approx 30.0m prior to (and opposite) junction with Church Lane
Description: Please forward for the attention of Traffic Management Noted as part of driven 3mth inspection 04.04.2025 - SN There is a missing advisory directional sign for 'Arborfield Chuch'. This isn't a mandatory sign so I'm unsure as to who would make the decision as to whether it should be replaced. The two upright posts to which it would be affixed are still in place. They are positioned in a grass verge No footway is present Width of adjacent carriageway 6.0m Speed 50mph Traffic count medium Further investigation and consideration for remedy required
Recomended Action:
|  | Enquiry Number: W2581647 |  |  |  | Assigned CSO:
|  | Date Raised: 09/04/2025 14:49:00 |  |  |  | Date Completed: 10/04/2025 08:15:00
Location: down from nirvana spa by the car garages
Description: very bad condition of the road and takes you by surprise as you cannot judge the deep crater until you r on it
Recomended Action:
|  | Enquiry Number: W2581793 |  |  |  | Assigned CSO:
|  | Date Raised: 14/04/2025 11:51:00 |  |  |  | Date Completed: 14/04/2025 14:48:00
Location: ?
Description: iThere is a major dip in the road and at 40 mph this is dangerous. It covers the whole side of the road goign toward Winnersh. This is outside of the BMW garage
Recomended Action:
|  | Enquiry Number: W2583557 |  |  |  | Assigned CSO:
|  | Date Raised: 05/06/2025 13:14:00 |  |  |  | Date Completed: 06/06/2025 08:50:00
Location: Opposite park / outside care home side
Description: Vegetation on footpath extremely overgrown - can barely walk on footway- no footway on other side of road - primary school nearby
Recomended Action:
|  | Enquiry Number: W2583584 |  |  |  | Assigned CSO:
|  | Date Raised: 06/06/2025 08:49:00 |  |  |  | Date Completed: 11/06/2025 08:46:00
Location: Mole Road, the highways verge bushes along 1 Mayfields
Description: Please forward this matter to Cleaner and Greener, noted by DE. The bushes along this footpath are overgrown and force pedestrians to lean very close to the road. There is also no space for 2 people walking past each other. Please consider the matter and arrange for cutting back the overgrown bushes.
Recomended Action:
|  | Enquiry Number: W2584142 |  |  |  | Assigned CSO:
|  | Date Raised: 20/06/2025 18:10:00 |  |  |  | Date Completed: 25/06/2025 09:30:00
Location: Mole Road. Near the MOT centre and on the carriage way that approaches the fitness centre
Description: Signs suggest that this has previously been noticed as a piece of damaged carriageway however it has deteriorated significantly recently . Drivers who approach it at normal road speed are launching as they traverse the significant dip in the road.
Recomended Action:
|  | Enquiry Number: W2584890 |  |  |  | Assigned CSO: Flooding
|  | Date Raised: 11/07/2025 11:40:00 |  |  |  | Date Completed: 18/07/2025 12:27:00
Location: Mole Road between the mini roundabout and Nirvana Spa.
Description: The three manholes between the mini roundabout and Nirvana Spa have dropped and cars trying to avoid them are in danger of hitting oncoming traffic. The one nearest the roundabout is the worse.
Recomended Action:
|  | Enquiry Number: W2585574 |  |  |  | Assigned CSO:
|  | Date Raised: 29/07/2025 16:21:00 |  |  |  | Date Completed: 30/07/2025 08:20:00
Location: wheatsheaf close junction with mole road
Description: road signage has been left after road works have been completed and cones have also been left down this road
Recomended Action:
|  | Enquiry Number: W2585629 |  |  |  | Assigned CSO:
|  | Date Raised: 30/07/2025 17:45:00 |  |  |  | Date Completed: 01/08/2025 09:24:00
Location: It is on mole road, just along from Nirvana spa on the side if you were approaching from the Arborfield area. It is located in the section that has temporary signage stating ramp.
Description: The road has sunken to an unacceptable level. It has been like this for 3 years and has gotten worse. There has only been temporary signage put up recently warning drivers of a ramp, but it needs repairing as it is dangerous when you go over it in a vehicle.
Recomended Action:
Orders In Date Order - Latest First
| Road Name: |  |  | 44701060 - Mole Road - Sindlesham, 44701060
|  | Order Number: ORD2500170 |  |  |  | Originator:
|  | Date Raised: 21/01/2025 19:19:11 |  |  |  | Date Completed: 23/01/2025 13:08:00
|  | Location: 44701060 - MOLE ROAD - SINDLESHAM |  |  |  | Date Instructed: 21/01/2025 19:23:14
|  | Description: IJet and clear silt from short section of culvert from ditch to manhole and then from the manhole under the road to the receiving ditch on the west side (see attached drawing). In view of busyness of road it is recommended jetter is parked on access to Reading Football Club Training Ground and this would probably circumvent the need for TM. If required, TM for Mole Road should be based upon the following risk criteria: Road Speed: National Speed 50MPH Approx Road Width: 6m Approx Traffic Flow: Heavy Approx HGV / Bus Traffic Flow: low Footways: No Near Bend: No Near Pedestrian Crossing: No. Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout:No |  |  |  | Priority: 3 Days
|  | Order Number: ORD2500558 |  |  |  | Originator:
|  | Date Raised: 05/03/2025 11:18:10 |  |  |  | Date Completed: 15/04/2025 12:26:00
|  | Location: 44701060 - MOLE ROAD - SINDLESHAM |  |  |  | Date Instructed: 05/03/2025 11:31:20
|  | Description: Picture(s) attached for reference. Location: Mole Road - Sindlesham - Near the layby that's near Ellis Hill Works: 10.0m x 1.50m HRA patch - There is another HRA patch near this one that's to be done at the same time - on w/order Suggested Traffic Management: Two-way TC. Road Speed: 50mph. Approx Road Width: 5.5m. Approx Traffic Flow: Low/Medium/High, depending on time of day. Approx HGV Traffic Flow: Low. Footways: No. Near Bend: No. Near a Hill: No. Near Pedestrian Crossing: No. Near Traffic Signals: No. Near Junction: Yes. Near School: No. Near Roundabout: No. Please supply pictures of completed works. |  |  |  | Priority: 77 Days
|  | Order Number: ORD2500559 |  |  |  | Originator:
|  | Date Raised: 05/03/2025 11:35:51 |  |  |  | Date Completed: 15/04/2025 09:46:00
|  | Location: 44701060 - MOLE ROAD - SINDLESHAM |  |  |  | Date Instructed: 05/03/2025 11:37:20
|  | Description: Picture(s) attached for reference. Location: Mole Road - Sindlesham - Near the layby that's near Ellis Hill Works: 8.40m x 1.50m HRA patch - There is another HRA patch near this one that's to be done at the same time - on w/order ORD2500558 Suggested Traffic Management: Two-way TC (Lights are on order ORD2500558) Road Speed: 50mph. Approx Road Width: 5.5m. Approx Traffic Flow: Low/Medium/High, depending on time of day. Approx HGV Traffic Flow: Low. Footways: No. Near Bend: No. Near a Hill: No. Near Pedestrian Crossing: No. Near Traffic Signals: No. Near Junction: Yes. Near School: No. Near Roundabout: No. |  |  |  | Priority: 77 Days
|  | Order Number: ORD2500817 |  |  |  | Originator:
|  | Date Raised: 10/04/2025 15:01:27 |  |  |  | Date Completed: 15/05/2025 16:00:00
|  | Location: 44701060 - MOLE ROAD - SINDLESHAM |  |  |  | Date Instructed: 10/04/2025 15:03:12
|  | Description: Picture(s) attached for reference. Location: Mole Road by the lay-by and other patches to be done during the closure. Works: 6.00m x 1.10m HRA patch (Marked as 4). Suggested Traffic Management: To be carried out within the road closure. Road Speed: 0mph closure. Approx Road Width: 5.5m. Approx Traffic Flow: 0. Approx HGV Traffic Flow: 0. Footways: No. Near Bend: No. Near a Hill: No. Near Pedestrian Crossing: No. Near Traffic Signals: No. Near Junction: Yes. Near School: No. Near Roundabout: No. Please supply pictures of completed works. |  |  |  | Priority: 30 Days
|  | Order Number: ORD2500835 |  |  |  | Originator:
|  | Date Raised: 15/04/2025 07:47:29 |  |  |  | Date Completed: 15/04/2025 09:41:00
|  | Location: 44701060 - MOLE ROAD - SINDLESHAM |  |  |  | Date Instructed: 15/04/2025 07:52:09
|  | Description: PATCH 3 6M X 1.4M HRA WITH CHIPS ORDER NOT PLACED ROAD CLOSURE ALREADY IN PLACE |  |  |  | Priority: 2 Days
|  | Order Number: ORD2500845 |  |  |  | Originator:
|  | Date Raised: 16/04/2025 08:08:18 |  |  |  | Date Completed: 17/04/2025 12:25:00
|  | Location: 44701060 - MOLE ROAD - SINDLESHAM |  |  |  | Date Instructed: 16/04/2025 08:13:11
|  | Description: C/WAY DEFECT BY ROUNDABOUT DEFECT 4 & 5 MAKE INTO ONE PERM REPAIR 12 X 1.5M ORDER NOT RAISED ROAD CLOSURE ALREADY IN PLACE |  |  |  | Priority: 1 Days
|  | Order Number: ORD2500846 |  |  |  | Originator:
|  | Date Raised: 16/04/2025 08:19:33 |  |  |  | Date Completed: 19/06/2025 07:36:00
|  | Location: 44701060 - MOLE ROAD - SINDLESHAM |  |  |  | Date Instructed: 16/04/2025 08:21:22
|  | Description: INCREASED PATCH 4 BY 5.5M AGREED ON SITE HRA WITH CHIPS TOTAL PATCH SIZE 8 X 1M |  |  |  | Priority: 1 Days
|  | Order Number: ORD2500914 |  |  |  | Originator:
|  | Date Raised: 01/05/2025 12:09:39 |  |  |  | Date Completed: 01/01/9999 00:00:00
|  | Location: 44701060 - MOLE ROAD - SINDLESHAM |  |  |  | Date Instructed: 01/05/2025 12:17:18
|  | Description: Picture(s) attached for reference. Location: Mole Road - Sindlesham - Outside BMW servicing and White House Motors. Works: 3.00m x 5.30m HRA and PCC. Level c/way to remove dip. Suggested Traffic Management: May require road closure. Road Speed: 30mph. Approx Road Width: 6.3m. Approx Traffic Flow: Low/Medium/High, depending on time of day. Approx HGV Traffic Flow: Low. Footways: Yes. Near Bend: No. Near a Hill: No. Near Pedestrian Crossing: No. Near Traffic Signals: No. Near Junction: No. Near School: No. Near Roundabout: No. Please supply pictures of completed works. |  |  |  | Priority: 31 Days
|  | V1.9 | 11/08/2025 15:04:43
Page 26 of 26