## Defects
Defects In Date Order - Latest First
| Road Name: |  |  | 44701102 - Nine Mile Ride - Wokingham, 44701102
|  | Defect Number : D2231405 |  |  | Source: Inspection Area 3
|  | Date Raised:09/12/2022 08:32:00 |  |  | Date Completed:09/12/2022 11:47:10
|  | Location: Kerbside by # The Oaks # SGN works opposite & Road closure |  |  | Priority : 24 Hours - Urgent
Description: S3 L3 Please make safe uneven carrigeway - marked Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: Low Approx HGV / Bus Traffic Flow: Low Approx pedestrian volume along Low Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No Other hazard: SGN works TM recommended: Section of Road currently closed SGN access available
|  | Defect Number : D2231450 |  |  | Source:
|  | Date Raised:14/12/2022 07:29:06 |  |  | Date Completed:20/12/2022 08:23:01
|  | Location: lift manhole, in center of carriageway, and astertain ownership. In ESRI- WBC manholes are shown to be located in footway location:on carriageway, By Johnson and Johnson Bus stop on NINE MILE RIDE, WOKINGHAM, RG40 3DY. Nearest landmark: roundabout with Old Wokingham Road - see map tab for exact location or history number map tab history number W2244369 Please send feedback to: TM may be required. any problems call Notes: approx road width 11.2m varies Near a roundabout traffic count - medium/high |  |  | Priority : 24 Hours - Urgent
Description: ?
|  | Defect Number : D2231705 |  |  | Source:
|  | Date Raised:04/01/2023 09:07:27 |  |  | Date Completed:04/01/2023 19:55:00
|  | Location: Clear gullies including jetting gully outlets. Also, check condition of nearest surface water manhole / soakaway. remove any remaining standing water Location: Side road off Nine Mile Ride. Outside No.28 - refer to attached plan edged in red TM may be required. any problems call Notes: Near a junction Near a bend on side road |  |  | Priority : 24 Hours - Urgent
Description: ?
|  | Defect Number : D2231984 |  |  | Source:
|  | Date Raised:12/01/2023 07:51:00 |  |  | Date Completed:20/01/2023 13:01:00
|  | Location: Litter along Nine Mile Ride: Wokingham Without Parish Council Please could litter be cleared along Nine Mile Ride in the parish. We cannot allow outr litter volunteers to clear this busy road because of the safety risks. We suspect a Highways Licence would be required to enable this to be done effectively. |  |  | Priority : Planned Maintenance
Description: Litter along Nine Mile Ride: Wokingham Without Parish Council Please could litter be cleared along Nine Mile Ride in the parish. We cannot allow outr litter volunteers to clear this busy road because of the safety risks. We suspect a Highways Licence would be required to enable this to be done effectively.
|  | Defect Number : D2232331 |  |  | Source:
|  | Date Raised:23/01/2023 10:19:00 |  |  | Date Completed:24/01/2023 09:36:24
|  | Location: Close to Johnson and Johnson Bus Stop |  |  | Priority : 24 Hours - Urgent
Description: Please remove loose material and make safe around sunk manhole cover. Road Speed: 40MPH. Approx Road Width: 7.0M. Approx Traffic Flow: High, depending on time of day. Approx HGV / Bus Traffic Flow: Med Footways: Yes Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: Yes
|  | Defect Number : D2232747 |  |  | Source: Inspection Area 3
|  | Date Raised:06/02/2023 12:07:00 |  |  | Date Completed:07/02/2023 11:52:25
|  | Location: Nine Miie Ride at Pinewood Campus. |  |  | Priority : 24 Hours - Urgent
Description: L3 S3 cat 1b. Please make safe cway damage, marked. Water leak affecting cway has been reported to SE Water. Located at entrance to Johnson & Johnson. Suggest controlling traffic Under Stop / Go for short duration of make safe, Marshall any vehicles in and out of Johnson & Johnson. Sign well back on Nine Mile Ride. Road Speed: 40MPH Approx Road Width: 6M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: medium Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: YES, Johnson & Johnson entrance. Near School: no Near Roundabout: no Other hazard: Avoid peak hours. Overhead cable. TM recommended yes
|  | Defect Number : D2334369 |  |  | Source:
|  | Date Raised:04/04/2023 10:24:00 |  |  | Date Completed:04/04/2023 10:59:26
|  | Location: Nine Mile Ride 50m from roundabout at Old Wokingham Road. Opposite pond. |  |  | Priority : 2 Hour - Emergency
Description: L4 S4 cat 1a. Please make safe cway pothole marked. Please clear up tarmac debris in kerbline. Road Speed: 40MPH Approx Road Width: 6M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: yes Other hazard: TM recommended yes
|  | Defect Number : D2334390 |  |  | Source:
|  | Date Raised:04/04/2023 14:11:00 |  |  | Date Completed:04/05/2023 10:00:00
|  | Location: Opp 10 Kingsbridge Cottages off Nine Mile Ride |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. 1 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked. 0.8 x 0.5 10mm DBM. Edge of cway. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2334391 |  |  | Source:
|  | Date Raised:04/04/2023 14:22:00 |  |  | Date Completed:04/05/2023 11:15:00
|  | Location: Opposite 11 Kingsbridge cottages off Nine Mile Ride |  |  | Priority : 28 Days - Standard Response
Description: 2 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked. 1.8 x 0.5 10mm DBM. Edge of cway. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2334392 |  |  | Source:
|  | Date Raised:04/04/2023 14:24:00 |  |  | Date Completed:04/05/2023 13:30:00
|  | Location: Opposite 11 Kingsbridge cottages off Nine Mile Ride |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. 3 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked. 0.8 x 0.5 10mm DBM. Edge of cway. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2334394 |  |  | Source:
|  | Date Raised:04/04/2023 14:28:00 |  |  | Date Completed:04/05/2023 12:45:00
|  | Location: Opposite 12 Kingsbridge cottages off Nine Mile Ride |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. 4 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked. 4.6 x x 0.7 10mm DBM. Edge of cway. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2334395 |  |  | Source:
|  | Date Raised:04/04/2023 14:31:00 |  |  | Date Completed:04/05/2023 11:15:00
|  | Location: Opposite 14 Kingsbridge cottages off Nine Mile Ride |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. 5 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked. 1.5 x 0.6 10mm DBM. Edge of cway. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2334396 |  |  | Source:
|  | Date Raised:04/04/2023 14:34:00 |  |  | Date Completed:04/05/2023 10:00:00
|  | Location: Opposite 15 Kingsbridge cottages off Nine Mile Ride |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. 6 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked. 0.8 x 0.5 10mm DBM. Centre of cway. 2.3m Road space left, 3.9m if using layby. Very low traffic count. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2334399 |  |  | Source:
|  | Date Raised:04/04/2023 14:41:00 |  |  | Date Completed:04/05/2023 12:15:00
|  | Location: Opposite 23/24 Kingsbridge cottages off Nine Mile Ride |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. 7 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked, around gully. 1m2 10mm DBM. Edge of cway. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
Orders In Date Order - Latest First
| Road Name: |  |  | 44701102 - Nine Mile Ride - Wokingham, 44701102
|  | Order Number: ORD2202076 |  |  | Originator:
|  | Date Raised: 06/12/2022 08:39:57 |  |  | Date Completed: 22/12/2022 10:15:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  | Date Instructed: 06/12/2022 08:43:14
|  | Description: Clear 3 gullies including jetting gully outlets . Also, jet heawalls. Refer to attached plan edged in red Location: between junction with Palmer close and THREE BIRCHES, NINE MILE RIDE, WOKINGHAM, RG40 3DY - Refer to attached plan edged in red TM may be required. Any problems call Notes: Near a junction Near a roundabout approx. road width 5.2m varies |  |  | Priority: 28 Days
|  | Order Number: ORD2202226 |  |  | Originator:
|  | Date Raised: 19/12/2022 16:30:04 |  |  | Date Completed: 04/01/2023 13:53:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  | Date Instructed: 19/12/2022 16:30:58
|  | Description: Free 1 jammed gully lid - Location: FMC ID number: FMC_20909 TM may be required. Any problems call Near a bend Near a bridge Footway – yes Near mobile homes site Approx. road width 5.4m varies traffic count medium/high depending on time of day |  |  | Priority: 31 Days
|  | Order Number: ORD2300527 |  |  | Originator:
|  | Date Raised: 17/03/2023 07:56:24 |  |  | Date Completed: 20/03/2023 10:00:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  | Date Instructed: 17/03/2023 08:02:22
|  | Description: Lamp Column 112(38) (id:16979) Approx. 155m east of Heathlands Rd x-rds Steel 8m Fabrikat 8M01A(114)PT Philips SGS203/100GTG 100w SP, LED Philips Luma 10500lm 4000k, Telensa Telecell NEMA+In Dim M (000339540200) Both units 112 & 113 have been reported as out of light, please investigate and repair on first visit, if possible, if not please advise of further works that are required. Last Telensa communication was: - 03.03.23 |  |  | Priority: 41 Days
|  | Order Number: ORD2300603 |  |  | Originator:
|  | Date Raised: 30/03/2023 20:14:12 |  |  | Date Completed: 19/04/2023 11:30:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  | Date Instructed: 30/03/2023 20:15:26
|  | Description: Reflective "Keep Left" bollard no. B631(NON) Nine Mile Ride (B3430), Wokingham Without (On island app. 250m west of Old Wokingham Rd rbt) - unique ID 026539. Clean bollard shell - currently very dirty which is reducing visibility/refelectivity (see W2349535). |  |  | Priority: 28 Days
|  | Order Number: ORD2300604 |  |  | Originator:
|  | Date Raised: 30/03/2023 20:18:21 |  |  | Date Completed: 19/04/2023 11:15:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  | Date Instructed: 30/03/2023 20:19:14
|  | Description: Reflective "Keep Left" bollard no. B633(NON) Nine Mile Ride (B3430), Wokingham Without (On island app. 245m west of Old Wokingham Rd rbt) - unique ID 026540. Clean bollard shell - currently very dirty which is reducing visibility/refelectivity (see W2349535). |  |  | Priority: 28 Days
|  | Order Number: ORD2300655 |  |  | Originator:
|  | Date Raised: 04/04/2023 20:56:55 |  |  | Date Completed: 11/04/2023 08:19:32
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  | Date Instructed: 04/04/2023 21:26:47
|  | Description: Defect: Make Safe x33 Potholes Location: Nine Mile Ride - Palmer Close-Old Wokingham Road R'about (see Photos) Carriageway or Footway: C/Way Photos attached: Yes Mapping attached: No Road Speed: 40 MPH Approx Road Width: 6m Approx Traffic Flow: Medium to High Footways: One side until after Pinewood Campus Near Bend: No Near a Hill: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes - Pinewood campus Near School: No Near Roundabout: No Additional TM: No |  |  | Priority: 1 Days
|  | V1.9 | 15/04/2026 11:21:24
Page 23 of 23