## Inspections
Inspections In Date Order - Latest First
| Road Name: |  |  | 44701102 - Nine Mile Ride - Wokingham, 44701102
|  | Date Due: 08/10/2023 00:00:00 |  |  | Date Completed: 28/09/2023 14:52:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 9 (3 Monthly) |  |  | Surface Condition: DRY
Defects Found: No
Inspection Comments: Several parked vehicles by Kingsbridge cottages
|  | Date Due: 08/07/2023 00:00:00 |  |  | Date Completed: 27/06/2023 11:50:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 9 (3 Monthly) |  |  | Surface Condition: DRY
Defects Found: No
Inspection Comments: Scheduled resurfacing programme 28th June 23 for 3 days Scheduled resurfacing programme 28th June 23 for 3 days Observed white road markings at gullies
|  | Date Due: 02/07/2023 00:00:00 |  |  | Date Completed: 22/06/2023 11:03:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Walked Route 54 (12 Monthly) |  |  | Surface Condition: DRY
Defects Found: Yes
Inspection Comments: Email sent to Streetworks to report sign post installed at an angle on verge, following SSE works, Junction with Ravenswood. Observed areas of cway, marked up for repair work, on approach to Heathlands Rd junction. W2353625 to Highways Assets for (40) faded on cway, Junction with Honey Hill. W2353626 to Highways Assets for 2x directional arrows faded on cway, opp Junction with Honey Hill. D2336710 24hr. D2336713 24hr. D2336714 24hr. D2336715 24hr. W2353637 to Highways Assets for cway degradation 40m from roundabout at Old Wokingham Road. W2353640 to Highways Assets for (40) faded on cway 25m in from roundabout at Old Wokingham Road. D2336710 24hr. D2336713 24hr. D2336714 24hr. D2336715 24hr. W2353637 to Highways Assets for cway degradation 40m from roundabout at Old Wokingham Road. W2353640 to Highways Assets for (40) faded on cway 25m in from roundabout at Old Wokingham Road.
|  | Date Due: 08/04/2023 00:00:00 |  |  | Date Completed: 04/04/2023 15:31:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 9 (3 Monthly) |  |  | Surface Condition: DRY
Defects Found: Yes
Inspection Comments: D2334369 2hr. W2349979 to Highways Assets for cway degradation, 30m before Old Wokingham Road roundabout. Found rocking frame and cover / tarmac debris across cway, opp pond, near Johnson & Johnson. Streetworks informed SE Water, who attended to set up 2 way Signals for repair work to follow. Observed multiple locations of surface worn, marked up for remedial work. W2349981 to Highways Assets for worn markings in cway (40). D2334377. D2334390, D2334391, D2334392, D2334394, D2334395, D2334396, D2334399. All in Kingsbridge cottages off Nine Mile Ride.
|  | Date Due: 08/01/2023 00:00:00 |  |  | Date Completed: 04/01/2023 08:28:00
|  | Inspector: |  |  | Weather: ?
|  | Route: Driven Route 9 (3 Monthly) |  |  | Surface Condition: WET
Defects Found: Yes
Inspection Comments: Section of Road with standing water following heavy rainfall. Cway degradation previously reported to Highways Assets Cway degradation previously reported to Highways Assets
Defects In Date Order - Latest First
| Road Name: |  |  | 44701102 - Nine Mile Ride - Wokingham, 44701102
|  | Defect Number : D2230260 |  |  |  | Source:
|  | Date Raised:04/10/2022 10:59:00 |  |  |  | Date Completed:12/10/2022 12:49:00
|  | Location: Nine Mile Ride, Wokingham, opposite Palmer Close. |  |  |  | Priority : 3 Days
Description: Mostly garden/green waste, mixed with DIY waste.
|  | Defect Number : D2230288 |  |  |  | Source:
|  | Date Raised:05/10/2022 09:54:00 |  |  |  | Date Completed:05/10/2022 12:42:34
|  | Location: Marked outside dunedin |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe pothole marked outside Dunedin. Permanent repair if possible, but please let me know Road Speed: 40MPH Approx Road Width: 6.0M. Approx Traffic Flow: med, depending on time of day. Approx HGV / Bus Traffic Flow: med Footways: yes Near Bend: no Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No
|  | Defect Number : D2230347 |  |  |  | Source:
|  | Date Raised:10/10/2022 11:37:00 |  |  |  | Date Completed:14/10/2022 11:30:00
|  | Location: ? |  |  |  | Priority : 28 Days - Standard Response
Description: Please sweep to stop drains/gullies getting blocked due on the 12th of October
|  | Defect Number : D2230359 |  |  |  | Source:
|  | Date Raised:10/10/2022 14:33:00 |  |  |  | Date Completed:04/11/2022 10:30:00
|  | Location: ? |  |  |  | Priority : 28 Days - Standard Response
Description: Please sweep along here or provide a quote for encroachment removal if required. Thank you
|  | Defect Number : D2230994 |  |  |  | Source:
|  | Date Raised:17/11/2022 13:30:48 |  |  |  | Date Completed:18/11/2022 10:56:11
|  | Location: between house numbers 3 and 6 |  |  |  | Priority : 24 Hours - Urgent
Description: 5 little potholes making 1 big one
|  | Defect Number : D2231081 |  |  |  | Source:
|  | Date Raised:22/11/2022 09:38:00 |  |  |  | Date Completed:23/11/2022 09:30:00
|  | Location: Marked around manhole cover |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe around manhole cover Permanent repair if possible, but please let me know Road Speed: i believe 40MPH Approx Road Width: 6.0M. Approx Traffic Flow: med/high, depending on time of day. Approx HGV / Bus Traffic Flow: med Footways: yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: yes Near School: No Near Roundabout: yes
|  | Defect Number : D2231141 |  |  |  | Source:
|  | Date Raised:24/11/2022 10:41:13 |  |  |  | Date Completed:24/11/2022 12:09:47
|  | Location: There is a footpath that runs from Old Wokingham Road Crowthorne along the south side of Nine Mile Ride. It badly needs some attention to clean it off and make it safe. Footpath has been covered up a lot in places and it’s dangerous. the footway alongside the Nine Mile Ride on the South side |  |  |  | Priority : Planned Maintenance
Description: Pic attached - reminder as on leaf schedule for week commencing 28th
|  | Defect Number : D2231155 |  |  |  | Source:
|  | Date Raised:25/11/2022 12:58:38 |  |  |  | Date Completed:25/11/2022 14:54:46
|  | Location: lift manhole, in center of carriageway,(covered with trench plate) and astertain ownership. WBC manhole in footway location: outside SHAMROCK VILLA, NINE MILE RIDE, WOKINGHAM, RG40 3DY history number W2243677 Please send feedback to: TM may be required. any problems call Notes: approx road width 11.2m varies Near a roundabout traffic count - medium/high |  |  |  | Priority : 24 Hours - Urgent
Description: 25/11 - not sure used right BOQ, please amend as required
|  | Defect Number : D2231405 |  |  |  | Source: Inspection Area 3
|  | Date Raised:09/12/2022 08:32:00 |  |  |  | Date Completed:09/12/2022 11:47:10
|  | Location: Kerbside by # The Oaks # SGN works opposite & Road closure |  |  |  | Priority : 24 Hours - Urgent
Description: S3 L3 Please make safe uneven carrigeway - marked Road Speed: 30MPH Approx Road Width: 6M Approx Traffic Flow: Low Approx HGV / Bus Traffic Flow: Low Approx pedestrian volume along Low Footways: Yes one side Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: No Near School: No Near Roundabout: No Other hazard: SGN works TM recommended: Section of Road currently closed SGN access available
|  | Defect Number : D2231450 |  |  |  | Source:
|  | Date Raised:14/12/2022 07:29:06 |  |  |  | Date Completed:20/12/2022 08:23:01
|  | Location: lift manhole, in center of carriageway, and astertain ownership. In ESRI- WBC manholes are shown to be located in footway location:on carriageway, By Johnson and Johnson Bus stop on NINE MILE RIDE, WOKINGHAM, RG40 3DY. Nearest landmark: roundabout with Old Wokingham Road - see map tab for exact location or history number map tab history number W2244369 Please send feedback to: TM may be required. any problems call Notes: approx road width 11.2m varies Near a roundabout traffic count - medium/high |  |  |  | Priority : 24 Hours - Urgent
Description: ?
|  | Defect Number : D2231705 |  |  |  | Source:
|  | Date Raised:04/01/2023 09:07:27 |  |  |  | Date Completed:04/01/2023 19:55:00
|  | Location: Clear gullies including jetting gully outlets. Also, check condition of nearest surface water manhole / soakaway. remove any remaining standing water Location: Side road off Nine Mile Ride. Outside No.28 - refer to attached plan edged in red TM may be required. any problems call Notes: Near a junction Near a bend on side road |  |  |  | Priority : 24 Hours - Urgent
Description: ?
|  | Defect Number : D2231984 |  |  |  | Source:
|  | Date Raised:12/01/2023 07:51:00 |  |  |  | Date Completed:20/01/2023 13:01:00
|  | Location: Litter along Nine Mile Ride: Wokingham Without Parish Council Please could litter be cleared along Nine Mile Ride in the parish. We cannot allow outr litter volunteers to clear this busy road because of the safety risks. We suspect a Highways Licence would be required to enable this to be done effectively. |  |  |  | Priority : Planned Maintenance
Description: Litter along Nine Mile Ride: Wokingham Without Parish Council Please could litter be cleared along Nine Mile Ride in the parish. We cannot allow outr litter volunteers to clear this busy road because of the safety risks. We suspect a Highways Licence would be required to enable this to be done effectively.
|  | Defect Number : D2232331 |  |  |  | Source:
|  | Date Raised:23/01/2023 10:19:00 |  |  |  | Date Completed:24/01/2023 09:36:24
|  | Location: Close to Johnson and Johnson Bus Stop |  |  |  | Priority : 24 Hours - Urgent
Description: Please remove loose material and make safe around sunk manhole cover. Road Speed: 40MPH. Approx Road Width: 7.0M. Approx Traffic Flow: High, depending on time of day. Approx HGV / Bus Traffic Flow: Med Footways: Yes Near Bend: No Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: Yes
|  | Defect Number : D2232747 |  |  |  | Source: Inspection Area 3
|  | Date Raised:06/02/2023 12:07:00 |  |  |  | Date Completed:07/02/2023 11:52:25
|  | Location: Nine Miie Ride at Pinewood Campus. |  |  |  | Priority : 24 Hours - Urgent
Description: L3 S3 cat 1b. Please make safe cway damage, marked. Water leak affecting cway has been reported to SE Water. Located at entrance to Johnson & Johnson. Suggest controlling traffic Under Stop / Go for short duration of make safe, Marshall any vehicles in and out of Johnson & Johnson. Sign well back on Nine Mile Ride. Road Speed: 40MPH Approx Road Width: 6M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: medium Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: YES, Johnson & Johnson entrance. Near School: no Near Roundabout: no Other hazard: Avoid peak hours. Overhead cable. TM recommended yes
|  | Defect Number : D2334369 |  |  |  | Source:
|  | Date Raised:04/04/2023 10:24:00 |  |  |  | Date Completed:04/04/2023 10:59:26
|  | Location: Nine Mile Ride 50m from roundabout at Old Wokingham Road. Opposite pond. |  |  |  | Priority : 2 Hour - Emergency
Description: L4 S4 cat 1a. Please make safe cway pothole marked. Please clear up tarmac debris in kerbline. Road Speed: 40MPH Approx Road Width: 6M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: yes Other hazard: TM recommended yes
|  | Defect Number : D2334390 |  |  |  | Source:
|  | Date Raised:04/04/2023 14:11:00 |  |  |  | Date Completed:04/05/2023 10:00:00
|  | Location: Opp 10 Kingsbridge Cottages off Nine Mile Ride |  |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. 1 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked. 0.8 x 0.5 10mm DBM. Edge of cway. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2334391 |  |  |  | Source:
|  | Date Raised:04/04/2023 14:22:00 |  |  |  | Date Completed:04/05/2023 11:15:00
|  | Location: Opposite 11 Kingsbridge cottages off Nine Mile Ride |  |  |  | Priority : 28 Days - Standard Response
Description: 2 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked. 1.8 x 0.5 10mm DBM. Edge of cway. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2334392 |  |  |  | Source:
|  | Date Raised:04/04/2023 14:24:00 |  |  |  | Date Completed:04/05/2023 13:30:00
|  | Location: Opposite 11 Kingsbridge cottages off Nine Mile Ride |  |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. 3 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked. 0.8 x 0.5 10mm DBM. Edge of cway. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2334394 |  |  |  | Source:
|  | Date Raised:04/04/2023 14:28:00 |  |  |  | Date Completed:04/05/2023 12:45:00
|  | Location: Opposite 12 Kingsbridge cottages off Nine Mile Ride |  |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. 4 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked. 4.6 x x 0.7 10mm DBM. Edge of cway. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2334395 |  |  |  | Source:
|  | Date Raised:04/04/2023 14:31:00 |  |  |  | Date Completed:04/05/2023 11:15:00
|  | Location: Opposite 14 Kingsbridge cottages off Nine Mile Ride |  |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. 5 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked. 1.5 x 0.6 10mm DBM. Edge of cway. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2334396 |  |  |  | Source:
|  | Date Raised:04/04/2023 14:34:00 |  |  |  | Date Completed:04/05/2023 10:00:00
|  | Location: Opposite 15 Kingsbridge cottages off Nine Mile Ride |  |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. 6 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked. 0.8 x 0.5 10mm DBM. Centre of cway. 2.3m Road space left, 3.9m if using layby. Very low traffic count. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2334399 |  |  |  | Source:
|  | Date Raised:04/04/2023 14:41:00 |  |  |  | Date Completed:04/05/2023 12:15:00
|  | Location: Opposite 23/24 Kingsbridge cottages off Nine Mile Ride |  |  |  | Priority : 28 Days - Standard Response
Description: L2 S2 CAT2A. 7 of 7 in this road. May need to cone off layby for parking & opposite for clear lane for Traffic. Give & Take. Please carry out permanent reinstatement to cway marked, around gully. 1m2 10mm DBM. Edge of cway. Road Speed: 30MPH Approx Road Width: 4.5M Approx Traffic Flow: medium Approx HGV / Bus Traffic Flow: low Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: yes Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2336190 |  |  |  | Source:
|  | Date Raised:06/06/2023 10:35:00 |  |  |  | Date Completed:06/06/2023 12:51:05
|  | Location: marked on nine mile ride marked opposite the bus stop between Johnson and Johnson and the roundabout with old Wokingham Road. |  |  |  | Priority : 24 Hours - Urgent
Description: 1 of 3 Please make safe pothole marked on nine mile ride marked opposite the bus stop between Johnson and Johnson and the roundabout with old Wokingham Road. Permanent repair if possible, but please let me know. RB Road Speed: 40MPH Approx Road Width: 6.0M. Approx Traffic Flow: med, depending on time of day. Approx HGV / Bus Traffic Flow: med Footways: yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: yes Near School: no Near Roundabout: yes
|  | Defect Number : D2336191 |  |  |  | Source:
|  | Date Raised:06/06/2023 10:38:00 |  |  |  | Date Completed:06/06/2023 12:53:59
|  | Location: marked on nine mile ride marked opposite the bus stop between Johnson and Johnson and the roundabout with old Wokingham Road. |  |  |  | Priority : 24 Hours - Urgent
Description: 2 of 3 Please make safe pothole marked on nine mile ride marked opposite the bus stop between Johnson and Johnson and the roundabout with old Wokingham Road. Permanent repair if possible, but please let me know. Road Speed: 40MPH Approx Road Width: 6.0M. Approx Traffic Flow: med, depending on time of day. Approx HGV / Bus Traffic Flow: med Footways: yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: yes Near School: no Near Roundabout: yes
|  | Defect Number : D2336192 |  |  |  | Source:
|  | Date Raised:06/06/2023 10:38:00 |  |  |  | Date Completed:06/06/2023 12:58:05
|  | Location: marked on nine mile ride marked opposite the bus stop between Johnson and Johnson and the roundabout with old Wokingham Road. |  |  |  | Priority : 24 Hours - Urgent
Description: 3 of 3 Please make safe pothole marked on nine mile ride marked opposite the bus stop between Johnson and Johnson and the roundabout with old Wokingham Road. Permanent repair if possible, but please let me know. Road Speed: 40MPH Approx Road Width: 6.0M. Approx Traffic Flow: med, depending on time of day. Approx HGV / Bus Traffic Flow: med Footways: yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: yes Near School: no Near Roundabout: yes
|  | Defect Number : D2336237 |  |  |  | Source:
|  | Date Raised:07/06/2023 12:04:00 |  |  |  | Date Completed:08/06/2023 10:24:00
|  | Location: Pinewood boxing club, Pinewood Centre, Old Wokingham Road, Wokingham |  |  |  | Priority : 3 Days
Description: Fridge
|  | Defect Number : D2336343 |  |  |  | Source: Street Lighting
|  | Date Raised:09/06/2023 13:05:00 |  |  |  | Date Completed:09/06/2023 14:30:00
|  | Location: ? |  |  |  | Priority : 2 Hour - Emergency
Description: Column 101 NMR reported as hit/leaning - JB requested VH attend as a 2-hour emergency call out on 09.06.23 to make safe, was attended to by VH on same day. Column leaning. Ive pushed it upright but 5he shaft is slightly bent.it is now solid in the ground.Needs new 8m steel column. Will need traffic management for the works.
|  | Defect Number : D2336710 |  |  |  | Source:
|  | Date Raised:22/06/2023 09:21:00 |  |  |  | Date Completed:23/06/2023 08:03:22
|  | Location: Nine Mile Ride, 80m before Johnson and Johnson, coming from Old Wokingham Road. |  |  |  | Priority : 24 Hours - Urgent
Description: Please make safe cway pothole marked. 1m off kerb. May require 2 way Traffic control off peak. Road Speed: 40MPH Approx Road Width: 7M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: no Other hazard: TM recommended
|  | Defect Number : D2336713 |  |  |  | Source:
|  | Date Raised:22/06/2023 09:48:00 |  |  |  | Date Completed:23/06/2023 07:56:09
|  | Location: Nice Mile Ride 40m before Roundabout at Old Wokingham Road. By lamp column 105. |  |  |  | Priority : 24 Hours - Urgent
Description: 1 of 3 at this location. Please make safe cway pothole marked. May require Traffic control. Sign back on Old Wokingham Road. Road Speed: 40MPH Approx Road Width: 7M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: yes Other hazard: off peak working. TM recommended yes
|  | Defect Number : D2336714 |  |  |  | Source:
|  | Date Raised:22/06/2023 09:53:00 |  |  |  | Date Completed:23/06/2023 07:56:53
|  | Location: Nine Mile Ride 40m in from roundabout at Old Wokingham Road. By lamp column 105. |  |  |  | Priority : 24 Hours - Urgent
Description: 2 of 3 at this location. Please make safe cway pothole marked. May require Traffic control. Sign back on Old Wokingham Road. Road Speed: 40MPH Approx Road Width: 7M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: yes Other hazard: off peak working. TM recommended yes
|  | Defect Number : D2336715 |  |  |  | Source:
|  | Date Raised:22/06/2023 09:56:00 |  |  |  | Date Completed:23/06/2023 07:57:38
|  | Location: Nine Mile Ride 40m before Roundabout at Old Wokingham Road. By Lamp column 105. |  |  |  | Priority : 24 Hours - Urgent
Description: 3 of 3 at this location. Please make safe cway pothole marked. May require Traffic control. Sign back on Old Wokingham Road. Road Speed: 40MPH Approx Road Width: 7M Approx Traffic Flow: high Approx HGV / Bus Traffic Flow: high Approx pedestrian volume along Footways: low Near Bend: no Near Pedestrian Crossing: no Near Traffic Signals: no Near Junction: no Near School: no Near Roundabout: yes Other hazard: off peak working. TM recommended yes
|  | Defect Number : D2337676 |  |  |  | Source:
|  | Date Raised:31/07/2023 15:52:00 |  |  |  | Date Completed:01/08/2023 06:41:40
|  | Location: Nine mile ride junction with Heathlands, about 5 or 6 crossings with tactile paving have not been cleaned and need to for H&S reasons. |  |  |  | Priority : Planned Maintenance
Description: Tactile paving at all the pedestrian crossings here are covered with leaves and mud and should be included in the schedule as these help blind and elderly feel the tactile paving at the crossing to know where it is and to help them grip Urbaser - added to 56 day schedule on Day 11 when we are in Crowthorne
|  | Defect Number : D2337962 |  |  |  | Source:
|  | Date Raised:16/08/2023 10:27:00 |  |  |  | Date Completed:16/08/2023 12:12:13
|  | Location: Section of Nine Mile Ride between rail bridge and double roundabouts with Sandhurst Rd. Vegetation is from opposite Thames Water site, to roundabout with Lower Wokingham Rd. |  |  |  | Priority : 24 Hours - Urgent
Description: L2 S3, Please cut back all the vegetation that is encroaching onto the FW. Approx 15m worth, see photos. Road Speed: 30MPH Approx Road Width: 6.0M. Approx Traffic Flow: High, depending on time of day. Approx HGV / Bus Traffic Flow: Med Footways: Yes Near Bend: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: Yes
|  | Defect Number : D2338135 |  |  |  | Source:
|  | Date Raised:23/08/2023 10:23:00 |  |  |  | Date Completed:11/01/2024 13:15:00
|  | Location: At entrance to Pinewood Campus off Nine Mile Ride. |  |  |  | Priority : 28 Days - Standard Response
Description: (1 of 4) Please patch marked area in C-way. Size: 0.7m x 0.6m = 0.42m² Material: 10mm Recommended TM: possible sign and guarding. Road Speed: 40MPH Approx Road Width: 15.0M. Approx Traffic Flow: low, depending on time of day. Approx HGV / Bus Traffic Flow: Low Footways: Yes Near Bend: Yes Near Pedestrian Crossing: Yes Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: No
|  | Defect Number : D2338136 |  |  |  | Source:
|  | Date Raised:23/08/2023 10:26:00 |  |  |  | Date Completed:11/01/2024 13:21:00
|  | Location: At entrance to Pinewood Campus off Nine Mile Ride. |  |  |  | Priority : 28 Days - Standard Response
Description: (2 of 4) Please patch marked area in C-way. Size: 1.1m x 0.7m = 0.8m² Material: 10mm Recommended TM: possible sign and guarding. Road Speed: 40MPH Approx Road Width: 15.0M. Approx Traffic Flow: low, depending on time of day. Approx HGV / Bus Traffic Flow: Low Footways: Yes Near Bend: Yes Near Pedestrian Crossing: Yes Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: No
|  | Defect Number : D2338137 |  |  |  | Source:
|  | Date Raised:23/08/2023 10:28:00 |  |  |  | Date Completed:11/01/2024 14:01:00
|  | Location: At entrance to Pinewood Campus off Nine Mile Ride |  |  |  | Priority : 28 Days - Standard Response
Description: (3 of 4) Please patch marked area in C-way. Size: 0.9m x 0.9m = 0.8m² Material: 10mm Recommended TM: possible sign and guarding. Road Speed: 40MPH Approx Road Width: 15.0M. Approx Traffic Flow: low, depending on time of day. Approx HGV / Bus Traffic Flow: Low Footways: Yes Near Bend: Yes Near Pedestrian Crossing: Yes Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: No
|  | Defect Number : D2338138 |  |  |  | Source:
|  | Date Raised:23/08/2023 10:31:00 |  |  |  | Date Completed:11/01/2024 13:25:00
|  | Location: At entrance to Pinewood Campus off Nine Mile Ride. |  |  |  | Priority : 28 Days - Standard Response
Description: (4 of 4) Please patch marked area in C-way. Size: 1.1m x 1.0m = 1.1m² Material: 10mm Recommended TM: possible sign and guarding. Road Speed: 40MPH Approx Road Width: 15.0M. Approx Traffic Flow: low, depending on time of day. Approx HGV / Bus Traffic Flow: Low Footways: Yes Near Bend: Yes Near Pedestrian Crossing: Yes Near Traffic Signals: No Near Junction: Yes Near School: No Near Roundabout: No
|  | Defect Number : D2338211 |  |  |  | Source:
|  | Date Raised:29/08/2023 15:42:00 |  |  |  | Date Completed:30/08/2023 11:32:00
|  | Location: Nine Mile Ride Wokingham, pinned on map by customer near St Sebastians Close |  |  |  | Priority : 3 Days
Description: Single large tyre
Orders In Date Order - Latest First
| Road Name: |  |  | 44701102 - Nine Mile Ride - Wokingham, 44701102
|  | Order Number: ORD2202076 |  |  |  | Originator:
|  | Date Raised: 06/12/2022 08:39:57 |  |  |  | Date Completed: 22/12/2022 10:15:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  |  | Date Instructed: 06/12/2022 08:43:14
|  | Description: Clear 3 gullies including jetting gully outlets . Also, jet heawalls. Refer to attached plan edged in red Location: between junction with Palmer close and THREE BIRCHES, NINE MILE RIDE, WOKINGHAM, RG40 3DY - Refer to attached plan edged in red TM may be required. Any problems call Notes: Near a junction Near a roundabout approx. road width 5.2m varies |  |  |  | Priority: 28 Days
|  | Order Number: ORD2202226 |  |  |  | Originator:
|  | Date Raised: 19/12/2022 16:30:04 |  |  |  | Date Completed: 04/01/2023 13:53:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  |  | Date Instructed: 19/12/2022 16:30:58
|  | Description: Free 1 jammed gully lid - Location: FMC ID number: FMC_20909 TM may be required. Any problems call Near a bend Near a bridge Footway – yes Near mobile homes site Approx. road width 5.4m varies traffic count medium/high depending on time of day |  |  |  | Priority: 31 Days
|  | Order Number: ORD2300527 |  |  |  | Originator:
|  | Date Raised: 17/03/2023 07:56:24 |  |  |  | Date Completed: 20/03/2023 10:00:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  |  | Date Instructed: 17/03/2023 08:02:22
|  | Description: Lamp Column 112(38) (id:16979) Approx. 155m east of Heathlands Rd x-rds Steel 8m Fabrikat 8M01A(114)PT Philips SGS203/100GTG 100w SP, LED Philips Luma 10500lm 4000k, Telensa Telecell NEMA+In Dim M (000339540200) Both units 112 & 113 have been reported as out of light, please investigate and repair on first visit, if possible, if not please advise of further works that are required. Last Telensa communication was: - 03.03.23 |  |  |  | Priority: 41 Days
|  | Order Number: ORD2300603 |  |  |  | Originator:
|  | Date Raised: 30/03/2023 20:14:12 |  |  |  | Date Completed: 19/04/2023 11:30:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  |  | Date Instructed: 30/03/2023 20:15:26
|  | Description: Reflective "Keep Left" bollard no. B631(NON) Nine Mile Ride (B3430), Wokingham Without (On island app. 250m west of Old Wokingham Rd rbt) - unique ID 026539. Clean bollard shell - currently very dirty which is reducing visibility/refelectivity (see W2349535). |  |  |  | Priority: 28 Days
|  | Order Number: ORD2300604 |  |  |  | Originator:
|  | Date Raised: 30/03/2023 20:18:21 |  |  |  | Date Completed: 19/04/2023 11:15:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  |  | Date Instructed: 30/03/2023 20:19:14
|  | Description: Reflective "Keep Left" bollard no. B633(NON) Nine Mile Ride (B3430), Wokingham Without (On island app. 245m west of Old Wokingham Rd rbt) - unique ID 026540. Clean bollard shell - currently very dirty which is reducing visibility/refelectivity (see W2349535). |  |  |  | Priority: 28 Days
|  | Order Number: ORD2300655 |  |  |  | Originator:
|  | Date Raised: 04/04/2023 20:56:55 |  |  |  | Date Completed: 11/04/2023 08:19:32
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  |  | Date Instructed: 04/04/2023 21:26:47
|  | Description: Defect: Make Safe x33 Potholes Location: Nine Mile Ride - Palmer Close-Old Wokingham Road R'about (see Photos) Carriageway or Footway: C/Way Photos attached: Yes Mapping attached: No Road Speed: 40 MPH Approx Road Width: 6m Approx Traffic Flow: Medium to High Footways: One side until after Pinewood Campus Near Bend: No Near a Hill: Yes Near Pedestrian Crossing: No Near Traffic Signals: No Near Junction: Yes - Pinewood campus Near School: No Near Roundabout: No Additional TM: No |  |  |  | Priority: 1 Days
|  | Order Number: ORD2301175 |  |  |  | Originator:
|  | Date Raised: 09/06/2023 13:12:15 |  |  |  | Date Completed: 03/04/2024 11:01:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  |  | Date Instructed: 09/06/2023 13:16:23
|  | Description: Lamp Column 101(49) (id:16991) Approx. 15m west of New Wokingham Rd rbt Steel 8m CU FR608003 tb plt gv Philips Luma 1B R3 10500lm N P, LED Philips Luma 10500lm 4000k, Telensa Telecell NEMA+In Dim M (000339551800) Remove existing lantern & retain onsite, remove column to tip. Install 1no SG 8 metre post top column complete with new number (101) Re-fit retained lantern to new column. Will require 1no transfer of underground service (Private) Carry out 1no electrical test once energised. Traffic management may be required: - |  |  |  | Priority: (6) Days
|  | Order Number: ORD2301241 |  |  |  | Originator:
|  | Date Raised: 20/06/2023 10:23:20 |  |  |  | Date Completed: 15/05/2025 11:40:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  |  | Date Instructed: 22/04/2024 16:05:20
|  | Description: SM 2024-25 Footway Schemes - Nine Mile Ride (9647) Provisional sum code utilised to represent additional uplift value - to be removed in Actual Sub Total. Slurry seal @15mm, sqm area of 10mm product x1.5 to encompass value. |  |  |  | Priority: 343 Days
|  | Order Number: ORD2301243 |  |  |  | Originator:
|  | Date Raised: 20/06/2023 11:28:33 |  |  |  | Date Completed: 15/05/2025 11:35:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  |  | Date Instructed: 22/04/2024 16:02:57
|  | Description: SM 2024-25 Footway Schemes - Nine Mile Ride (9649) Provisional sum code utilised to represent additional uplift value - to be removed in Actual Sub Total. Slurry seal @15mm, sqm area of 10mm product x1.5 to encompass value. |  |  |  | Priority: 343 Days
|  | Order Number: ORD2301262 |  |  |  | Originator:
|  | Date Raised: 21/06/2023 13:53:15 |  |  |  | Date Completed: 25/03/2025 11:28:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  |  | Date Instructed: 22/04/2024 15:39:32
|  | Description: SM 2024-25 Footway Schemes - Nine Mile Ride (9634) Provisional sum code utilised to represent additional uplift value - to be removed in Actual Sub Total. Slurry seal @15mm, sqm area of 10mm product x1.5 to encompass value. |  |  |  | Priority: 343 Days
|  | Order Number: ORD2301370 |  |  |  | Originator:
|  | Date Raised: 12/07/2023 09:49:41 |  |  |  | Date Completed: 18/09/2023 16:00:00
|  | Location: 44701102 - NINE MILE RIDE - WOKINGHAM |  |  |  | Date Instructed: 20/07/2023 10:05:38
|  | Description: Structural Maintenance 2023-24, Asphalt Preservation. NINE MILE RIDE 7919 'Provisional Sum' code used to represent the material cost of the asphalt preservation product (in m2). See attached BoQ for further information. |  |  |  | Priority: 255 Days
|  | V1.9 | 15/04/2026 10:10:51
Page 43 of 43